# Call forward sheet

Site address:	22 Lake Lane, Kawana	Project no:	001/2021
Client:	Bob Smith	Building surveyor:	Lindsay Brown
Contact no:	07 3765 4319	Office number:	07 3009 3211

|  |  |  | Ordering |  | Supplier details |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Task/activity | Order no. | Order day | Delivery date | Material supplier | Contractor | Supplier contact no. | Instructions or comments |
| Base stage |  |  |  |  |  |  |  |  |
| 21 | Order toilet | 100100 | 10/03/21 | 15/03/21 |  | Hire Me | 3847 7788 | Emptied weekly. Call for unscheduled service. |
| 22 | Order crossover | 100105 | 10/03/21 | 15/03/21 |  | Hire Me | 3847 7788 |  |
| 23 | Order temporary fencing | 100106 | 10/03/21 | 16/03/21 |  | Melbourne Temp Fencing | 3587 5547 |  |
| 24 | Earthworks | 100109 | 3/03/21 | 18/03/21 |  | Jack Excavations | 3745 1154 |  |
| 25 | Prepare flooring | 100110 | 15/03/21 | 18/03/21 |  | Carpenters R Us | 3536 4780 |  |
| 26 | Stormwater rough in | 100111 | 3/03/21 | 19/03/21 |  | Paul’s Plumbing | 3854 4547 |  |
| 27 | Under slab sewer | 100112 | 8/03/21 | 19/03/21 |  | Paul’s Plumbing | 3854 4547 |  |
| 28 | Order timber | 100114 | 3/03/21 | 18/03/21 | Timber Specialists |  | 3541 1111 |  |