Apply project risk management techniques

Templates

Contents

Stakeholder Analysis Template	2

Communications Plan Template	3

Communication Requirements Analysis Worksheet	4

Contract Change Control System Checklist and Worksheet	5

Contract Performance Report Template	6

Generic Change Request Template	7

Lessons Learned Documentation Template	8

Project Change Control System Development Checklist and Worksheet	9

Project Change Request Tracking Report	10

Project Status Review Meeting Guideline Sheet	11

Project Risk Prioritisation Worksheet/Template	12

Project Risk Categorisation Worksheet	14

Project Risk Review Matrix	15

Project Change Request Template	16

Rating Impacts for a Risk	17

Risk Brainstorming Session Worksheet	18

Risk Identification – SWOT Analysis	19

Risk Management Plan Template	21

Risk Response Plan Template	23

Schedule Change Control System Development Checklist and Worksheet	24

Schedule Change Request Template	25

Workaround Planning Worksheet	26

# Stakeholder Analysis Template

| # Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| Project Stakeholder | Specific Information Needs | Best Source of Information Needed | Planned Method of Delivery | Timing Considerations |
| Project Manager | Progress updates, risk reports | Risk register, progress reports | Meetings, emails | Weekly |
| Customer #1 | Milestones achieved, quality standards | Progress reports | Written reports, meetings | Monthly or as requested |
| Customer #2 | Design and construction updates | Progress reports, design documents | Meetings, emails | Monthly |
| Customer #3 | Compliance with agreed specifications | Compliance and progress updates | Written reports | As required |
| Performing Organisation | Budget adherence, project performance | Financial and progress documentation | Internal reports | Monthly |
| Project Team Members | Task responsibilities, deadlines | Project plans, schedules | Emails, meetings | Weekly |
| Sponsor | Overall progress, financial updates | Financial and project status reports | Presentations, written updates | Quarterly |
| Senior Executive | High-level project performance overview | Executive summaries | Presentations, emails | Quarterly or as required |
| Other Internal Stakeholders | Operational impact, resource needs | Internal project updates | Internal meetings, reports | As required |
| Other External Stakeholders | Compliance with local regulations | Compliance and progress documentation | Written reports | As required |

# Communications Plan Template

| # Project Name: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |  |
| # Date: |  |  |  |  |  |  |
| Key Stakeholders (Distribution Schedule) | Stakeholder Issues | Key Messages to Communicate | Communication Methods to be Used (written, one-on-one, electronic, meetings, etc.) | Description of Specific Communications (content, format, level of detail, etc.) | Timing Issues (see also Bar Chart, Project Schedule) | Other |
| Client | Budget, design changes, smart tech integration | Milestone achievements, budget status | Written reports, meetings | High-level progress reports, updated drawings | Bi-weekly or as requested |  |
| Senior Management | Strategic alignment, risk exposure | Project status, risk register summary | Presentations, executive summaries | Dashboard updates, risk summaries | Monthly or as required |  |
| Sponsor | ROI, financial performance | Budget adherence, milestone achievements | Written updates, presentations | Financial reports, milestone tracking | Quarterly |  |
| Project team members | Task assignments, deadlines, risks | Task responsibilities, schedule updates | Meetings, emails | Weekly task lists, risk logs, action items | Weekly |  |
| Employees | Safety, work schedules | WHS protocols, daily tasks | Toolbox talks, emails | Safety briefings, daily work plans | Daily |  |
| Subcontractors | Task coordination, safety compliance | Work schedules, site access | One-on-one, written | Task checklists, safety briefings | Daily |  |
| Suppliers | Delivery timelines, material specs | Delivery schedules, product requirements | Emails, phone calls | Delivery plans, material specifications | As required |  |
| Unions | Workplace safety, compliance | WHS compliance | Written reports | Safety adherence reports, compliance updates | As required |  |
| Government Agencies | Regulatory compliance | Permit status, inspection results | Written reports, meetings | Compliance documentation, inspection reports | As required |  |
| News Media | Noise, traffic, environmental impact | Construction schedule, mitigation measures | Noticeboards, community meeting | Compliance documentation, inspection reports | As required |  |
| Community | Zoning, building code compliance | Permit applications, compliance updates | Written reports, meetings | Compliance documentation, inspection reports | As required |  |
| Other |  |  |  |  |  |  |

# Communication Requirements Analysis Worksheet

| # Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| General Area of Communication Need | Information Needed, and for Whom? | Optimum Information Format(s) | How is this communication essential to success of project? | Decision to implement Yes/No |
| Project Organisation Relationships | Roles, responsibilities, reporting lines for project team (builders, consultants, engineers) | Org charts, contact lists, project briefs | Ensures clarity in task ownership and accountability | Yes |
| Stakeholder Responsibility Relationships | Expectations, deliverables, and timelines for stakeholders (client, sponsor, council) | Stakeholder matrix, Gantt charts, meeting minutes | Aligns stakeholder expectations and reduces conflict | Yes |
| Sponsor Relationships | Funding sources, budget approvals, sponsor expectations | Budget reports, sponsor updates, formal agreements | Maintains financial control and sponsor confidence | Yes |
| Senior Executive Relationships | Oversight, strategic alignment, risk management | Executive summaries, dashboards, risk registers | Ensures project aligns with broader organisational goals | Yes |
| Disciplines, Departments, Specialties, etc. | Coordination between trades (electrical, structural, HVAC, smart tech) and consultants | Technical drawings, scopes of work, coordination meetings | Prevents clashes and ensures compliance with NCC and smart building standards | Yes |
| Logistics of Project Staffing by Location | Site access, staff schedules, safety protocols | Site maps, rosters, WHS documentation | Ensures safe and efficient site operations | Yes |
| External: Media | Project milestones, community impact, promotional updates | Press releases, social media posts, newsletters | Builds public trust and transparency | No (unless public interest is high) |
| External: Community | Noise, traffic, environmental impact, construction schedule | Community notices, signage, council updates | Maintains good neighbour relations and avoids complaints | Yes |
| External: Government, Regulatory Agencies | Compliance with Building Regulation 2021, NCC, QDC, QBCC licensing | Formal submissions, inspection reports, certificates | Ensures legal compliance and avoids penalties | Yes |
| Other | Insurance, sustainability, fire safety, smart tech integration | Policy documents, certificates, environmental reports | Protects project viability and ensures resilience and innovation | Yes |

# Contract Change Control System Checklist and Worksheet

| # Project Name: |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| # Date: |  |  |
| Determine those responsible for approving or rejecting proposed contract changes: Be sure to provide for appropriate review of all changes. Project Director – Final authority on scope and budget changes Contracts Administrator – Reviews documentation and compliance Site Supervisor – Approves minor site-related changes Client Representative – Required for changes affecting design or cost Legal/Contracts Team – Reviews contractual implications |  |  |
| Define any types of changes qualifying for automatic approval without review: Minor material substitutions of equal or better quality Adjustments to delivery dates within a 3-day window Administrative corrections (e.g., typos, formatting) |  |  |
| Define steps by which contracts may be changed, including: |  |  |
| Paperwork Change Request Form submitted by contractor or consultant Supporting documentation (drawings, cost estimates, impact analysis) |  |  |
| Tracking systems Logged in project management software (e.g., Procore or Buildertrend) Unique change ID assigned for traceability |  |  |
| Dispute resolution procedures Initial review by Contracts Administrator Escalation to Project Director and Legal if unresolved Mediation clause invoked if necessary |  |  |
| Approval levels required <$5,000: Site Supervisor $5,000–$20,000: Contracts Administrator $20,000 or design-impacting: Project Director and Client Representative |  |  |
| Describe how contract changes will be integrated with the project's integrated change control system: All approved changes are updated in the master contract and project schedule Budget adjustments reflected in financial tracking tools Notifications sent to all affected stakeholders Change log maintained for audit and review |  |  |
| Additional Remarks: |  |  |
| Submitted | Name/Title: AH - CA | Date: 11/8/25 |
| Approval | Name/Title: JP - CM | Date: 11/8/25 |

# Contract Performance Report Template

| # Project Name: |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| # Date: |  |  |
| # Status of Vendor Performance, relative to project/contract objectives: |  |  |
| # Scope (On Scope? If not, how serious) On scope. All deliverables are aligned with the original contract. Minor adjustments (e.g., prefabricated panel substitutions) have been approved and documented. |  |  |
| # Schedule (On schedule? Ahead or behind by how much, etc.) Slightly behind schedule by approximately 3 working days due to delays in steel framing delivery. Recovery plan in place with adjusted work sequencing. |  |  |
| # Cost (On budget? Under or over by how much, etc.) On budget. Current expenditure is within 1.5% of projected costs. Contingency fund remains available. |  |  |
| # Quality Meets quality standards. All inspections passed to date (foundation, steel framing, concrete slab). Prefabricated components meet specifications. |  |  |
| # Progress Report (What is completed, what is in process, key changes made, etc.): Completed: Site preparation, foundation pour, steel framing In Process: Installation of prefabricated wall panels, electrical rough-in Key Changes: Substitution of prefabricated panel supplier due to availability; approved by client and documented |  |  |
| Forecasting (Estimate of future project status and progress): Project expected to recover schedule within 2 weeks No major risks identified at this stage Next milestones: Lock-up stage by early September, smart tech installation by mid-September |  |  |
| Other Issues or Comments: No community complaints received Council inspections proceeding on schedule Vendor communication has been proactive and responsive |  |  |
| Submitted | Name/Title: AH - CA | Date: 11/8/25 |
| Approved | Name/Title: JP – PD | Date: 11/8/25 |

# Generic Change Request Template

| Project Name: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |
| Date: |  |  |  |  |  |
| Person(s) Requesting Change: Client Rep |  |  |  |  |  |
| Change Number: CR-001 |  |  |  |  |  |
| Type of Change Requested: |  |  |  |  |  |
|  | Project Scope Change |  | Project Budget Change |  | Project Schedule Change |

|  | Project Procurement/Contract Change |  | Other (specify) |
| --- | --- | --- | --- |
| # Detailed Description of Change: Request to incorporate an additional smart meeting room on the ground floor, equipped with video conferencing, automated lighting, and climate control. |  |  |  |
| # Reason for Change Requested: The client has revised their operational requirements and now anticipates a higher frequency of remote meetings. The additional smart meeting room will support hybrid work arrangements and improve collaboration. |  |  |  |

| # Effect on Project Cost: |  |  |
| --- | --- | --- |
| Projected Cost Overrun of approximately: 6.5 % |  |  |
| Estimated Cost Reduction of approximately: % |  |  |
| # Effect on Schedule: |  |  |
| Planned Project Completion Date: 15/11/25 |  |  |
| New Project Completion Date: 29/11/25 |  |  |
| Additional Remarks: This change aligns with the client's long-term operational goals and enhances the building’s marketability by integrating advanced smart office features. While it introduces a moderate cost and time impact, the benefits in functionality and future-proofing are considered worthwhile. Risk mitigation strategies will include early procurement of smart tech components and proactive coordination with council for approvals. |  |  |
| Approval | Project Manager: RW | Date: 11/8/25 |
| Approval | (Other): | Date: |

# Lessons Learned Documentation Template

| # Project Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Number: LL-001 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: Early Engagement of Smart Technology Suppliers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: Assistant Contracts Administrator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group:* |  |  |  | Initiating |  | Planning |  | Executing |  |  |  | Controlling |  |  |  |  |  | Closing |  |  |
| Specific Project Management Process Being Used: Change Control Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific Practice, Tool or Technique Being Used: Change Request Evaluation and Impact Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the action undertaken? A change request was submitted to add a smart meeting room with advanced technology features during the construction phase. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? The change was approved, but it caused a 2-week delay and a 6.5% cost overrun due to late procurement and design revisions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result: Minimal or no delay and cost impact, with smoother integration of smart technologies. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? Early consultation with smart technology suppliers during the planning phase and inclusion of flexible design provisions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific Lesson Learned? Engaging smart technology suppliers early in the planning phase helps avoid delays and cost overruns when integrating advanced systems later in the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? When a project includes evolving client requirements or emerging technologies not fully scoped at initiation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? Include provisional allowances and consult with tech suppliers during early design stages to anticipate future changes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? In upcoming procurement and fit-out stages, to ensure timely coordination with suppliers and subcontractors. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used in a future project? During the planning phase of future commercial builds involving smart systems, to improve scope definition and supplier engagement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learned: (check one) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Executive(s) |  |  | Project Manager(s) |  |  |  | Project Team(s) |  |  |  |  |  |  | All Staff |  |  |  |  |
|  |  |  | Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learned be disseminated? (check all that apply) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | e-mail |  |  | Intranet/Web site |  |  |  | Tip Sheet/FAQ |  |  |  |  |  |  | Library |  |  |  |  |
|  |  |  | Other: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Have you attached reference(s), example(s) and/or additional material(s)? |  |  |  |  |  |  |  |  |  |  |  |  |  | yes |  |  |  |  | no |
| Name(s) of attachment(s): - CR-001 Change Request Form (hypothetically attached – would be if it wasn’t a simulation) - Updated Project Schedule (Rev 3) (hypothetically attached – would be if it wasn’t a simulation) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Project Change Control System Development Checklist and Worksheet

# Project Name:

Prepared by:

# Date:

Determine those responsible for approving or rejecting proposed project changes: Be sure to provide for appropriate review of all changes. # Project Director # Client Representative # Commercial Manager # Contracts Administrator # Design Consultant (for technical changes) # Finance Officer (for budget-related changes) # All changes must be reviewed and approved by the Project Director, Client Representative, and Commercial Manager. Technical, financial, and contractual changes require additional review by relevant specialists.

Define Roles and Responsibilities of approving person or body: Project Director: Reviews all change requests, assesses impact, coordinates implementation, and ensures alignment with overall project objectives. Client Representative: Approves changes that affect scope, budget, or client requirements. Commercial Manager: Reviews contractual obligations, commercial risks, and ensures alignment with procurement and financial strategy. Contracts Administrator: Ensures contractual compliance and updates documentation. Design Consultant: Evaluates feasibility and design implications. Finance Officer: Assesses cost impact and budget alignment.

Get key stakeholder agreement on roles and responsibilities (list stakeholders): Project Director Client Representative Commercial Manager Contracts Administrator Design Consultant Finance Officer Senior Manager (for escalation if needed)

Define any types of changes qualifying for automatic approval without review: Minor adjustments to internal layout that do not affect structural elements, cost, or schedule Substitutions of materials with equivalent specifications and cost Administrative updates (e.g., contact details, document formatting)

Define steps by which contracts may be changed, including:

Paperwork Submit formal Change Request Form (CRF) Include impact assessment and justification Attach revised drawings or specifications if applicable

Tracking Systems Log change in Change Control Register Update project schedule and budget tracking tools Maintain version control of documents

Dispute Resolution procedures Refer to contract clauses for dispute resolution Escalate unresolved issues to senior management or legal advisor Document all communications and decisions

Approval levels required Changes under $5,000: Project Director Changes $5,000–$20,000: Project Director + Client Representative Changes over $20,000 or affecting scope/schedule: Full stakeholder review including Commercial Manager

Describe how contract changes will be integrated with the project's integrated change control system: # All approved contract changes will be: # Logged in the central Change Control Register # Reflected in updated project plans, budgets, and schedules # Communicated to all affected team members and subcontractors # Reviewed during regular project meetings # Included in project documentation and lessons learned records

# Project Change Request Tracking Report

| Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| Project Manager: RW |  |  |  |  |
| Project Change Request Administrator: Contracts Administrator |  |  |  |  |
| Change Number | Change Name | Change Requestor | Status of Change | Comments |
| 1 | Addition of Smart Meeting Room | Client Rep | Approved | 1. Reviewed and approved by Project Director, Client Rep, and Commercial Manager. |
|  |  |  |  | 2. |
| 2 | Substitution of Flooring Material | Site Supervisor | Approved | 1. Material meets spec and cost; no impact on schedule. |
|  |  |  |  | 2. |
| 3 | Relocation of Electrical Panel | Electrical Subcontractor | Under Review | 1. Requires design consultant input and cost assessment. |
|  |  |  |  | 2. |
| 4 | Extension of Landscaping Scope | Client Rep | Rejected | 1. Outside original scope and budget; not aligned with project objectives. |
|  |  |  |  | 2. |
| 5 | Upgrade to Solar Panel System | Sustainability Consultant | Approved | 1. Approved with minor cost increase; aligns with green building goals. |
|  |  |  |  | 2. |

# Project Status Review Meeting Guideline Sheet

| # Project Name: |  |  |  |
| --- | --- | --- | --- |
| Prepared by: |  |  |  |
| # Date: |  |  |  |
| # Meeting Participants: Project Director # Client Representative # Commercial Manager # Contracts Administrator # Site Supervisor # Design Consultant # Finance Officer |  |  |  |
| # Date of Meeting: 8/8/25 |  |  |  |
| # Status of Project Work to Date, Including Progress Reported This Period: |  |  |  |
| Structural steel framing completed Concrete slabs poured for all floors Prefabricated wall panels delivered and installation underway Electrical and plumbing rough-ins commenced Smart technology supplier engaged for system integration planning |  |  |  |
| # Special Problems or Issues to be Addressed: |  |  |  |
| Issue: |  | Who Will Address: |  |
| Delay in smart meeting room design approval |  | Design Consultant |  |
| Procurement delay for smart lighting system |  | Commercial Manager |  |
| Clarification on revised landscaping scope |  | Client Representative |  |
| Budget adjustment for solar panel upgrade |  |  |  |
| # Plans For Next Period: Complete installation of prefabricated panels Begin internal fit-out and ceiling grid installation Finalise smart meeting room design and commence installation Submit updated project schedule and budget for review Conduct mid-project quality assurance inspection |  |  |  |
| # Other Notes and Concerns: Weather delays have been minimal and within contingency Stakeholder communication remains strong Risk register to be updated with new smart tech integration risks Next review meeting scheduled for 26 August 2025 |  |  |  |
| Status Report Forwarded to: Commerical Manager and Project Director |  |  |  |
| # Name: Jaime P | # Title: Commercial Manager |  | # Date: 8/8/25 |
| # Name: Justin P | # Title: Project Director |  | # Date: 8/8/25 |
| # Name: | # Title: |  | # Date: |

# Project Risk Prioritisation Worksheet/Template

# Project Name:

Prepared by:

# Date:

### By Rank:

| Identified Risk | Low Risk (Check √) | Medium Risk (Check √) | High Risk (Check √) | Work Breakdown Structure Level |
| --- | --- | --- | --- | --- |
| Delay in smart technology procurement |  |  |  |  |
| Weather-related construction delays |  |  |  |  |
| Design changes requested late by client |  |  |  |  |
| Safety incident on site |  |  |  |  |

### By Required Response:

| Identified Risk | Can Be Handled Later (specify planned response) | Requires Immediate Response! (specify planned actions and who is assigned responsibility) |
| --- | --- | --- |
| Delay in council approvals |  | Expedite submission and follow-up; Design Consultant to lead |
| Budget overrun due to material cost fluctuations | Monitor market trends and adjust contingency |  |
| Miscommunication between subcontractors | Improve coordination in weekly meetings |  |

### By Area of Expected Impact:

| Area of Impact | Identified Risks affecting this area | Level of Risk: High, Medium, Low | Basis for High-Risk Assessments |
| --- | --- | --- | --- |
| Cost | Budget overrun, smart tech delays | Medium | Smart tech integration adds cost; material prices fluctuate |
| Schedule | Council approval delays, procurement delays | High | Delays could push completion beyond contractual deadline |
| Functionality | Late design changes, smart tech issues | Medium | Changes may affect layout and system integration |
| Quality | Safety incidents, incomplete documentation | High | Safety risks and poor documentation can compromise build quality and compliance |

# Project Risk Categorisation Worksheet

# Project Name:

Prepared by:

# Date:

NOTE: List all identified project risks within each category. Retain this information for reference throughout the risk management process:

Technical, quality, or performance risks—such as reliance on unproven or complex technology, unrealistic performance goals, changes to the technology used or to industry standards during the project. - Integration of smart office technologies with existing systems - Use of prefabricated materials requiring precise installation tolerances - Potential incompatibility between smart lighting and HVAC automation systems - Changes in industry standards for energy efficiency during construction - Reliance on new subcontractors for smart tech installation

Project-management risks—such as poor allocation of time and resources, inadequate quality of the project plan, poor use of project management disciplines. - Inadequate time allocated for council approvals - Poor coordination between subcontractors and suppliers - Delays in finalising design changes requested by the client - Incomplete documentation for contract variations - Underestimation of time required for smart system commissioning

Organisational risks—such as cost, time, and scope objectives that are internally inconsistent, lack of prioritisation of projects, inadequacy or interruption of funding, and resource conflicts with other projects in the organisation. - Conflicting priorities between client departments (e.g., IT vs. Facilities) - Limited availability of internal resources for decision-making - Budget constraints affecting scope flexibility - Delayed internal approvals for change requests - Resource conflicts with other concurrent projects

External risks—such as shifting legal or regulatory environment, labour issues, changing owner priorities, country risk, and weather. Force majeure risks such as earthquakes, floods, and civil unrest generally require disaster recovery actions rather than risk management. - Delays in council approvals due to regulatory backlog - Weather-related disruptions (e.g., heavy rain affecting slab pours) - Shifting client priorities due to market conditions - Supply chain disruptions for imported smart tech components - Labour shortages or industrial action affecting subcontractors

# Project Risk Review Matrix

| # Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| # Meeting Date: 11/8/25 |  |  |  |  |
| # Purpose of Meeting: To review current project risks, assess any changes in risk status, and update mitigation strategies. |  |  |  |  |
| CHANGES IN RISK FACTORS: Notes |  |  |  |  |
| Identified Risk | Changes in Probability Of Occurrence | Changes in Priority | Changes in Ownership/ Responsibility | Changes in Needed Response |
| Smart tech procurement delays | Increased due to supplier backlog | Raised to High | Commercial Manager | Escalate supplier engagement and explore alternate vendors |
| Weather-related delays | Decreased due to improved forecast | Lowered to Low | Site Supervisor | Continue monitoring; no immediate action needed |
| Council approval delays | No change | Remains Medium | Design Consultant | Maintain regular follow-ups with council |
| Safety incident on site | No change | Remains High | Site Supervisor | Reinforce safety training and conduct site audits |
| Budget overrun from material costs | Increased due to market volatility | Raised to Medium | Finance Officer | Review contingency allocation and update cost forecasts |
| Miscommunication between subcontractors | Decreased due to improved coordination | Lowered to Low | Project Director | Maintain weekly coordination meetings |
| # Additional Notes/Comments/Agreements/Next Steps: Commercial Manager to provide updated procurement timeline for smart systems by next meeting Design Consultant to submit revised landscaping plan for client review Finance Officer to prepare updated budget forecast reflecting recent material cost trends Next risk review meeting scheduled for 26 August 2025 Risk register to be updated and redistributed to all stakeholders |  |  |  |  |

# Project Change Request Template

| # Project Name: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |
| # Date: |  |  |  |  |  |
| # Changes are being made to the following: |  |  |  |  |  |
|  | Project Charter |  |  | Project Management Approach |  |
|  | Scope Statement |  |  | Work Breakdown Structure |  |
|  | Performance Measurement Baselines |  |  | Major Milestones and Target Dates |  |
|  | Key Staff |  |  | Risk Management Plan |  |
|  | Scope Management Plan |  |  | Schedule Management Plan |  |
|  | Cost Management Plan |  |  | Quality Management Plan |  |
|  | Staffing Management Plan |  |  | Communications Management Plan |  |
|  | Risk Response Plan |  |  | Procurement Management Plan |  |
| Changes to Supporting Detail? (explain): Updated architectural drawings, revised procurement schedule, and adjusted budget forecast to reflect the addition of smart meeting room and solar panel upgrade. |  |  |  |  |  |
| Description of Changes being made: 1. Addition of Smart Meeting Room Risk Issues Prompting Changes: Client requested enhanced remote collaboration capabilities. Corrective Action: Design revised to include smart tech; procurement and installation scheduled; budget adjusted. |  |  |  |  |  |
| 2. Upgrade to Solar Panel System Risk Issues Prompting Changes: Sustainability consultant identified opportunity for improved energy efficiency. Corrective Action: Specification updated; procurement initiated; minor cost increase approved. |  |  |  |  |  |
| 3. Adjustment to Project Schedule Risk Issues Prompting Changes: Delays in smart tech procurement and council approvals. Corrective Action: Milestones revised; contingency time reallocated; stakeholders notified. |  |  |  |  |  |
| Stakeholders being notified: |  |  |  |  |  |
| Name/Title: Jaime P |  | Signature: JP |  |  | Date: 11/8/25 |
| Name/Title: Justin P |  | Signature: JP |  |  | Date: 11/8/25 |

# Rating Impacts for a Risk

| # Project Name: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |  |
| # Date: |  |  |  |  |  |
| Evaluating Impact of a Risk on Major Project Objectives (ordinal scale or cardinal, non-linear scale) |  |  |  |  |  |
| Project Objective | Very Low .05 | Low .1 | Moderate .2 | High .4 | Very High .8 |
| Cost | Insignificant Cost Increase | <5% Cost Increase | 5–10% Cost Increase | 10–20% Cost Increase | >20% Cost Increase |
| Schedule | Insignificant Schedule Slippage | Schedule Slippage <5% | Overall Project Slippage 5–10% | Overall Project Slippage 10–20% | Overall Project Schedule Slips >20% |
| Scope | Scope Decrease Barely Noticeable | Minor Areas of Scope Are Affected | Major Areas of Scope Are Affected | Scope Reduction Unacceptable to the Client | Project End Item Is Effectively Useless |
| Quality | Quality Degradation Barely Noticeable | Only Very Demanding Applications Are Affected | Quality Reduction Requires Client Approval | Quality Reduction Unacceptable to the Client | Project End Item Is Effectively Unusable |

The impacts on project objectives can be assessed on a scale from Very Low to Very High or on a numerical scale.
The numerical (cardinal) scale shown here is non-linear, indicating that the organization wishes specifically
to avoid risks with high and very-high impact.

# Risk Brainstorming Session Worksheet

| # Project Name: |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepared by: |  |  |  |  |
| # Date: |  |  |  |  |
| # Session Facilitator: Scott C |  |  |  |  |
| Title/Position: Site Manager |  |  |  |  |
| # Participating Group: Project Team – including representatives from design, contracts, commercial, site supervision, and finance |  |  |  |  |
| # Location: |  |  |  |  |
| Identified Risk | Probability of Occurrence | Potential Impact | Proposed Actions | Identified by Whom? |
| Delay in smart tech procurement | High | High – schedule and cost | Engage alternate suppliers; expedite procurement | Commercial Manager |
| Council approval delays | Medium | Medium – schedule | Submit early and follow up regularly | Design Consultant |
| Safety incident on site | Medium | High – quality and compliance | Conduct refresher training and audits | Site Supervisor |
| Budget overrun due to material cost | Medium | Medium – cost | Monitor market trends; adjust contingency | Finance Officer |
| Late client design changes | Medium | Moderate – scope and schedule | Implement scope freeze; improve client communication | Project Director |
| Miscommunication between subcontractors | Low | Low – coordination | Weekly coordination meetings and shared documentation | Contracts Administrator |
| Weather-related delays | Low | Low – schedule | Monitor forecasts and adjust buffers | Site Supervisor |

# Risk Identification – SWOT Analysis

# Project Name:

Prepared by:

# Date:

Project Manager: Rob W

SWOT Analysis Facilitator: Justin P – Project Director

SWOT Analysis Participants: Project Team – Design Consultant, Commercial Manager, Site Supervisor, Finance Officer, Contracts Administrator

SWOT Analysis Recorder: Contracts Administrator

Date of SWOT Analysis: 11/8/25

Project Strengths: (What potential strengths exist about the project, the project team, the sponsor, the organisation structure, the client, the project schedule, the project budget, the product of the project, etc.?) - Use of prefabricated materials to reduce construction time and improve quality - Strong collaboration between project team members and stakeholders - Clear client vision and commitment to smart office technologies - Experienced subcontractors and consultants engaged - Well-defined project scope and schedule with contingency allowances

Project Weaknesses: (What potential weaknesses exist about the project, the project team, the sponsor, the organisation structure, the client, the project schedule, the project budget, the product of the project, etc.?) - Late-stage design changes requested by client impacting schedule - Limited flexibility in budget for unexpected scope additions - Dependence on external suppliers for smart technology components - Tight approval timelines for council and regulatory bodies - Documentation gaps in variation tracking and change control

Project Opportunities: (What potential opportunities exist in regard to achieving the project requirements, the product requirements, the project schedule, the project resources, the project quality, etc.?) - Integration of smart technologies enhances building functionality and market appeal - Use of prefabricated materials allows faster construction and reduced labour costs - Potential for future expansion or modular upgrades due to flexible design - Strong stakeholder engagement supports collaborative problem-solving - Sustainability features (e.g., solar panels) may qualify for government incentives or certifications

Project Threats: (What potential threats exist in regard to achieving the project requirements, the product requirements, the project schedule, the project resources, the project quality, etc.?) - Delays in council approvals could impact schedule and handover - Supply chain disruptions for smart tech components may affect installation timelines - Budget constraints could limit flexibility in responding to client changes - Safety incidents on site could lead to work stoppages or reputational damage - Weather-related disruptions may affect critical construction phases like slab pouring

# Risk Management Plan Template

# Project Name:

Prepared by:

# Date:

# Description of Risk Management Methodology to be Used: A proactive and structured approach will be used to identify, assess, monitor, and respond to risks throughout the project lifecycle. The methodology includes regular risk reviews, stakeholder engagement, and integration with project controls.

# Approaches - Risk identification through brainstorming, SWOT analysis, and historical data - Risk assessment using qualitative and quantitative methods - Risk prioritisation using impact/probability matrices - Risk response planning (avoid, mitigate, transfer, accept) - Continuous monitoring and updating of the risk register

# Tools - Risk Register - Risk Matrix - Change Control System - Lessons Learned Log - Project Management Software (e.g., MS Project or equivalent)

# Data Sources - Historical data from similar projects - Expert judgment from consultants and contractors - Client requirements and specifications - Regulatory and environmental guidelines - Supplier and subcontractor input

# Roles and Responsibilities: - Project Director: Oversees risk management strategy and approves major risk responses - Contracts Administrator: Maintains the risk register and coordinates risk documentation - Commercial Manager: Assesses financial and contractual risks - Design Consultant: Evaluates design-related risks and technical feasibility - Site Supervisor: Monitors operational risks and safety compliance - Client Representative: Provides input on client-side risks and priorities

# Risk Management Action #1: Mitigate risk of smart technology procurement delays by engaging alternate suppliers, confirming delivery timelines, and adjusting procurement schedule.

# Team Leader Commercial Manager

# Team Members Contracts Administrator, Finance Officer, Procurement Coordinator

# Support Project Director, Supplier Representatives

# Risk Management Action #2: Mitigate risk of safety incidents on site by conducting refresher safety training, updating site signage, and performing weekly safety audits.

# Team Leader Site Supervisor

# Team Members Safety Officer, Contracts Administrator, Construction Foreman

# Support Project Director, WHS Consultant

# [Add sections as needed]

# Budget: Estimated $5,000 allocated for safety training sessions, updated signage, and consultant support. This is covered under the project’s contingency allowance.

# Timing: (Describe how risk management will relate to the project life cycle, and at what points it will be reviewed during the execution of the project) Risk management activities will be integrated throughout the project life cycle: - Initiation & Planning: Initial risk identification and planning - Execution: Ongoing monitoring, implementation of mitigation actions, and weekly reviews - Controlling: Formal risk reviews during monthly status meetings and after any major change - Closing: Final risk assessment and documentation of lessons learned Risk reviews will occur: - Bi-weekly during active construction phases - Immediately following any incident or change request - At key milestones (e.g., completion of framing, fit-out commencement)

Risk Response Plan Template

# Project Name:

Prepared by:

# Date:

# Description of Risk Identified: Delay in procurement and installation of smart meeting room technology due to supplier backlog and integration complexity.

# Person(s) Responsible: Commercial Manager, Contracts Administrator, Project Director

# Results from Risk Analysis: Probability: High Impact: High (Cost and Schedule) Risk Rating: Critical Affected Areas: Procurement, Schedule, Budget, Functionality

# Agreed Responses (avoidance, transference, mitigation, acceptance):

Response #1 Mitigation: Engage alternate suppliers and confirm delivery timelines early.

Response #2 Acceptance: Accept minor delay and adjust project schedule with contingency buffer.

Response #3 Transference: Include penalty clauses in supplier contracts for late delivery.

# Residual Risk Level: Moderate – Risk remains but is controlled through proactive supplier management and schedule adjustment.

# Action Steps: - Identify and contact alternate smart tech suppliers - Update procurement schedule and notify stakeholders - Revise contract terms to include delivery guarantees - Adjust project milestones and communicate changes - Monitor supplier performance and escalate issues promptly

# Budget & Time for Response: - Budget: Estimated $12,000 for alternate supplier engagement and contract adjustments - Time: 2 weeks added to project schedule; response actions initiated immediately and reviewed weekly

# Contingency/Fallback Plans: - Use temporary meeting room setup with basic AV equipment until smart systems are installed - Reallocate internal resources to accelerate installation once components arrive - Escalate to senior management if supplier delays exceed 3 weeks

# Schedule Change Control System Development Checklist and Worksheet

# Project Name:

Prepared by:

# Date:

Determine those responsible for approving or rejecting proposed schedule changes: Be sure to provide for appropriate review of all changes. - Project Director - Client Representative - Commercial Manager All schedule changes must be reviewed and approved by the Project Director, Client Representative, and Commercial Manager to ensure alignment with contractual obligations, client expectations, and overall project strategy.

Define categories of schedule changes qualifying for automatic approval without review: - Minor adjustments to internal task durations that do not affect critical path or milestone dates - Re-sequencing of non-dependent tasks for efficiency - Administrative updates to scheduling software (e.g., formatting, naming conventions)

Describe how schedule change control will be integrated with the integrated change control system: Schedule changes will be: - Logged in the Change Control Register - Evaluated alongside scope and cost impacts - Reflected in updated project schedule, performance baselines, and status reports - Communicated to all affected stakeholders - Reviewed during regular project meetings and risk assessments - Documented in the Lessons Learned Log for future reference

Define steps by which schedule documents may be changed, including:

Paperwork - Submit a formal Schedule Change Request Form - Include justification, impact analysis, and revised schedule snapshot - Attach supporting documentation (e.g., updated Gantt chart, milestone adjustments)

Tracking Systems - Update project scheduling software (e.g., MS Project or equivalent) - Maintain version control and audit trail of changes - Reflect changes in the integrated project dashboard

Dispute Resolution Procedures - Refer to contract clauses for schedule-related disputes - Escalate unresolved issues to senior management or legal advisor - Document all communications and decisions

Approval Levels Required - Changes affecting non-critical tasks: Project Director - Changes affecting milestones or client deliverables: Project Director + Client Representative - Changes with contractual or financial implications: Full stakeholder review including Commercial Manager

# Schedule Change Request Template

| # Project Name: |  |  |
| --- | --- | --- |
| Prepared by: |  |  |
| # Date: |  |  |
| # Person(s) Requesting Change: Client Representative |  |  |
| # Change Number: SC-001 |  |  |
| # Detailed Description of Schedule Change: Request to extend the project schedule by two weeks to accommodate the procurement and installation of smart meeting room technology, which was added through a recent approved change request. |  |  |
| # Reason for Schedule Change Requested: Supplier delays and additional integration requirements for smart systems have impacted the original timeline. The extension ensures proper installation and testing without compromising quality. |  |  |
| # Effect on Project Cost: |  |  |
| Projected Cost Overrun of approximately: 6.5% |  |  |
| Estimated Cost Reduction of approximately: % |  |  |
| # Overall Effect on Schedule: |  |  |
| Planned Project Completion Date: 15/11/25 |  |  |
| New Project Completion Date: 29/11/25 |  |  |
| Additional Remarks: The schedule extension has been reviewed and is considered necessary to maintain quality standards and meet client expectations for smart office functionality. No impact on other critical path activities is expected. |  |  |
| Approval | Project Manager: JP | Date: 11/8/25 |
| Approval | (Other): | Date: |

# Workaround Planning Worksheet

# Project Name:

Prepared by:

# Date:

# Description of Emerging Risk Identified: Delay in delivery of smart meeting room technology due to supplier backlog and international shipping constraints.

# Person(s) Responsible: Commercial Manager, Contracts Administrator

# Results from Risk Analysis (if applicable): Probability: High Impact: High (affects schedule and functionality) Risk Rating: Critical Affected Areas: Schedule, Cost, Client Satisfaction

# Description of Plan to Respond (avoidance, transference, mitigation, acceptance): Mitigation and Acceptance Mitigate by sourcing alternate suppliers and adjusting installation sequence Accept minor delay and adjust project schedule accordingly

# Description of Residual Risk Level: Moderate – Risk remains due to potential supplier limitations, but impact is reduced through proactive planning.

# Action Steps: Identify and contact alternate suppliers Confirm availability and delivery timelines Adjust installation schedule to accommodate late delivery Communicate revised timeline to stakeholders Monitor supplier performance and escalate if necessary

# Budget & Time for Response: Budget: Estimated $10,000 for alternate supplier engagement and expedited shipping Time: 2-week extension to project schedule

# Contingency/Fallback Plans: Use temporary meeting room setup with basic AV equipment Reallocate internal resources to accelerate installation once components arrive Escalate to senior management if delays exceed 3 weeks

Additional Notes: This workaround ensures continuity of construction activities while maintaining client expectations for smart functionality. Weekly progress reviews will include supplier updates and risk reassessment.