## Comparison Program
|  | Last Updated: | 2021-03-08
|  | Status: | For ECI Agreement - Revision A
|  | Prepared by: | RB-McN |  |  | Jan 2021 | Feb 2021 |  |  | Feb 2021 | Mar 2021 |  |  | Mar 2021 | Apr 2021 |  |  | Apr 2021 | May 2021 |  |  | May 2021 | Jun 2021 |  |  | Jun 2021 | Jul 2021 |  |  | Jul 2021 | Aug 2021 |  |  | Aug 2021 | Sep 2021 |  |  | Sep 2021 | Oct 2021 |  |  | Oct 2021 | Nov 2021 |  |  | Nov 2021 | Dec 2021 |  |  | Dec 2021 | Jan 2022 |  |  | Jan 2022 | Feb 2022 |  |  | Feb 2022 | Mar 2022 |  |  | Mar 2022 | Apr 2022 |  |  | Apr 2022 | May 2022 |  |  | May 2022 | Jun 2022 |  |  | Jun 2022 | Jul 2022 |  |  | Jul 2022 | Aug 2022 |  |  | Aug 2022 | Sep 2022 |  |  | Sep 2022 | Oct 2022 |  |  | Oct 2022 | Nov 2022 |  |  | Nov 2022
Activity |  |  | Responsible Party | ~ Duration | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
ROCKPOOL - 154-156 Marine Pde Coolangatta
ROL AND EASEMENT REALTED ITEMS
|  | Agreement upon Easement contents | Sunland / Rainbow 2021 | Milestone | 4: u; 1: Agreement upon Easement contents
|  | ROL issued to Titles Office and Title Payment | Sunland | 2 weeks | 3: ROL issued to Titles Office and Title Payment
|  | Settlement of Lot (30 September 2021) | Rainbow 2021 / Sunland | Milestone | 4: u; 1: Settlement of Lot (30 September 2021)
DEVELOPMENT REALTED ITEMS
|  | Consent from Land Holder for purposes of DA Submission | Rainbow 2021 | Latest | 4: u; 1: Consent from Land Holder for purposes of DA Submission
|  | DA Application - Code Assessable Submission Assessment | Rainbow 2021 | 4 months | 4: u; 1: DA Application - Code Assessable Submission Assessment
|  | Allow OPW Applications under Code to be successful | McNab | 2 months | 1: Allow OPW Applications under Code to be successful
|  | DA Application - Impact Assessable Submission Assessment | Rainbow 2021 | 4 months | 4: u; 1: DA Application - Impact Assessable Submission Assessment
|  | OPW Preparation - Excavation and Sand Management Plan | McNab | 2 weeks | 4: OPW Preparation - Excavation and Sand Management Plan
|  | OPW Preparation - Excavation Stability Report | McNab | 2 weeks | 4: OPW Preparation - Excavation Stability Report
|  | OPW Preparation - Acid Sulfate Management Plan | McNab | 2 weeks | 4: OPW Preparation - Acid Sulfate Management Plan
|  | OPW Preparation - Dewatering Management Plan | McNab | 2 weeks | 4: OPW Preparation - Dewatering Management Plan
|  | OPW Preparation - Civil Service Connections Water/Sewer/Storm | McNab | 2 weeks | 4: OPW Preparation - Civil Service Connections Water/Sewer/Storm
|  | Easement works For Construction design (access agreed w/ Sunland) | McNab | 6 weeks | 1: Easement works For Construction design (access agreed w/ Sunland)
SALES RELATED ITEMS
|  | Sales and Marketing Materials | Joe Adsett Architects | 3 weeks | 3: Sales and Marketing Materials
|  | Publishing of Marketing Materials | Rainbow 2021 | Milestone | 3: u; 4: Publishing of Marketing Materials
SALES DISPLAY RELATED ITEMS
|  | Structural rectification works internal | McNab | 4 weeks | 3: Design; 1: Fabrication
|  | Structural rectification works external | McNab | 5 weeks | 3: Design; 4: Instal
|  | Display Fitout Works | McNab | 7 weeks | 4: Display Fitout Works
|  | Display CofC forecast | McNab | Milestone | 4: u; 1: Display CofC forecast
|  | Sales Display Open to Public | McNab | Milestone | 1: u; 2: Sales Display Open to Public
|  | Decomissioning of the Sales Display and make good | McNab | 2 weeks | 1: Decomissioning of the Sales Display and make good
DESIGN & CONSTRUCTION (Impact Scheme directed)
|  | Sign Up Consultants:Structure,Civil,Services,Wind,Geotech,Certifier,Fire Eng |  |  | 1: Sign Up Consultants:Structure,Civil,Services,Wind,Geotech,Certifier,Fire Eng
|  | Design Coordination Meeting - 01 | 2021-04-01 | 1 day | 1: u; 2: Design Coordination Meeting - 01
|  | Design Coordination Meeting - 02 (prelim services spatials lock) | 2021-04-08 | 1 day | 2: u; 3: Design Coordination Meeting - 02 (prelim services spatials lock)
|  | Design Coordination Meeting - 03 (review D&C Peer Review) | 2021-04-15 | 1 day | 3: u; 4: Design Coordination Meeting - 03 (review D&C Peer Review)
|  | Design Coordination Meeting - 04 (post Peer reivew docs published) | 2021-04-22 | 1 day | 4: u; 1: Design Coordination Meeting - 04 (post Peer reivew docs published)
|  | Design Coordination Meeting - 05 (w/ all Designers incl Subbies) | 2021-06-24 | 1 day | 4: u; 1: Design Coordination Meeting - 05 (w/ all Designers incl Subbies)
|  | Design Coordination Meeting - 06 | 2021-07-01 | 1 day | 1: u; 2: Design Coordination Meeting - 06
|  | Design Coordination Meeting - 07 | 2021-07-08 | 1 day | 2: u; 3: Design Coordination Meeting - 07
|  | Design Coordination Meeting - 08 | 2021-07-15 | 1 day | 3: u; 4: Design Coordination Meeting - 08; 4: DEFINED MILESTONE TERMS
|  | Design Coordination Meeting - 09 | 2021-07-22 | 1 day | 4: u; 1: Design Coordination Meeting - 09; 1: 50% Model Development means: Spatially areas are established. Routes for services are also understood.
|  | DESIGN MILESTONES |  |  | 1: Basic coordination and further development needed for interactions between services and structure.
|  | Revision to Impact Scheme; 3 Basements and Height (March impact) | JAA | 4 weeks | 4: u; 1: Revision to Impact Scheme; 3 Basements and Height (March impact); 1: 100% Model Development means: All spatials are locked in that allow for the next level of detial to commence.
|  | 50% Model Coordination of Disciplines (March Impact Scheme) | JAA/McNab/Edge/Services | 5 weeks | 4: u; 1: 50% Model Coordination of Disciplines (March Impact Scheme); 1: This stage can only be achieved after the input / verification of the spatials from a D&C Peer Review.
|  | 50% Documentation Produced (Impact Scheme) | McNab/JAA | 2 weeks | 2: u; 3: 50% Documentation Produced (Impact Scheme); 1: Note: Model Development is different to the 50/70/100% Design milestones in that these reflect actual drawings
|  | 100% Model Development by JAA for all spatials | McNab/JAA | Milestone | 4: u; 1: 100% Model Development by JAA for all spatials; 1: produced from the model. Published drawings contain dimensions and annotations suitable for printed use.
|  | 70% Design Development Review (Impact Scheme) | McNab/JAA/Rainbow2021 | Milestone | 4: u; 1: 70% Design Development Review (Impact Scheme)
|  | 100% Design Development Review (Impact Scheme) | McNab/JAA/Rainbow2021 | Milestone | 4: u; 1: 100% Design Development Review (Impact Scheme)
|  | Issued For Construction Achieved (Impact Scheme)(pre start on site) | McNab/JAA/Rainbow2021 | Milestone | 4: u; 1: Issued For Construction Achieved (Impact Scheme)(pre start on site)
|  | Issued For Construction UPDATE - Impact Approval | McNab/JAA/Rainbow2021 | Milestone | 4: Issued For Construction UPDATE - Impact Approval; 1: u
CONTRACT FORMATION
|  | Market Testing / Pricing and Estimating | McNab | 4 weeks | 3: Market Testing / Pricing and Estimating
|  | Client review of McNab Project Price (agreement to proceed to D&C) | McNab | 1 week | 4: Client review of McNab Project Price (agreement to proceed to D&C)
|  | D&C Head Contract Formation and Execution | McNab | 2 weeks | 4: u; 1: D&C Head Contract Formation and Execution
|  | Opportunity for D&C Services procurement | McNab | 4 weeks | 1: Opportunity for D&C Services procurement
MOBILISATION PRELIMINARIES
|  | Building Approval Stage 1 - In-Ground Structure (Code Scheme) | McNab |  | 3: u; 4: Building Approval Stage 1 - In-Ground Structure (Code Scheme)
|  | Easement works | McNab | 6 weeks | 3: Easement works
|  | Site Establishment | McNab | Milestone | 3: Site Establishment
|  | Building Approval Stage 2 - Structure to Level 01 (Code Scheme) | McNab |  | 1: u; 2: Building Approval Stage 2 - Structure to Level 01 (Code Scheme)
|  | Building Approval Stage 3 - All Build (Impact)(Code not considered) | McNab |  | 1: u; 2: Building Approval Stage 3 - All Build (Impact)(Code not considered)
|  | Building Approval Stage 4 - Contingency for Impact Scheme Delay | McNab |  | 3: Building Approval Stage 4 - Contingency for Impact Scheme Delay; 4: u
[5 empty] | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
[6 empty] | Jan 2021 | Feb 2021 |  |  | Feb 2021 | Mar 2021 |  |  | Mar 2021 | Apr 2021 |  |  | Apr 2021 | May 2021 |  |  | May 2021 | Jun 2021 |  |  | Jun 2021 | Jul 2021 |  |  | Jul 2021 | Aug 2021 |  |  | Aug 2021 | Sep 2021 |  |  | Sep 2021 | Oct 2021 |  |  | Oct 2021 | Nov 2021 |  |  | Nov 2021 | Dec 2021 |  |  | Dec 2021 | Jan 2022 |  |  | Jan 2022 | Feb 2022 |  |  | Feb 2022 | Mar 2022 |  |  | Mar 2022 | Apr 2022 |  |  | Apr 2022 | May 2022 |  |  | May 2022 | Jun 2022 |  |  | Jun 2022 | Jul 2022 |  |  | Jul 2022 | Aug 2022 |  |  | Aug 2022 | Sep 2022 |  |  | Sep 2022 | Oct 2022 |  |  | Oct 2022 | Nov 2022 |  |  | Nov 2022
CONSULTANT AND AUTHORITY FEES COST FLOW
Last Updated: RB-McN 16/03/2021
|  | CONSULTANT AND AUTHORITY FEES | SCHEDULED FEE TOTAL |  | 1: 1/2 CONCEPT CLAIM; 1: 1/2 CONCEPT CLAIM; 1: 1/2 DD CLAIMED; 1: 1/2 DD CLAIMED; 1: 1/2 IFC CLAIMED; 1: 3/4 IFC CLAIMED; 1: 100% IFC CLAIMED; 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.; u 1: 10% CONCS.SERV.
|  | Architect |  |  | 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Certifier | 24346 |  | 1: 1500; 1: 1500; 1: 0; 1: 3173; 1: 3173; 1: 3500; 1: 1750; 1: 1750; 1: 800; u 1: 800; u 1: 800; u 1: 800; u 1: 800; u 1: 800; u 1: 800; u 1: 800; u 1: 800; u 1: 800
|  | Structural Engineer | 122300 |  | 1: 12750; 1: 12750; 1: 0; 1: 22750; 1: 22750; 1: 25650; 1: 12825; 1: 12825; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Civil Engineer | 36000 |  | 1: 0; 1: 0; 1: 0; 1: 10500; 1: 10500; 1: 7500; 1: 3750; 1: 3750; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Geotech | 16500 |  | 1: 5250; 1: 5250; 1: 0; 1: 3000; 1: 3000; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Fire Engineer | 14500 |  | 1: 0; 1: 0; 1: 0; 1: 5800; 1: 5800; 1: 1000; 1: 500; 1: 500; 1: 90; u 1: 90; u 1: 90; u 1: 90; u 1: 90; u 1: 90; u 1: 90; u 1: 90; u 1: 90; u 1: 90
|  | Mechanical | 28600 |  | 1: 4430; 1: 4430; 1: 0; 1: 6405; 1: 6405; 1: 2215; 1: 1107.5; 1: 1107.5; 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250
|  | Electrical | 29205 |  | 1: 4760; 1: 4760; 1: 0; 1: 6200; 1: 6200; 1: 2392.5; 1: 1196.25; 1: 1196.25; 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250
|  | Hydraulic (Revit capable) | 15785 |  | 1: 2465; 1: 2465; 1: 0; 1: 3455; 1: 3455; 1: 1232.5; 1: 616.25; 1: 616.25; 1: 148; u 1: 148; u 1: 148; u 1: 148; u 1: 148; u 1: 148; u 1: 148; u 1: 148; u 1: 148; u 1: 148
|  | Fire Services | 14855 |  | 1: 2320; 1: 2320; 1: 0; 1: 3250; 1: 3250; 1: 1160; 1: 580; 1: 580; 1: 139.5; u 1: 139.5; u 1: 139.5; u 1: 139.5; u 1: 139.5; u 1: 139.5; u 1: 139.5; u 1: 139.5; u 1: 139.5; u 1: 139.5
|  | Traffic impact Assessment | 10000 |  | 1: 1325; 1: 1325; 1: 0; 1: 2475; 1: 2475; 1: 600; 1: 300; 1: 300; 1: 120; u 1: 120; u 1: 120; u 1: 120; u 1: 120; u 1: 120; u 1: 120; u 1: 120; u 1: 120; u 1: 120
|  | Wind Consultant | 16500 |  | 1: 8250; 1: 8250; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Dilapidation Report by Structural Engineer | 15000 |  | 1: 7500; 1: 7500; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Display Structural Rectification |  |  | 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
[15 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
|  | Retention Systems / Piling D&C | 30000 |  | 1: 7500; 1: 7500; 1: 0; 1: 7500; 1: 7500; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Pot Holling Survey and Services Locating | 20000 |  | 1: 10000; 1: 10000; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | CCTV of sewer and storwater services | 10000 |  | 1: 5000; 1: 5000; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Acoustic | 16550 |  | 1: 1625; 1: 1625; 1: 0; 1: 750; 1: 750; 1: 3975; 1: 1987.5; 1: 1987.5; 1: 385; u 1: 385; u 1: 385; u 1: 385; u 1: 385; u 1: 385; u 1: 385; u 1: 385; u 1: 385; u 1: 385
|  | DDA | 10500 |  | 1: 0; 1: 0; 1: 0; 1: 4000; 1: 4000; 1: 1250; 1: 625; 1: 625; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Structural Peer Review: | 9500 |  | 1: 0; 1: 0; 1: 0; 1: 4250; 1: 4250; 1: 500; 1: 250; 1: 250; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Section J/thermal comfort | 11000 |  | 1: 1500; 1: 1500; 1: 0; 1: 2500; 1: 2500; 1: 1500; 1: 750; 1: 750; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Façade Engineering, Vert Termination, FP1.4 report, Design Reivew | 12000 |  | 1: 3000; 1: 3000; 1: 0; 1: 3000; 1: 3000; 1: 0; 1: 0; 1: 0; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Traffic Engineering | 14800 |  | 1: 0; 1: 0; 1: 0; 1: 3700; 1: 3700; 1: 2450; 1: 1225; 1: 1225; 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250; u 1: 250
|  | Landscaping | 30710 |  | 1: 3915; 1: 3915; 1: 0; 1: 10075; 1: 10075; 1: 1365; 1: 682.5; 1: 682.5; 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0; u 1: 0
|  | Waste Services | 10400 |  | 1: 1800; 1: 1800; 1: 0; 1: 2400; 1: 2400; 1: 1000; 1: 500; 1: 500
|  | Flood report | 8000 |  | 1: 4000; 1: 4000; 1: 0
|  | QFES referral agency assessment fees | 44656.68 |  | 1: 44656.68
|  | CoGC Fees per Plumbing Fixtures | 64761 |  | 1: 64761
|  | Energex connection and services agreement costs | 0
|  | OPW Re-routing of sewer and stormwater infrastructure | 898 |  | 1: 898
|  | OPW Stormwater connection | 770 |  | 1: 770
|  | OPW connection to water asset | 770 |  | 1: 770
|  | OPW connection to sewer asset | 770 |  | 1: 770
|  | OPW Minor change fee (20% of the associated fees) | 641.6 |  | 1: 641.6
|  | OPW Bulk Earthworks associated fees | 1983 |  | 1: 1983
|  | OPW Application costs - Civil Engineering works + GIA | 1100 |  | 1: 1100
|  | OPW Application costs - Landscaping external of lot. | 541 |  | u 1: 541
|  | OPW Application costs - Landscaping internal of lot. Incl GIA | 1556.4 |  | u 1: 1556.4
|  | OPW Application costs -Tree works | 246 |  | 1: 246
|  | OPW Application costs - VXO and Footpaths + permissable change | 521 |  | 1: 521
[7 empty] | 0 |  |  |  | 0 |  |  |  | 88890 |  |  |  | 88890 |  |  |  | 109417.68 |  |  |  | 110620 |  |  |  | 105183 |  |  |  | 59552.6 |  |  |  | 28645 |  |  |  | 28645 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2432.5 |  |  |  | 2432.5 |  |  |  | 2432.5 |  |  |  | 2432.5 |  |  |  | 2432.5 |  |  |  | 2432.5 |  |  |  | 2432.5 |  |  |  | 2432.5 |  |  |  | 4529.9 |  |  |  | 2432.5
|  |  | 646265.68 |  | 4: 0; 1: Feb 2021; 4: Feb 2021; 1: Mar 2021; 4: Mar 2021; 1: Apr 2021; 4: Apr 2021; 1: May 2021; 4: May 2021; 1: Jun 2021; 4: Jun 2021; 1: Jul 2021; 4: Jul 2021; 1: Aug 2021; 4: Aug 2021; 1: Sep 2021; 4: Sep 2021; 1: Oct 2021; 4: Oct 2021; 1: Nov 2021; 4: Nov 2021; 1: Dec 2021; 4: Dec 2021; 1: Jan 2022; 4: Jan 2022; 1: Feb 2022; u 4: Feb 2022; u 1: Mar 2022; u 4: Mar 2022; u 1: Apr 2022; u 4: Apr 2022; u 1: May 2022; u 4: May 2022; u 1: Jun 2022; u 4: Jun 2022; u 1: Jul 2022; u 4: Jul 2022; u 1: Aug 2022; u 4: Aug 2022; u 1: Sep 2022; u 4: Sep 2022; u 1: Oct 2022; u 4: Oct 2022; u 1: Nov 2022; u 4: Nov 2022
Formulas:
RB-McN = [RB-McN, row above]+7

## Sheet2
ROCKPOOL ECI CONSULTANT AND AUTHORITY FEES CASH FLOW
Last Updated: BE-McN 17/03/2021
CONSULTANT AND AUTHORITY FEES | SCHEDULED FEE TOTAL | [5 empty] | 1/2 CONCEPT CLAIM |  | 1/2 CONCEPT CLAIM |  |  |  | 1/2 DD CLAIMED |  | ECI Cost Total | 1/2 DD CLAIMED |  | 1/2 IFC CLAIMED |  | 3/4 IFC CLAIMED |  | 100% IFC CLAIMED | [5 empty] | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV. |  | 10% CONCS.SERV.
Architect | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Certifier | 24346 | [5 empty] | 1500 |  | 1500 |  | 0 |  | 3173 |  | 6173 | 3173 |  | 3500 |  | 1750 |  | 1750 | [5 empty] | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800 |  | 800
Structural Engineer | 122300 | [5 empty] | 12750 |  | 12750 |  | 0 |  | 22750 |  | 48250 | 22750 |  | 25650 |  | 12825 |  | 12825 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Civil Engineer | 36000 | [5 empty] | 0 |  | 0 |  | 0 |  | 10500 |  | 10500 | 10500 |  | 7500 |  | 3750 |  | 3750 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Geotech | 16500 | [5 empty] | 5250 |  | 5250 |  | 0 |  | 3000 |  | 13500 | 3000 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Fire Engineer | 14500 | [5 empty] | 0 |  | 0 |  | 0 |  | 5800 |  | 5800 | 5800 |  | 1000 |  | 500 |  | 500 | [5 empty] | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90 |  | 90
Mechanical | 28600 | [5 empty] | 4430 |  | 4430 |  | 0 |  | 6405 |  | 15265 | 6405 |  | 2215 |  | 1107.5 |  | 1107.5 | [5 empty] | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
Electrical | 29205 | [5 empty] | 4760 |  | 4760 |  | 0 |  | 6200 |  | 15720 | 6200 |  | 2392.5 |  | 1196.25 |  | 1196.25 | [5 empty] | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
Hydraulic (Revit capable) | 15785 | [5 empty] | 2465 |  | 2465 |  | 0 |  | 3455 |  | 8385 | 3455 |  | 1232.5 |  | 616.25 |  | 616.25 | [5 empty] | 148 |  | 148 |  | 148 |  | 148 |  | 148 |  | 148 |  | 148 |  | 148 |  | 148 |  | 148
Fire Services | 14855 | [5 empty] | 2320 |  | 2320 |  | 0 |  | 3250 |  | 7890 | 3250 |  | 1160 |  | 580 |  | 580 | [5 empty] | 139.5 |  | 139.5 |  | 139.5 |  | 139.5 |  | 139.5 |  | 139.5 |  | 139.5 |  | 139.5 |  | 139.5 |  | 139.5
Traffic impact Assessment | 10000 | [5 empty] | 1325 |  | 1325 |  | 0 |  | 2475 |  | 5125 | 2475 |  | 600 |  | 300 |  | 300 | [5 empty] | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120 |  | 120
Wind Consultant | 16500 | [5 empty] | 8250 |  | 8250 |  | 0 |  | 0 |  | 16500 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Dilapidation Report by Structural Engineer | 15000 | [5 empty] | 7500 |  | 7500 |  | 0 |  | 0 |  | 15000 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Display Structural Rectification | [6 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Retention Systems / Piling D&C | 30000 | [5 empty] | 7500 |  | 7500 |  | 0 |  | 7500 |  | 22500 | 7500 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Pot Holling Survey and Services Locating | 20000 | [5 empty] | 10000 |  | 10000 |  | 0 |  | 0 |  | 20000 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CCTV of sewer and storwater services | 10000 | [5 empty] | 5000 |  | 5000 |  | 0 |  | 0 |  | 10000 | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Acoustic | 16550 | [5 empty] | 1625 |  | 1625 |  | 0 |  | 750 |  | 4000 | 750 |  | 3975 |  | 1987.5 |  | 1987.5 | [5 empty] | 385 |  | 385 |  | 385 |  | 385 |  | 385 |  | 385 |  | 385 |  | 385 |  | 385 |  | 385
DDA | 10500 | [5 empty] | 0 |  | 0 |  | 0 |  | 4000 |  | 4000 | 4000 |  | 1250 |  | 625 |  | 625 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Structural Peer Review: | 9500 | [5 empty] | 0 |  | 0 |  | 0 |  | 4250 |  | 4250 | 4250 |  | 500 |  | 250 |  | 250 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Section J/thermal comfort | 11000 | [5 empty] | 1500 |  | 1500 |  | 0 |  | 2500 |  | 5500 | 2500 |  | 1500 |  | 750 |  | 750 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Façade Engineering, Vert Termination, FP1.4 report, Design Reivew | 12000 | [5 empty] | 3000 |  | 3000 |  | 0 |  | 3000 |  | 9000 | 3000 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Traffic Engineering | 14800 | [5 empty] | 0 |  | 0 |  | 0 |  | 3700 |  | 3700 | 3700 |  | 2450 |  | 1225 |  | 1225 | [5 empty] | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250 |  | 250
Landscaping | 30710 | [5 empty] | 3915 |  | 3915 |  | 0 |  | 10075 |  | 17905 | 10075 |  | 1365 |  | 682.5 |  | 682.5 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Waste Services | 10400 | [5 empty] | 1800 |  | 1800 |  | 0 |  | 2400 |  | 6000 | 2400 |  | 1000 |  | 500 |  | 500
Flood report | 8000 | [5 empty] | 4000 |  | 4000 |  | 0 |  |  |  | 8000
0
McNab ECI Management Fee | 66000 | [5 empty] | 16500 |  | 16500 |  | 16500 |  | 16500 |  | 66000
0
QFES referral agency assessment fees | 44656.68 | [11 empty] | 44656.68 |  | 44656.68
CoGC Fees per Plumbing Fixtures | 64761 | [14 empty] | 64761
Energex connection and services agreement costs | 0
OPW Re-routing of sewer and stormwater infrastructure | 898 | [14 empty] | 898
OPW Stormwater connection | 770 | [14 empty] | 770
OPW connection to water asset | 770 | [14 empty] | 770
OPW connection to sewer asset | 770 | [14 empty] | 770
OPW Minor change fee (20% of the associated fees) | 641.6 | [16 empty] | 641.6
OPW Bulk Earthworks associated fees | 1983 | [14 empty] | 1983
OPW Application costs - Civil Engineering works + GIA | 1100 | [16 empty] | 1100
OPW Application costs - Landscaping external of lot. | 541 | [42 empty] | 541
OPW Application costs - Landscaping internal of lot. Incl GIA | 1556.4 | [42 empty] | 1556.4
OPW Application costs -Tree works | 246 | [14 empty] | 246
OPW Application costs - VXO and Footpaths + permissable change | 521 | [16 empty] | 521
|  |  | 0 |  | 0 |  | 105390 |  | 105390 |  | 16500 |  | 166339.68 |  | 393619.68 | 175381 |  | 59552.6 |  | 28645 |  | 28645 |  | 0 |  | 0 |  | 2432.5 |  | 2432.5 |  | 2432.5 |  | 2432.5 |  | 2432.5 |  | 2432.5 |  | 2432.5 |  | 2432.5 |  | 4529.9 |  | 2432.5
| 712265.68 | #REF! | Feb 2021 | Feb 2021 | Mar 2021 | Mar 2021 | Apr 2021 | Apr 2021 | May 2021 | May 2021 | Jun 2021 | Jun 2021 | Jul 2021 | Jul 2021 |  | Aug 2021 | Aug 2021 | Sep 2021 | Sep 2021 | Oct 2021 | Oct 2021 | Nov 2021 | Nov 2021 | Dec 2021 | Dec 2021 | Jan 2022 | Jan 2022 | Feb 2022 | Feb 2022 | Mar 2022 | Mar 2022 | Apr 2022 | Apr 2022 | May 2022 | May 2022 | Jun 2022 | Jun 2022 | Jul 2022 | Jul 2022 | Aug 2022 | Aug 2022 | Sep 2022 | Sep 2022 | Oct 2022 | Oct 2022 | Nov 2022 | Nov 2022

## Sheet1
Week Commencing | Blue House | GREEN | Red Sea | Fisheries | Staff Accommodation | Fly Camp | Total
House
2014-08-25 | 0 H’Brook until Dec | 0 H’Brook until Dec | 6(expat) | 40 | 50 (4 mouldy) | 0 | 96 expat + 12 national
12(national)
2014-09-01 | “ | “ | 0 | 40 | 50 (4 mouldy) | 0 | 90
2014-09-08 | “ | “ | 0 | 40 | 50 (4 mouldy) | 0 | 90
2014-09-15 | “ | “ | 0 | 40 | 50 (4 mouldy) | 0 | 90
2014-09-22 | “ | “ | 0
2014-09-29 | “ | “ | 0
2014-10-06 | “ | “ | 0
2014-10-13 | “ | “ | 0
2014-10-20 | “ | “ | 0
2014-10-27 | “ | “ | 0
2014-11-03 | “ | “ | 0
2014-11-10 | “ | “ | 0