## AGENDA
Brisbane Hospital Project - Meeting Agenda
1st meeting
Next Meeting Date: | 11.02.2021
Time: | 10.00am
Location: | Boardroom
Attendees
Craig Camenzind | Project Manager
Rob Weidner | Logistic Manager
Tara Gilson | Estimator
Leanne Cameron | Work And Safety
Sara Vaninetti | Project Assistant
Topics
Allocate goals and responsibility of each team member
Estimator to run through the project
Documents required
n/a at this stage

## Estimators Meeting
Estimators Meeting
11.02.2021
Project/topic | Details | Action | Comments
Allocate goals and responsibility of each team member | Craig - PM Rob - Logistic Tara - Estimator Leanne - Work and Safety Sara - Project Assistant | Goal: * Respect the program provided at contract time * Follow cost and profit * Ensure Quality and Standards Responsibility: * Craig to manage the installer and be the main contact on site * Rob to place order, check lead time and call material forward as requested by PM and Programm * Tara to provide folder for Project Manager and advise the builder of each member reponsability * Leanne to provide all the documents necessary for this project to the builder such as SWMS... * Sara to assist with Variations, Claim, Drawings and Inductions for this project | To review next month after the job actually started
Estimator to run through the project | Tara ran through major information regarding the job | - Commence date on site 15.02.2021 - Project to finish end Nov 2021 - Aconex program used by the builder to communicate - Claim date as per contract 25th each month - Builder CA: John Smith, johnsmith@gmail.com 0410123456 - Floor Preparation excluded by the contract to provide variation with day dockets | Everyone can access all the information on idrive under 'Brisbane Hospital' folder
***New topic that came out during the meeting: | Occurence of meeting | Decide to do monthly meeting - Sara to send invitation by email of the occurrence [every first Tuesday of the month at 10.00am] | Ensure daily communication as well between team members