## Schedule of Lump Sum
Item No. | Description | Qty | Total (excl. GST)
1 | Site Establishment & fencing / preliminaries/ Dial Before You Dig | 1 | 32365.9528
2 | Demolish and remove the existing 2 discus + 2 shot put stations, cages and footings as per the RFQ | 1 | 4352.472
3 | Demolish and remove the long jump pit walls and pit sand as per the RFQ | 1 | 7990.8197
4 | Excavate and remove the soil between the existing long jump run ups and install the additional concrete as per the RFQ. | 1 | 17257.8485
5 | Construct the 2 new discus stations as per the RFQ | 1 | 14039.2215
6 | Construct the 3 new shot put stations as per the RFQ |  | 14437.5186
7 | Construct the new long jump pit walls as per the RFQ |  | 34072.2489
8 | Supply and install new pit sand as per the RFQ |  | 3262.8566
9 | Supply, prep and install the new rubber sporting surface on the discus, shot put stations and long jump run ups as per the RFQ |  | 67484.7392
10 | Install the required drainage as per the RFQ |  | 4031.3464
11 | Site restorations and clean-up |  | 3455.4398
12 | All other works and obligations under the Contract NOT INCLUDED ELSEWHERE in this Schedule |  | 0
| TOTAL (excl. GST) |  | 202750.464 | 0 | Check

## Rate Spread Lump Sum
Item No. | Description | In-direct | Direct |  | % | Calculated | Offer
1 | Management and Staff | 0 | 18000 |  | 10.23% | 2732.6388 | 20732.6388
2 | Preliminaries | 0 | 4600 |  | 2.613% | 698.341 | 5298.341
3 | Site Establishment | 0 | 5500 |  | 3.125% | 834.973 | 6334.973
4 | Demolish and remove the existing 2 discus + 2 shot put stations, cages and footings | 0 | 3778.8 |  | 2.147% | 573.672 | 4352.472
5 | Demolish and remove the long jump pit walls and pit sand | 0 | 6937.6 |  | 3.941% | 1053.2197 | 7990.8197
6 | Excavate and remove the soil between the existing long jump run ups and install the additional concrete | 0 | 14983.2 |  | 8.512% | 2274.6485 | 17257.8485
7 | Construct the 2 new discus stations | 0 | 12188.8 |  | 6.924% | 1850.4215 | 14039.2215
8 | Construct the 3 new shot put stations | 0 | 12534.6 |  | 7.121% | 1902.9186 | 14437.5186
9 | Construct the new long jump pit walls | 0 | 29581.4 |  | 16.81% | 4490.8489 | 34072.2489
10 | Supply and install new pit sand | 0 | 2832.8 |  | 1.609% | 430.0566 | 3262.8566
11 | Supply, prep and install the new rubber sporting surface on the discus, shot put stations and long jump run ups | 0 | 58590 |  | 33.28% | 8894.7392 | 67484.7392
12 | Install the required drainage | 0 | 3500 |  | 1.988% | 531.3464 | 4031.3464
13 | Site restorations and clean-up | 0 | 3000 |  | 1.704% | 455.4398 | 3455.4398
14 | All other works and obligations under the Contract NOT INCLUDED ELSEWHERE in this Schedule | 0 | 0 |  | 0% | 0 | 0
15 | Contingency | 5000 | 0 |  | 0% | 0 | 0
16 | Head Office Overheads | 12671.904 | 0 |  | 0% | 0 | 0
17 | Risk and Profit | 9051.36 | 0 |  | 0% | 0 | 0
| TOTALS | 26723.264 | 176027.2 |  | 100% | 26723.264 | 202750.464
| GRAND TOTAL |  |  | 202750.464
202750.464
|  |  |  | 0 |  | 0 | 0
|  |  |  | Check |  | Check | Check

## Summary Lump Sum
Item No. | Description | Total
1 | Management and Staff | 18000
2 | Preliminaries | 4600
3 | Site Establishment | 5500
4 | Demolish and remove the existing 2 discus + 2 shot put stations, cages and footings | 3778.8
5 | Demolish and remove the long jump pit walls and pit sand | 6937.6
6 | Excavate and remove the soil between the existing long jump run ups and install the additional concrete | 14983.2
7 | Construct the 2 new discus stations | 12188.8
8 | Construct the 3 new shot put stations | 12534.6
9 | Construct the new long jump pit walls | 29581.4
10 | Supply and install new pit sand | 2832.8
11 | Supply, prep and install the new rubber sporting surface on the discus, shot put stations and long jump run ups | 58590
12 | Install the required drainage | 3500
13 | Site restorations and clean-up | 3000
14 | All other works and obligations under the Contract NOT INCLUDED ELSEWHERE in this Schedule | 0
15 | Contingency | 5000
16 | Head Office Overheads | 12671.904
17 | Risk and Profit | 9051.36
| TOTAL | 202750.464
|  | 202750.464 | 0 | Check

## Estimate Lump Sum
Item No. | Description |  | Quantity |  |  | Unit | Unit Rate | Cost | Allocation | Total | Check
1 | Management and Staff
1.1 | Management |  |  |  | 0 | wks
a | Project Manager | Anthony Hrdalo | 1 | Staff | 0 | wks | 0 | 0 | 100% | 0
[6 empty] | wks | #DIV/0! | 0 |  | 0 | 0 | 0
1.2 | Engineering |  |  |  | 0 | wks
a | Project Engineer |  | 1 | Staff | 0 | wks | 0 | 0 | 100% | 0
b | Site Engineer |  | 0 | Staff | 0 | mths | 0 | 0 | 100% | 0
[6 empty] | wks | #DIV/0! | 0 |  | 0 | 0 | 0
1.3 | Site Supervision |  |  |  | 6 | wks
a | Supervisor |  | 1 | Staff | 6 | wks | 3000 | 18000 | 100% | 18000
[6 empty] | wks | 3000 | 18000 |  | 18000 | 18000 | 0
1.4 | Consultants |  |  |  | 1 | item
a | Consultant |  | 1 | Item | 1 | Item | 0 | 0 | 100% | 0
[6 empty] | item | 0 | 0 |  | 0 | 0 | 0
1 | TOTAL COST FOR: | Management and Staff |  |  | 6 | wks | 3000 | 18000 |  | 18000 | 0 | 18000
Item No. | Description |  | Quantity |  |  | Unit | Unit Rate | Cost | Allocation | Total | Check
2 | Preliminaries
2.1 | Contract Costs |  |  |  | 1 | item
a | Liquidated Damages |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | Inclement Weather |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | Retention |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
d | Security |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | Additional Security |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | item | 0 | 0 |  | 0 | 0 | 0
2.2 | Insurances |  |  |  | 1 | item
a | Workers Compensation |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | Superannuation |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | Public and Product Liability |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
d | Contract Works |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
e | Professional Indemnity |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
f | Vehicle and Plant Insurance |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | item | 0 | 0 |  | 0 | 0 | 0
2.3 | Office Costs |  |  |  | 6 | wks
a | Computers |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | Photocopier |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | Printers |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
d | Phone/Mobiles/Internet/Rentals |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
e | Stationary/Office Supplies |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
f | Other/Misc. |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
[6 empty] | wks | 0 | 0 |  | 0 | 0 | 0
2.4 | Crib/Ablution Costs |  |  |  | 6 | wks
a | Crib/Toilet/Cleaning Supplies |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
b | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | wks | 0 | 0 |  | 0 | 0 | 0
2.5 | Site Labour - Cleaning |  |  |  | 6 | wks
a | Cleaner |  | 1 | cleaner | 6 | wks | 0 | 0 | 100% | 0
b | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | wks | 0 | 0 |  | 0 | 0 | 0
2.6 | Site Security |  |  |  | 6 | wks
a | Security Guards |  | 1 | guards | 6 | wks | 0 | 0 | 100% | 0
b | Other/Misc. |  | 1 | item | 0 | item | 0 | 0 | 100% | 0
[6 empty] | wks | 0 | 0 |  | 0 | 0 | 0
2.7 | Survey | 3 days |  |  | 1 | item
a | Surveyor |  | 1 | surveyor | 1 | item | 500 | 500 | 100% | 500
b | Works as Ex. Drawings |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
c | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | item | 1000 | 1000 |  | 1000 | 1000 | 0
2.8 | Site Rubbish |  |  |  | 6 | wks
a | General Rubbish |  | 1 | item | 6 | wks | 100 | 600 | 100% | 600
b | Builders Waste |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
c | Steel Recycling |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
d | Paper/Cardboard Recycling |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
e | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | wks | 100 | 600 |  | 600 | 600 | 0
2.9 | Utilities (Temporary Services) |  |  |  | 6 | wks
a | Diesel |  | 1 | item | 6 | wks | 300 | 1800 | 100% | 1800
b | Water |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
c | Sewer |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
d | Electricity |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
e | Petrol - Unleaded |  | 1 | item | 6 | wks | 100 | 600 | 100% | 600
f | Other/Misc. |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
[6 empty] | wks | 416.6667 | 2500 |  | 2500 | 2500 | 0
2.1 | Other Costs |  |  |  | 6 | wks
a | Training |  | 1 | item | 1 | Item | 0 | 0 | 100% | 0
b | Audits |  | 1 | item | 1 | Item | 0 | 0 | 100% | 0
c | Accommodation |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
d | Entertainment - Internal |  | 1 | item | 1 | Item | 0 | 0 | 100% | 0
e | Entertainment - Client |  | 1 | item | 1 | Item | 0 | 0 | 100% | 0
f | Petty Cash |  | 1 | item | 1 | Item | 500 | 500 | 100% | 500
g | Other/Misc. |  | 1 | item | 1 | Item | 0 | 0 | 100% | 0
[6 empty] | wks | 83.3333 | 500 |  | 500 | 500 | 0
2 | TOTAL COST FOR: | Preliminaries |  |  | 6 | wks | 766.6667 | 4600 |  | 4600 | 0 | 4600
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
3 | Site Establishment
3.1 | Establish Project Plans/Documentation |  |  |  | 1 | item
a | CMC |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | Quality |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | OHS |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
d | Environmental |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
e | Traffic/Pedestrian |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
f | Construction Programme |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
g | Dilapidation Report |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
h | Other |  | 1 | item | 1 | item | 1000 | 1000 | 100% | 1000
[6 empty] | item | 1000 | 1000 |  | 1000 | 1000 | 0
3.2 | OHS&E |  |  |  | 1 | item
a | PPE |  | 1 | item | 1 | item | 200 | 200 | 100% | 200
b | Signs |  | 1 | item | 1 | item | 200 | 200 | 100% | 200
c | Environmental Protection |  | 1 | item | 1 | item | 300 | 300 | 100% | 300
d | First Aid Kits |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
e | Electrical Inspections |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
f | Lifting Gear Inspections |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
g | Medicals |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
h | First Aid Consultations |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
J | Other/Misc. |  | 1 | item | 1 | item | 200 | 200 | 100% | 200
[6 empty] | item | 1000 | 1000 |  | 1000 | 1000 | 0
3.3 | Site Facilities |  |  |  | 6 | wks
a | Site Office |  | 1 | no | 6 | wks | 0 | 0 | 100% | 0
b | Lunch Room |  | 1 | no | 6 | wks | 0 | 0 | 100% | 0
c | Port-a-Loo | includes clean-out | 1 | no | 6 | wks | 0 | 0 | 100% | 0
d | Container |  | 1 | no | 6 | wks | 0 | 0 | 100% | 0
e | ATF Fencing |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
f | Electrical Connection/Dis-connection |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
g | Water/Sewer Connection/Dis-Connection |  | 1 | item | 6 | wks | 0 | 0 | 100% | 0
h | Establish/Disestablish Facilities |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
j | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | wks | 0 | 0 |  | 0 | 0 | 0
3.4 | Environmental Controls |  |  |  | 1 | item
a | Silt Fence |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | Pit Traps |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
c | Filters (Sock) |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
d | Entry/Exit Gate |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
e | Wash-out Area |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
f | Stockpile and Storage Area |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
g | Watercart |  | 1 | item | 2 | wks | 0 | 0 | 100% | 0
h | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | item | 1000 | 1000 |  | 1000 | 1000 | 0
3.5 | Traffic Controls |  |  |  | 6 | wks
a | Traffic Control Plan | Plug | 1 | item | 0 | item | 0 | 0 | 100% | 0
b | Road Occupancy Licence | Plug | 1 | item | 0 | item | 0 | 0 | 100% | 0
c | Water Filled Barriers | Plug | 21 | days | 0 | units | 0 | 0 | 100% | 0
d | Signage |  | 1 | item | 0 | item | 0 | 0 | 100% | 0
e | 2 x Traffic Controller - Night Shift | Fusion | 2 | traffic control | 0 | hrs | 0 | 0 | 100% | 0
f | 2 x Skilled Labour - Night Shift | Fusion | 2 | labour | 0 | hrs | 0 | 0 | 50% | 0
g | Other/Misc. |  | 1 | item | 0 | item | 0 | 0 | 100% | 0
[6 empty] | wks | 0 | 0 |  | 0 | 0 | 0
3.6 | Services Search |  |  |  | 1 | item
a | DBYD |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | Services Search/Identification | Plug | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | item | 0 | 0 |  | 0 | 0 | 0
3.7 | General Consumables and Small Tools |  |  |  | 6 | wks
a | Genral Consumables |  | 1 | item | 6 | wks | 250 | 1500 | 50% | 750
b | Small Tools |  | 1 | item | 6 | wks | 250 | 1500 | 50% | 750
c | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | wks | 250 | 3000 |  | 1500 | 1500 | 0
3.8 | Floatage |  |  |  | 1 | item
a | 5Ton Excavator | Internal | 1 | item | 2 | no | 250 | 500 | 100% | 500
b | Posi Track | Internal | 1 | item | 2 | no | 250 | 500 | 100% | 500
c | Other/Misc. |  | 1 | item | 1 | no | 0 | 0 | 100% | 0
[6 empty] | item | 1000 | 1000 |  | 1000 | 1000 | 0
3 | TOTAL COST FOR: | Site Establishment |  |  | 4 | wks | 1375 | 7000 |  | 5500 | 0 | 5500
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
4 | Demolish and remove the existing 2 discus + 2 shot put stations, cages and footings
4.1 | Demolish and remove the existing 2 discus + 2 shot put stations, cages and footings | 1 day |  |  | 1 | item
a | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 90 | 810 | 100% | 810
b | E/O Hammer |  | 1 | item | 9 | hrs | 40 | 360 | 100% | 360
c | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
d | Remove Concrete Waste | Tip Fees | 1 | item | 12 | ton | 30 | 360 | 100% | 360
e | Remove Other Waste | Tip Fees | 1 | item | 1 | item | 500 | 500 | 100% | 500
f | 12Ton Boggie Tipper | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
g | Other/Misc. |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
[6 empty] | item | 3778.8 | 3778.8 |  | 3778.8 | 3778.8 | 0
4 | TOTAL COST FOR: | Demolish and remove the existing 2 discus + 2 shot put stations, cages and footings |  |  | 1 | item | 3778.8 | 3778.8 |  | 3778.8 | 0 | 3778.8
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
5 | Demolish and remove the long jump pit walls and pit sand
5.1 | Demolish and remove (2 off) the long jump pit walls and pit sand | 2 days |  |  | 1 | item
a | 5Ton Excavator | includes operator | 1 | item | 18 | hrs | 90 | 1620 | 100% | 1620
b | E/O Hammer |  | 1 | item | 18 | hrs | 40 | 720 | 100% | 720
c | 2 x Skilled Labour | Fusion | 2 | labour | 18 | hrs | 41.6 | 1497.6 | 100% | 1497.6
d | Remove Concrete Waste | Tip Fees | 1 | item | 40 | ton | 30 | 1200 | 100% | 1200
e | Remove Other Waste | Tip Fees | 1 | item | 1 | item | 0 | 0 | 100% | 0
f | 12Ton Boggie Tipper | includes operator | 2 | item | 9 | hrs | 100 | 1800 | 100% | 1800
g | Other/Misc. |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
[6 empty] | item | 6937.6 | 6937.6 |  | 6937.6 | 6937.6 | 0
5 | TOTAL COST FOR: | Demolish and remove the long jump pit walls and pit sand |  |  |  | 1 | item | 6937.6 |  | 6937.6 | 0 | 6937.6
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
6 | Excavate and remove the soil between the existing long jump run ups and install the additional concrete | 45m and 30m in length
6.1 | Excavate (300thk) and remove the soil between the existing long jump run ups |  | 1 day |  | 25 | m3
a | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 90 | 810 | 100% | 810
b | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
c | Remove Excavated Spoil | Loose on Site | 1 | item | 50 | ton | 0 | 0 | 100% | 0
d | 12Ton Boggie Tipper | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
e | Other/Misc. |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
[6 empty] | m3 | 102.352 | 2558.8 |  | 2558.8 | 2558.8 | 0
6.2 | Install the additional concrete between the excavated existing long jump run ups |  |  |  | 1 | item
6.1.1 | Subgrade Preparation | included at 6.1 |  |  | 75 | m2
a | Plate Compactor | Dry Hire | 1 | item | 1 | day | 120 | 120 | 100% | 120
b | 2 x Skilled Labour | Fusion | 2 | labour | 0 | hrs | 41.6 | 0 | 100% | 0
c | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 4.9333 | 370 |  | 370 | 370 | 0
6.1.2 | Subbase - assume 150thk | 1 day |  |  | 75 | m2
a | Supply DGB20 - Recycled |  | 1 | item | 25 | ton | 30 | 750 | 100% | 750
b | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 90 | 810 | 100% | 810
c | Plate Compactor | Dry Hire | 1 | item | 1 | day | 120 | 120 | 100% | 120
d | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
e | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
f | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 35.7173 | 2678.8 |  | 2678.8 | 2678.8 | 0
6.1.3 | Edgeboards | 2 days |  |  | 1 | item
a | Edgeboards | 150thk | 1 | item | 1 | item | 100 | 100 | 100% | 100
b | Accessories |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
c | 2 x Formworkers | Plug | 2 | formworkers | 4 | hrs | 70 | 560 | 100% | 560
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 810 | 810 |  | 810 | 810 | 0
6.1.4 | Reinforcing Mesh | 1/2 day |  |  | 75 | m2
a | Supply Reinforcing Mesh | SL81 | 1 | item | 75 | m2 | 20 | 1500 | 100% | 1500
b | Accessories |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
c | 2 x Skilled Labour | Fusion | 2 | labour | 4 | hrs | 41.6 | 332.8 | 100% | 332.8
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 26.4373 | 1982.8 |  | 1982.8 | 1982.8 | 0
6.1.5 | Concrete | 1/2 day |  |  | 12 | m3
a | Concrete Supply | 25MPa | 1 | item | 12 | m3 | 235 | 2820 | 100% | 2820
b | Concrete Pump |  | 1 | item | 1 | item | 1600 | 1600 | 100% | 1600
c | 3 x Concretors | Plug | 3 | concretors | 2 | hrs | 70 | 420 | 100% | 420
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m3 | 407.5 | 4890 |  | 4890 | 4890 | 0
6.1.6 | Concrete Finishing | 1/2 day each |  |  | 75 | m2
a | 3 x Concretors | Plug | 3 | concretors | 6 | hrs | 70 | 1260 | 100% | 1260
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 17.4667 | 1310 |  | 1310 | 1310 | 0
6.1.7 | Strip/Clean Up and Repair/Patching | 1 day |  |  | 1 | item
a | 2 x Skilled Labour | Fusion | 2 | labour | 4 | hrs | 41.6 | 332.8 | 100% | 332.8
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 382.8 | 382.8 |  | 382.8 | 382.8 | 0
6 | TOTAL COST FOR: | Excavate and remove the soil between the existing long jump run ups and install the additional concrete |  |  | 1 | item | 14983.2 | 14983.2 |  | 14983.2 | 0 | 14983.2
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
7 | Construct the 2 new discus stations | 3.1 x 3.1 with 2.5 diameter circle
7.1 | Construct the 2 new discus stations |  |  |  | 1 | item
7.1.1 | Earthworks - Cut to Subgrade - 600thk | 1 day |  |  | 12 | m3
a | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
b | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
c | Remove Excavated Spoil | Loose on Site | 1 | item | 25 | ton | 0 | 0 | 100% | 0
d | 12Ton Boggie Tipper | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
e | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m3 | 216.5667 | 2598.8 |  | 2598.8 | 2598.8 | 0
7.1.2 | Subgrade Preparation | included at 7.1.1 |  |  | 20 | m2
a | Plate Compactor | Dry Hire | 1 | item | 0.5 | day | 120 | 60 | 100% | 60
b | 2 x Skilled Labour | Fusion | 2 | labour | 0 | hrs | 41.6 | 0 | 100% | 0
c | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 15.5 | 310 |  | 310 | 310 | 0
7.1.3 | Subbase - assume 450thk | 1/2 day |  |  | 20 | m2
a | Supply DGB20 - Recycled |  | 1 | item | 20 | ton | 30 | 600 | 100% | 600
b | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
c | Plate Compactor | Dry Hire | 1 | item | 1 | day | 120 | 120 | 100% | 120
d | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
e | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
f | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 130.94 | 2618.8 |  | 2618.8 | 2618.8 | 0
7.1.4 | Edgeboards | 1 day |  |  | 25 | m
a | Edgeboards | 150thk | 1 | item | 25 | m | 10 | 250 | 100% | 250
b | Accessories |  | 1 | item | 1 | item | 200 | 200 | 100% | 200
c | 2 x Formworkers | Plug | 2 | formworkers | 9 | hrs | 70 | 1260 | 100% | 1260
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m | 70.4 | 1760 |  | 1760 | 1760 | 0
7.1.5 | Fixtures | 2 days |  |  | 1 | item
a | Centre Point - 4mm inside Diameter Brass Tube | Plug | 1 | item | 1 | item | 200 | 200 | 100% | 200
b | Stainless Steel Discuss Circle 2.5m Diameter | Supplied | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | Draianage - 20mm Brass Pipe | Plug | 4 | item | 1 | item | 200 | 800 | 100% | 800
d | Accessories |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
e | 2 x Formworkers | Plug | 2 | formworkers | 4 | hrs | 70 | 560 | 100% | 560
f | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 2110 | 2110 |  | 2110 | 2110 | 0
7.1.6 | Reinforcing Mesh | 1/2 day |  |  | 20 | m2
a | Supply Reinforcing Mesh | SL81 | 1 | item | 20 | m2 | 20 | 400 | 100% | 400
b | Accessories |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
c | 2 x Skilled Labour | Fusion | 2 | labour | 2 | hrs | 41.6 | 166.4 | 100% | 166.4
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 35.82 | 716.4 |  | 716.4 | 716.4 | 0
7.1.7 | Concrete | 2 x 1/2 day each |  |  | 3.2 | m3
a | Concrete Supply | 25MPa | 1 | item | 3.2 | m3 | 235 | 752 | 100% | 752
b | 2 x Concretors | Plug | 2 | concretors | 2 | hrs | 70 | 280 | 100% | 280
c | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m3 | 338.125 | 1082 |  | 1082 | 1082 | 0
7.1.8 | Concrete Finishing | 2 x 1/2 day each |  |  | 20 | m2
a | 2 x Concretors | Plug | 2 | concretors | 4 | hrs | 70 | 560 | 100% | 560
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 30.5 | 610 |  | 610 | 610 | 0
7.1.9 | Strip/Clean Up and Repair/Patching | 1 day |  |  | 1 | item
a | 2 x Skilled Labour | Fusion | 2 | labour | 4 | hrs | 41.6 | 332.8 | 100% | 332.8
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 382.8 | 382.8 |  | 382.8 | 382.8 | 0
7 | TOTAL COST FOR: | Construct the 2 new discus stations |  |  | 1 | item | 12188.8 | 12188.8 |  | 12188.8 | 0 | 12188.8
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
8 | Construct the 3 new shot put stations | 2.44 x 2.44 with 2.135 diameter circle
8.1 | Construct the 3 new shot put stations |  |  |  | 1 | item
8.1.1 | Earthworks - Cut to Subgrade - 600thk | 1 day |  |  | 12 | m3
a | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
b | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
c | Remove Excavated Spoil | Loose on Site | 1 | item | 25 | ton | 0 | 0 | 100% | 0
d | 12Ton Boggie Tipper | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
e | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m3 | 216.5667 | 2598.8 |  | 2598.8 | 2598.8 | 0
8.1.2 | Subgrade Preparation | included at 7.1.1 |  |  | 18 | m2
a | Plate Compactor | Dry Hire | 1 | item | 1 | day | 120 | 120 | 100% | 120
b | 2 x Skilled Labour | Fusion | 2 | labour | 0 | hrs | 41.6 | 0 | 100% | 0
c | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 20.5556 | 370 |  | 370 | 370 | 0
8.1.3 | Subbase - assume 450thk | 1 day |  |  | 18 | m2
a | Supply DGB20 - Recycled |  | 1 | item | 18 | ton | 30 | 540 | 100% | 540
b | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
c | Plate Compactor | Dry Hire | 1 | item | 1 | day | 120 | 120 | 100% | 120
d | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
e | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
f | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 142.1556 | 2558.8 |  | 2558.8 | 2558.8 | 0
8.1.4 | Edgeboards | 2 days |  |  | 30 | m
a | Edgeboards | 150thk | 1 | item | 30 | m | 10 | 300 | 100% | 300
b | Accessories |  | 1 | item | 1 | item | 200 | 200 | 100% | 200
c | 2 x Formworkers | Plug | 2 | formworkers | 9 | hrs | 70 | 1260 | 100% | 1260
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m | 60.3333 | 1810 |  | 1810 | 1810 | 0
8.1.5 | Fixtures | 2 days |  |  | 1 | item
a | Centre Point - 4mm inside Diameter Brass Tube | Plug | 1 | item | 1 | item | 200 | 200 | 100% | 200
b | Stainless Steel Discuss Circle 2.135m Diameter | Supplied | 1 | item | 1 | item | 0 | 0 | 100% | 0
c | Draianage - 20mm Brass Pipe | Plug | 4 | item | 1 | item | 200 | 800 | 100% | 800
d | Accessories |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
e | 2 x Formworkers | Plug | 2 | formworkers | 4 | hrs | 70 | 560 | 100% | 560
f | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 2110 | 2110 |  | 2110 | 2110 | 0
8.1.6 | Reinforcing Mesh | 1/2 day |  |  | 18 | m2
a | Supply Reinforcing Mesh | SL81 | 1 | item | 18 | m2 | 20 | 360 | 100% | 360
b | Accessories |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
c | 2 x Skilled Labour | Fusion | 2 | labour | 4 | hrs | 41.6 | 332.8 | 100% | 332.8
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 46.8222 | 842.8 |  | 842.8 | 842.8 | 0
8.1.7 | Concrete | 1/2 day each |  |  | 3 | m3
a | Concrete Supply | 25MPa | 1 | item | 3 | m3 | 235 | 705 | 100% | 705
b | 2 x Concretors | Plug | 2 | concretors | 2 | hrs | 70 | 280 | 100% | 280
c | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m3 | 345 | 1035 |  | 1035 | 1035 | 0
8.1.8 | Concrete Finishing | 2 x 1/2 day each |  |  | 18 | m2
a | 2 x Concretors | Plug | 2 | concretors | 4 | hrs | 70 | 560 | 100% | 560
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 33.8889 | 610 |  | 610 | 610 | 0
8.1.9 | Strip/Clean Up and Repair/Patching | 1 day |  |  | 1 | item
a | 2 x Skilled Labour | Fusion | 2 | labour | 4 | hrs | 41.6 | 332.8 | 100% | 332.8
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 382.8 | 382.8 |  | 382.8 | 382.8 | 0
8.1.10 | Stop Board | 1 day |  |  | 1 | item
a | Stop Board | Supplied | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | 2 x Skilled Labour | Fusion | 2 | labour | 2 | hrs | 41.6 | 166.4 | 100% | 166.4
c | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 216.4 | 216.4 |  | 216.4 | 216.4 | 0
8 | TOTAL COST FOR: | Construct the 3 new shot put stations |  |  | 1 | item | 12534.6 | 12534.6 |  | 12534.6 | 0 | 12534.6
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
9 | Construct the new long jump pit walls | 5.2 x 7.0 and 5.2 x 8.0
9.1 | Construct the new long jump pit walls (2 off) |  |  |  | 1 | item
9.1.1 | Earthworks - Cut to Subgrade - 450thk | 1 day |  |  | 35 | m3
a | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 90 | 810 | 100% | 810
b | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
c | Remove Excavated Spoil | Loose on Site | 1 | item | 70 | ton | 0 | 0 | 100% | 0
d | 12Ton Boggie Tipper | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
e | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m3 | 71.68 | 2508.8 |  | 2508.8 | 2508.8 | 0
9.1.2 | Subgrade Preparation | included at 7.1.1 |  |  | 78 | m2
a | Plate Compactor | Dry Hire | 1 | item | 1 | day | 120 | 120 | 100% | 120
b | 2 x Skilled Labour | Fusion | 2 | labour | 0 | hrs | 41.6 | 0 | 100% | 0
c | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
d | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 4.7436 | 370 |  | 370 | 370 | 0
9.1.3 | Subbase - assume 300thk | 1 day |  |  | 78 | m2
a | Supply DGB20 - Recycled |  | 1 | item | 50 | ton | 30 | 1500 | 100% | 1500
b | 5Ton Excavator | includes operator | 1 | item | 9 | hrs | 100 | 900 | 100% | 900
c | Plate Compactor | Dry Hire | 1 | item | 1 | day | 120 | 120 | 100% | 120
d | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
e | Compaction Testing |  | 1 | item | 2 | no | 100 | 200 | 100% | 200
f | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 45.1128 | 3518.8 |  | 3518.8 | 3518.8 | 0
9.1.4 | Edgeboards | 2 days |  |  | 105 | m
a | Edgeboards - base 450thk | 150thk | 1 | item | 52 | m | 20 | 1040 | 100% | 1040
b | Edgeboards - walls 300thk | 300thk | 1 | item | 52 | m | 20 | 1040 | 100% | 1040
c | Accessories |  | 1 | item | 1 | item | 200 | 200 | 100% | 200
d | 2 x Formworkers | Plug | 2 | formworkers | 18 | hrs | 70 | 2520 | 100% | 2520
e | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m | 46.1905 | 4850 |  | 4850 | 4850 | 0
9.1.5 | Fixtures |  |  |  | 1 | item
a | Draianage Well - 20mm Brass Pipe | Plug | 4 | item | 1 | item | 200 | 800 | 100% | 800
b | Pit cover flush mount anchors | Plug | 1 | item | 52 | no | 40 | 2080 | 100% | 2080
c | Accessories |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
d | 2 x Skilled Labour | Fusion | 2 | labour | 9 | hrs | 41.6 | 748.8 | 100% | 748.8
e | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 4178.8 | 4178.8 |  | 4178.8 | 4178.8 | 0
9.1.6 | Reinforcing Mesh | 1 day |  |  | 78 | m2
a | Supply Reinforcing Mesh | SL81 | 1 | item | 78 | m2 | 20 | 1560 | 100% | 1560
b | Supply Reinforcing Bar for Wall | Plug | 1 | item | 1 | item | 500 | 500 | 100% | 500
c | Accessories |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
d | 2 x Steel Fixers | Fusion | 2 | steel fixers | 9 | hrs | 70 | 1260 | 100% | 1260
e | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 44.4872 | 3470 |  | 3470 | 3470 | 0
9.1.7 | Concrete | 1 day |  |  | 17 | m3
a | Concrete Supply - Base | 25MPa | 1 | item | 12 | m3 | 235 | 2820 | 100% | 2820
b | Concrete Supply - Wall | 25MPa | 1 | item | 5 | m3 | 235 | 1175 | 100% | 1175
c | Concrete Pump |  | 1 | item | 1 | item | 2000 | 2000 | 100% | 2000
d | 3 x Concretors | Plug | 3 | concretors | 9 | hrs | 70 | 1890 | 100% | 1890
e | Small Tools |  | 1 | item | 1 | item | 200 | 200 | 100% | 200
f | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m3 | 478.5294 | 8135 |  | 8135 | 8135 | 0
9.1.8 | Concrete Finishing | 1 day |  |  | 78 | m2
a | 3 x Concretors | Plug | 3 | concretors | 9 | hrs | 70 | 1890 | 100% | 1890
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | m2 | 24.8718 | 1940 |  | 1940 | 1940 | 0
9.1.9 | Strip/Clean Up and Repair/Patching | 1 day |  |  | 1 | item
a | 2 x Concretors | Plug | 2 | labour | 4 | hrs | 70 | 560 | 100% | 560
b | Other/Misc. |  | 1 | item | 1 | item | 50 | 50 | 100% | 50
[6 empty] | item | 610 | 610 |  | 610 | 610 | 0
9 | TOTAL COST FOR: | Construct the new long jump pit walls |  |  | 1 | item | 29581.4 | 29581.4 |  | 29581.4 | 0 | 29581.4
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
10 | Supply and install new pit sand
10.1 | Supply and install new pit sand |  |  |  | 1 | item
a | Supply and install new pit sand | Plug | 1 | item | 40 | ton | 60 | 2400 | 100% | 2400
b | 2 x Skilled Labour | Fusion | 2 | labour | 4 | hrs | 41.6 | 332.8 | 100% | 332.8
c | Other/Misc. |  | 1 | item | 1 | item | 100 | 100 | 100% | 100
[6 empty] | item | 2832.8 | 2832.8 |  | 2832.8 | 2832.8
10 | TOTAL COST FOR: | Supply and install new pit sand |  |  | 1 | item | 2832.8 | 2832.8 |  | 2832.8 | 0 | 2832.8
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
11 | Supply, prep and install the new rubber sporting surface on the discus, shot put stations and long jump run ups
11.1 | Removal of existing synthetic turf on the existing long jump/triple jump run ups |  |  |  | 1 | item
a | Removal of existing synthetic turf | Plug | 1 | item | 180 | m2 | 20 | 3600 | 100% | 3600
b | Other/Misc. |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
[6 empty] | item | 4100 | 4100 |  | 4100 | 4100
11.2 | Supply, prep and install the new synthetic turf on the existing long jump/triple jump run ups |  |  |  | 1 | item
a | Supply, prep and install the new synthetic turf | Plug | 1 | item | 180 | m2 | 200 | 36000 | 100% | 36000
b | Other/Misc. |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
[6 empty] | item | 36500 | 36500 |  | 36500 | 36500
11.3 | Supply, prep and install the new rubber sporting surface on the discus, shot put stations and long jump run ups |  |  |  | 1 | item
a | 2 new discus stations | Plug | 1 | item | 9.5 | m2 | 150 | 1425 | 100% | 1425
b | 3 new shot put stations | Plug | 1 | item | 7.1 | m2 | 150 | 1065 | 100% | 1065
c | Long jump run ups | Plug | 1 | item | 75 | m2 | 200 | 15000 | 100% | 15000
d | Other/Misc. |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
[6 empty] | item | 17990 | 17990 |  | 17990 | 17990
11 | TOTAL COST FOR: | Supply, prep and install the new rubber sporting surface on the discus, shot put stations and long jump run ups |  |  | 1 | item | 58590 | 58590 |  | 58590 | 0 | 58590
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
12 | Install the required drainage
12.1 | Install the required drainage |  |  |  | 1 | item
a | 2 new discus stations | Plug | 1 | item | 1 | item | 500 | 500 | 100% | 500
b | 3 new shot put stations | Plug | 1 | item | 1 | item | 500 | 500 | 100% | 500
c | Long jump pit walls (2 off) | Plug | 1 | item | 1 | item | 2000 | 2000 | 100% | 2000
d | Other/Misc. |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
[6 empty] | item | 3500 | 3500 |  | 3500 | 3500
12 | TOTAL COST FOR: | Install the required drainage |  |  | 1 | item | 3500 | 3500 |  | 3500 | 0 | 3500
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
13 | Site restorations and clean-up
13.1 | Site restorations and clean-up |  |  |  | 1 | item
a | Lose all Excavated Spoil on Site | Plug | 1 | item | 1 | item | 1000 | 1000 | 100% | 1000
b | Site restorations (includes new turf) | Plug | 1 | item | 1 | item | 1000 | 1000 | 100% | 1000
c | Clean-up | Plug | 1 | item | 1 | item | 500 | 500 | 100% | 500
d | Other/Misc. |  | 1 | item | 1 | item | 500 | 500 | 100% | 500
[6 empty] | item | 3000 | 3000 |  | 3000 | 3000
13 | TOTAL COST FOR: | Site restorations and clean-up |  |  | 1 | item | 3000 | 3000 |  | 3000 | 0 | 3000
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
14 | All other works and obligations under the Contract NOT INCLUDED ELSEWHERE in this Schedule
14.1 | Any other works and obligations |  |  |  | 1 | item
a | Item |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
b | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | item | 0 | 0 |  | 0 | 0
14 | TOTAL COST FOR: | All other works and obligations under the Contract NOT INCLUDED ELSEWHERE in this Schedule |  |  | 1 | item | 0 | 0 |  | 0 | 0 | 0
Item No. | Description |  | Quantity | Unit |  |  | Unit Rate | Cost | Allocation | Total
15 | Contingency
15.1 | Contingency |  |  |  | 1 | item
a | Item |  | 1 | item | 1 | item | 5000 | 5000 | 100% | 5000
b | Other/Misc. |  | 1 | item | 1 | item | 0 | 0 | 100% | 0
[6 empty] | item | 5000 | 5000 |  | 5000 | 5000
15 | TOTAL COST FOR: | Contingency |  |  | 1 | item | 5000 | 5000 |  | 5000 | 0 | 5000
[11 empty] | 181027.2 | 181027.2
|  |  | Total Cost |  |  |  |  | 182527.2 | AUD | 181027.2 | 0 | 0 | error
Surcharges
|  |  |  | Overheads |  | 7% |  | 12776.904 |  | 12671.904
|  |  |  | Risk and Profit |  | 5% |  | 9126.36 | AUD | 9051.36
|  |  |  | Subtotal |  |  |  | 204430.464 | AUD | 202750.464

## Programme
DRAFT - PLANNING OF WORKS
Weeks |  |  |  | 0 |  |  |  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6
Days |  |  |  | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Item | Description | Resource | Duration
1 | Tender
a | Submission |  | 0
2 | Contractual
a | Contract Award | Ironbuilt | 0
3 | Project Documentation/Design and Procurement
a | SWMS | Ironbuilt | 5 | bar: 0 1899-12-31 to 0 1900-01-04
b | QA | Ironbuilt | 5 | bar: 0 1899-12-31 to 0 1900-01-04
c | Procurement | Ironbuilt | 5 | bar: 0 1899-12-31 to 0 1900-01-04
4 | Site Access/Establishment
a | Establish Compound/Traffic Control/Sediment and Erosion Control/Fencing | Ironbuilt | 1 | bar: 1 1900-01-05 to 1 1900-01-07
b | Survey/Setout | TBA | 0 | bar: 1 1900-01-05; 2 1900-01-10; 3 16
5 | Demolish/Remove Existing 2 Discus, 2 Shot Put Stations, Cages and Footings
a | Demolish/Remove Existing 2 Discus, 2 Shot Put Stations, Cages and Footings | Ironbuilt | 2 | bar: 1 1900-01-06 to 1 1900-01-07
6 | Demolish/Remove Long Jump Pit Walls and Pit Sand
a | Demolish/Remove Long Jump Pit Walls and Pit Sand | Ironbuilt | 2 | bar: 1 1900-01-07 to 1 1900-01-08
7 | Excavate/Remove Spoil between Existing Long Jump Run Ups and Concrete
a | Excavation to Subgrade | Ironbuilt | 2 | bar: 1 1900-01-08 to 1 1900-01-09
b | Subgrade Preparation | Ironbuilt | 1 | bar: 1 1900-01-09
c | Subbase | Ironbuilt | 2 | bar: 1 1900-01-09 to 2 1900-01-10
d | Form/Reo/Pour Concrete | Ironbuilt | 4 | bar: 2 12 to 2 15
8 | Construct 2 new Discus Stations
a | Excavation to Subgrade | Ironbuilt | 1 | bar: 2 1900-01-10
b | Subgrade Preparation | Ironbuilt | 1 | bar: 2 1900-01-10
c | Subbase | Ironbuilt | 1 | bar: 2 1900-01-10
d | Drainage | Ironbuilt | 1 | bar: 2 12
e | Form/Reo/Pour Concrete | Ironbuilt | 4 | bar: 2 12 to 2 15
9 | Construct 3 new Shot Put Stations
a | Excavation to Subgrade | Ironbuilt | 1 | bar: 3 16
b | Subgrade Preparation | Ironbuilt | 1 | bar: 3 16
c | Subbase | Ironbuilt | 1 | bar: 3 16
d | Drainage | Ironbuilt | 1 | bar: 3 17
e | Form/Reo/Pour Concrete | Ironbuilt | 4 | bar: 3 17 to 3 20
10 | Construct new Long Jump Pit Walls
a | Excavation to Subgrade | Ironbuilt | 1 | bar: 3 16
b | Subgrade Preparation | Ironbuilt | 1 | bar: 3 16
c | Subbase | Ironbuilt | 1 | bar: 3 16
d | Drainage | Ironbuilt | 1 | bar: 3 17
e | Form/Reo/Pour Concrete | Ironbuilt | 6 | bar: 3 17 to 4 22
11 | Supply and Install new Pit Sand
a | Supply and Install new Pit Sand | Ironbuilt | 1 | bar: 6 31
12 | Supply, Prepare and Install new Rubber Sporting Surfaces
a | 2 new discus stations | TBC | 5 | bar: 5 26 to 5 30
b | 3 new shot put stations | TBC | 5 | bar: 5 26 to 5 30
c | Long jump run ups | TBC | 5 | bar: 5 26 to 5 30
13 | Install the required Drainage
a | 2 new discus stations | Ironbuilt | 5 | bar: 4 21 to 4 25
b | 3 new shot put stations | Ironbuilt | 5 | bar: 4 21 to 4 25
c | Long jump pit walls (2 off) | Ironbuilt | 5 | bar: 4 21 to 4 25
14 | Site Restorations and Clean-up
a | Site Restoration | Ironbuilt | 3 | bar: 6 31 to 6 33
b | Clean Up | Ironbuilt | 2 | bar: 6 33 to 6 34
a | Site Dis-establish + Clean Up | Ironbuilt | 1 | bar: 6 35