## Variations
Approved Variations |  |  |  | Pending Variations - Submitted
MH No | LC No |  |  |  | ev charging station and future provision
1 | 1 | Civil Latent Conditions | 65769 |  | TV Relocation
2 | 2 | PMT Easement Registration | 6600 |  | feature lighting to wall in front of lifts
3 | 3 | Interior Designer Screens Deletion | -50000 |  | Flagpole
4 | 4 | Queen Elizabeth Public Holiday | 7391.65
5 | 5 | Reinforcement PC Rate Difference | 180405.47
6 | 6 | Tea Making Station to Function Room | 13040
7 | 9 | OPW Landscape Changes | 1102.2
8 | 7 | Laundry Heat Pump | 5878
9 | 13 | Switchboard Upgrade | 8079.5
10 | 17 | Crimsafe Screens | 3861
11 | 12 | Western Façade Windows | 48950
12 | 20 | Corporate Signage Provisional Sum Difference | -7545
13 | 16 | PC Rate Vinyl, Carpet and Tiles | 46119.69
14 | 19 | Shelving Units to Corridor Tea Making Stations | 5170
15 | 21 | Wayfinding Signage Credit | -30000
16 | 22 | Café Terrace Changes | 3401.41 | Declined Variations
17 | 15 | Nurse Call Provisional Sums | 101962.55 | 8 | Wall Vinyl to Chute Room - $2,816 mcnab proceeding
18 | 23 | Stone benchtop prov sum adjustment | -6692.9 | 10 | Interconnecting Resident Doors - $17,550.28 mcnab proceeding
19 | 24 | Vinyl Supply | 46433.2 | 11 | E Water Sanitising Unit - $11,550 mcnab proceeding
20 | 26 | Structural Steel Provisional Sums | 19724.08 | 14 | Handwashing Joinery in Corridors - $13,750 not proceeding
21 | 27 | Traffic Island | 2244 | 18 | Solar Panel Increase - $94,281.22 not proceeding
22 | 25 | Added Rooms to Storage Area | 20881.61
|  | Total | 492775.46 |  | Total | 0
|  | Contract Value | 34267400
|  | Revised Contract Value | 34760175.46

## Sheet1
Approved Variations |  |  |  |  | Pending Variations - Submitted |  |  | Pending Variations - Not yet Submitted/not pursuing
MH No | LC No |  |  |  | 33 | New Fence Line | 3160.48
1 | 1 | Civil Latent Conditions | 65769 |  | 34 | Bio Macerator
2 | 2 | PMT Easement Registration | 6600
3 | 3 | Interior Designer Screens Deletion | -50000
4 | 4 | Queen Elizabeth Public Holiday | 7391.65
5 | 5 | Reinforcement PC Rate Difference | 180405.47
6 | 6 | Tea Making Station to Function Room | 13040
7 | 9 | OPW Landscape Changes | 1102.2
8 | 7 | Laundry Heat Pump | 5878
9 | 13 | Switchboard Upgrade | 8079.5
10 | 17 | Crimsafe Screens | 3861
11 | 12 | Western Façade Windows | 48950
12 | 20 | Corporate Signage Provisional Sum Difference | -7545
13 | 16 | PC Rate Vinyl, Carpet and Tiles | 46119.69 |  |  |  |  | not pursuing
14 | 19 | Shelving Units to Corridor Tea Making Stations | 5170 | [5 empty] | Absailing
15 | 21 | Wayfinding Signage Credit | -30000 | [5 empty] | Extra hanging rails
16 | 22 | Café Terrace Changes | 3401.41 | [5 empty] | Changes in Group Schedule - e water main one
17 | 15 | Nurse Call Provisional Sums | 101962.55 | [5 empty] | Internal Finishes changes - diff realised in pc rates and prov sums
18 | 23 | Stone benchtop prov sum adjustment | -6692.9 | [5 empty] | Soft Close Hinges - not going ahead
19 | 24 | Vinyl Supply | 46433.2 | [5 empty] | Suite changes to S1 and S2
20 | 26 | Structural Steel Provisional Sums | 19724.08 | [5 empty] | Credit Stone to Laminate Reception
21 | 27 | Traffic Island | 2244 | [5 empty] | Flagpole
22 | 25 | Added Rooms to Storage Area | 20881.61 | [5 empty] | Credit Roller Door Motor $500
23 | 29 | Corner and Door Protection | -10044.23 | [5 empty] | TV Relocation
24 | 30 | Additional Lighting to Lift Wall | 3064.88 |  | Declined Variations
25 | 31 | Lock to Joinery Nurse Station | 1798.5 |  | 8 | Wall Vinyl to Chute Room - $2,816 mcnab proceeding |  | client credits
26 | 32 | Carpet Supply | 22076.07 |  | 10 | Interconnecting Resident Doors - $17,550.28 mcnab proceeding |  |  | room deletions - doors and frames $10k
[5 empty] | 11 | E Water Sanitising Unit - $11,550 mcnab proceeding
[5 empty] | 14 | Handwashing Joinery in Corridors - $13,750 not proceeding |  |  | Bath to Quiet Room Changes potential credit $10k
[5 empty] | 18 | Solar Panel Increase - $94,281.22 not proceeding |  |  | Credits - Planter Box and Fountain Feature
[5 empty] | 28 | ev charging station and future provision |  |  | Credit Gutter Guard Deletion
|  | Total | 509670.68 |  |  | Total | 3160.48
|  | Contract Value | 34267400 | 0.065 | 222738.1
|  | Revised Contract Value | 34777070.68 | 0.065 | 226050.9594

## Potential Credits
Bath to Quiet Room Changes
Planter Box on Level 1
Water Fountain Feature
room deletions - doors and frames $10k