Current Project Picture

Monthly Project Report

Submitted: BMD | NOV 2022

Author:  KYLE CARLSON  | 008-8110 |

Executive Summary

Description of Project

Sitlzer engaged BMD to complete the RCTA Project which involved upgrading the Thorngate Rd Intersection, construct a new entry Road to the proposed training facilities and install Potable Water Infrastructure 63mm PE and 150 PVC Mains. Works included Traffic Management staging for the external works, numerous pavement types included Chip seal, Asphalt and Interlocking Block Pavers, Bulk Earthworks to Roads, Building Pads for the 360 CSR and Range Control Precincts. Stormwater RCBC Crossings and Landscaping

Month Goals

- Thorngate Road Opened to traffic and traffic management (shuttle flow) removed.

- Overhead powerlines removed (delay)

Month Achievements

- Pavers into mC-02 entry completed

- Culvert-01 rock protection works completed

Month Problems or Issues

- Ongoing delay in Removal of Overhead Powerlines - delay resolved, powerlines have been removed allowing commencement of Thorngate Rd widening works in Jan.

- Rainfall continues to be an issue - site received over 400mm over Christmas break.

- Has been discovered early Nov that a culvert headwall will need to be demolished and re-constructed due to incorrect orientation. Unlikely to recover - self performing with BMD concrete crew in Jan.

- Consultant has started holding BMD to a 48 hour inspection booking timeframe which has made it more difficult to obtain bookings when we need them.

- Fencing issue discovered - gates installed are incorrect size. Will be cost associated with re-building larger gates - circa 20k.

Month Results or Conclusions

- Overall production was low due to programme slippage because of client delays, wet weather, re-works.

- Able to hold margin, however it’s unlikely we will hold this position in January due to low productivity, high labour holding costs and a slow start to the year.

- Project received high overhead costs for annual leave for employees no longer on site.

- Delay claim has not been assessed by client or submitted to head client.

Recommendations

- Push for a response/assessment of the delay claim to ensure we know our position (meeting set with Maurice tomorrow to review).

- Focus on planning, booking subbies/plant a head of time to avoid delays in this stage of the project.

Delays

- Paving works - subbie had trouble tieing in pavers to the previous stage, took almost 1 week longer than anticipated to finish the Thorngate Road section.

- Overhead powerline removal delaying commencement of tie-in roadworks on Thorngate Rd.

  - EOT notice submitted and regular updates being provided to client with program updates.

  - Delay claim submitted with costs for re-sequenced works to date and future delay costs inc. overheads.

  - Delay has been removed - client has suggested that they wish to assess the claim at the end of the project rather than approve it now. My feeling is that they believe we are behind on other works (i.e. concurrent delay) however we are on track to complete other non-delayed works on time and I will provide regular status programmes to show this.

Delay to HV pit completion in MC-04 - delay cause is another subbie, so I have been talking to Siztler about this and it’s in the meeting minutes and programme but no notice sent yet (will be hard to come by a claim for this but I just want to ensure it does not hinder our Overhead powerline delay claim)

RFI’s

- Sample Submissions

- Concrete apron around HV pits

- Gates sizes confirmation

- Marker post location / height w.r.t. shoulder

Key Contract Dates

| Contract Award | 10/04/2022 |  |
| --- | --- | --- |
| Possession of Site | 21/04/2022 |  |
| Comments |  |  |
| Original Date for Practical Completion | 11/04/2023 |  |
| Approved Extension of Time Claims | 1 to meet actual POS date |  |
| Approved Date for Practical Completion | 24/04/2023 |  |
| Pending Extension of Time Claims | Overhead Powerline Delay |  |
| Forecasted Date for Final Completion | 09/06/2023 | No PC under this contract, only FC. |
| Days Ahead /behind Forecast program | 0 Days (float taken up by EOT/delay) |  |
| Liquidated Damages |  |  |
| Exposure $ | 0 Days / $ Quantity |  |
| Comments | EOT ongoing for overhead delay, which will push out PC accordingly. Client is pushing to assess and approve further down the track, but BMD will likely push back on this after internal review. |  |

Delays & Actions

- Overhead delay - costs submitted, pushing for assessment/response

Internal Delays and Actions:

Nil

Program/Status

- EOT’s claimed and approved

- 1 No for Possession of Site actual Date - Approved

- 1 No ongoing - Overhead powerline removal delay - awaiting final approval of date

Financial Report

Financial Status Summary

- Refer FSR spreadsheet

Contract Valuation Report

- Refer Val Report

Financial Status Report

- See attached FSR with Comments

- Overall Summary / Notes / Important detail

Over/Under Claim Report

- Refer Over/Under Report attached

Contract Variations Head Contract

- Refer Variation Register attached

Contract Variations Sub Contractors

- N/A

R & O Register

- Refer R&O Register attached

Client Relationship

- Overall Summary / Notes / Important detail

Currently the relationship with the site team is amicable, the client is difficult in terms of administration and HSE systems and that is taking up a lot of engineering time.

I am in regular contact with Trent Hutchings (Senior CA) to try and resolve / chase any pressing VO’s / Issues

Contractual /Commercial issues/Disputes

- Working around other subcontractors -potential for further disruption which aim to try and recover a portion of where it will require us to re-work things such as in MC-04 due to NT Electrical

Risk & Opportunities

- Refer spreadsheet

Resources

BMD Staff & Sub-Contractors

Labour Hire

Training/Local Industry Participation (TPAS)

| Project Training Requirement | e.g. Project KRA 1 and KRA 2, |  |
| --- | --- | --- |
| IPP Targets Achieved | DD-MM-YYYY |  |
| Name |  | Training / Certificate |
| Ima Digging | New Entrant |  |

Plant/Equipment - Required / Concerns

Subcontractors on Site for Month

- Hi QA

- Construction Sciences

- Fulton Hogan

- Spray Grass International

- EJA Survey

Procurement status including subcontractors & performance

Pre-Orders / Subcontractors / Suppliers

- Materials

- Plant

- Subcontractors

- Fulton Hogan Subcontract not executed - works underway

Completion Activities

|  | Status / Comments | Action | Date Due |
| --- | --- | --- | --- |
| Retention Security |  |  |  |
| Primary Security |  |  |  |
| Subcontractor Payment Security |  |  |  |
| Plans /As Constructed | HOTO has commenced, regular meetings being undertaken with client to keep on track |  |  |
| Actions |  |  |  |
| QA |  |  |  |
| P/C On maintenance |  |  |  |
| Handover / Project Sheet |  |  |  |
| P/C Off maintenance |  |  |  |
| Close Out Report |  |  |  |

Estimating Feedback

Production Rates - no concerns at this time

Progress Photos