## Sheet1
[11 empty] | Completed | C&V | Other team
| Friday 8/03/2024 | Saturday 9/03/2024 | Sunday 10/03/2024 | Monday 11/03/2024 | Tuesday 12/03/2024 | Wednesday 13/03/2024 | Thursday 14/03/2024 | Friday 15/03/2024 | Saturday 16/03/2024 | Sunday 17/03/2024 | Monday 18/03/2024 | Tuesday 19/03/2024 | Wednesday 20/03/2024 | Thursday 21/03/2024 | Friday 22/03/2024 | Saturday 23/03/2024 | Sunday 24/03/2024 | Monday 25/03/2024 | Tuesday 25/03/2025 | Wednesday 26/03/2024 | Thursday 27/03/2024
Duct bank 28 | C&V pour 1st lean mix lift 36m3 -Digger and spotter required |  |  | C&V FRP second lean mix lift 27m3 Super City Sawcut -Mark out required |  |  | Super City Dowel |  | strip shutters |  |  | install dowels and crack repair |  | C&V FRP PCC pcc steel delivery -TBC L12 | C&V FRP PCC -TBC L12 | C&V FRP PCC -TBC L12 | GODS DAY
Duct bank 16 |  | C&V pour 1st lean mix lift 30m3 -Diggerx2 |  | Super City Sawcut -Mark out required | C&V pour 2nd layer lean mix 23m3 Super City Dowel |  |  | Strip shutters Super City Dowel |  | GODS DAY! |  | FR blockout | install dowels and crack repair | pcc steel delivery | [6 empty] | C&V FRP PCC -TBC L12
Duct bank 14 |  |  |  | C&V form up sides -Pre pour arvo Super City Dowel | C&V form up sides -Pre pour arvo Super City Dowel |  | C&V pour 1st layer lean mix lift TBCm3 Super City Sawcut -Mark out required | Super City Dowel | C&V 2nd layer lean mix TBCm3 | GODS DAY! | Strip shutters |  | FR Blockout | install dowels and crack repair
Duct bank 12 |  |  |  | Super City Sawcut -Mark out required | Super City Dowel |  |  | C&V 1st layer lean mix Super City Dowel | Super City Dowel | GODS DAY! | C&V 2nd layer lean mix 21m3 | strip shutters |  |  | install dowels and crack repair
Duct bank 13 |  |  |  | remove soft spot proof roll | 1st layer base | 2nd layer base
Duct Bank 10 | [7 empty] | Pump water | Pump water | Back fill trench,compact,excavate | pour unsuitable lean mix 600mm | pour unsuitable lean mix 600mm | pour unsuitable lean mix 600mm | Blinder Norgroup SUPER CITY AND L11 | FRP | FRP | Pour |  |  |  | Leanmix Cap
SC09
SC04 | [7 empty] | CV pour blinding TBCm3 -Digger required | C&V FRP | GODS DAY! | C&V pour top of apron TBCm3 | strip shutters
SC03 | [7 empty] | CV pour top of apron TBCm3 -Digger required | Strip shutters | GODS DAY!
L12 Culvert | [8 empty] | access track for exsisting drain | Excavate | Excavate GODS DAY! | C&V pour blinder 15m3+ Digger required | C&V FRP | C&V FRP | C&V FRP | C&V Pour TBCm3 Pump required | C&V strip and clean and cure
L11 Culvert
Swale aprons | [8 empty] | SC01 rockline -Excavator from DB pours required, Moxy and Loader to shift rock | SC01 rockline -Excavator from DB pours | SC01 rockline -Excavator from DB pours | SC08 rockline -Excavator from DB pours | SC08 rockline -Excavator from DB pours | SC08 rockline -Excavator from DB pours | SC09 rockline | SC09 rockline | SC09 rockline
Mag sign | Excavate | FRP | FRP |  |  |  |  | MAG 25 Blinding | MAG 25 FRP | GODS DAY! | MAG 25 FRP | MAG 25 Pour
HV Service Centre access rd | Vac truck trench HV | Vac truck trench HV | Vac truck trench HV | Vac truck trench HV | Vac truck trench HV | Vac truck trench HV | Vac truck trench HV
Finish works Siera to Victor | [6 empty] | topsoil haulage and place | topsoil haulage and place SC04 | topsoil haulage and place SC01 | topsoil haulage and place SC01/7 | topsoil haulage and place SC07