## ProjectBudget
PROJECT BUDGET
Budget Proposal from Estimator and GM/CM Budget Margin Call
| Project Name: | Rockpool Pelican Waters |  |  |  |  | Project No: | 21033
Estimator Budget Proposal | [10 empty] | GM / CM Signature required before letting this trade? Y/N
Item | Trade | Selected Trade | Budget | QS Issue | Difference 5.08 Budget to QS Issue | Buyout and Cost Risks | Estimator Comments | Revised Budgets | PM Target Adjustments | Jobpac Budgets
1
2 | 2 - BULK EARTHWORKS | Daniels | 201242 | 201242 | 0 |  |  | 201242
3 | 3 - PILING | Australasian Pilng | 1349563 | 1349563 | 0 |  | Possible Additional cost for increase in Steel Reo Cost & concrete Supply; Oppertunity for Reo inclusion in PS Sum | 1349563
4 | 4 - TERMITE TREATMENT | Termiprotect | 8580 | 8580 | 0 |  |  | 8580
5 | 5 - DETAILED EXCAVATION | McNab | 91545 | 91545 | 0 |  |  | 91545
6 | 6 - CONCRETE SUPPLY | Cordwells | 538076 | 538076 | 0 | 19000 | Advised $5 per M3 for fuel Surcharge in April | 557076
7 | 7 - CONCRETE LABOUR | TMD | 529368 | 529368 | 0 |  |  | 529368
8 | 8 - CONCRETE PUMPING | McNab | 143597 | 143597 | 0 |  |  | 143597
9 | 9 - CONCRETE TESTING & SUNDRIES | McNab | 62421 | 62421 | 0 |  |  | 62421
10 | 10 - REINFORCEMENT SUPPLY | McNab | 727261 | 727261 | 0 |  | PC Rate of $1960/t to be included in the contract | 727261
11 | 11 - REINFORCEMENT PLACING | Hulk Steelies | 214152 | 214152 | 0 |  |  | 214152
12 | 12 - POST TENSIONING |  | 0 | 0 | 0 |  |  | 0
13 | 13 - FORMWORK | Formwork Services | 994001 | 994001 | 0 |  |  | 994001
14 | 14 - PRECAST CONCRETE |  | 0 | 0 | 0 |  |  | 0
15 | 15 - MASONRY - BLOCKWORK | MG Brick and Blocklaying | 1817765 | 1817765 | 0 |  |  | 1817765
16 | 16 - MASONRY - BRICK |  | 0 | 0 | 0 |  |  | 0
17 | 17 - WATERPROOFING & TANKING | M&M Waterproofing | 256310 | 256310 | 0 |  |  | 256310
18 | 18 - STRUCTURAL STEEL | Bridge Fab | 176000 | 176000 | 0 | 3000 | Possible Additional cost for increase in Steel Reo Cost | 179000
19 | 19 - ROOFING | Havendeen | 255327 | 255327 | 0 |  |  | 255327
20 | 20 - ROOF ACCESS & SAFETY | Soteria | 28265 | 28265 | 0 |  |  | 28265
21 | 21 - ALUMINIUM WINDOWS & DOORS | Hitec - Sunenergy Spec | 1189248 | 1189248 | 0 |  | Hi-tec Glazing pricing adopted prior to their insolvency | 1189248
22 | 22 - BALUSTRADES |  | 0 | 0 | 0 |  |  | 0
23 | 23 - TIMBER WINDOWS & DOORS |  | 0 | 0 | 0 |  |  | 0
24 | 24 - METALWORK | Custom metal Solution | 646695 | 646695 | 0 | 48502.125 | 5%-10% increase in Aluminium advised during March. Based on market advice of aluminum material uplift. No specific advice received from subcontractors. | 695197.125
25 | 25 - SCREENS, AWNINGS & FAÇADE ELEMENTS |  | 0 | 0 | 0 |  |  | 0
26 | 26 - CLADDING | Best tiling | 64499 | 64500 | 1 |  |  | 64500
27 | 27 - ROLLER DOORS | Noosa Garage Doors | 5697 | 5697 | 0 |  |  | 5697
28 | 28 - OPERABLE WALLS |  | 0 | 0 | 0 |  |  | 0
29 | 29 - TRUSSES | Custom Steel Frames | 196190 | 196190 | 0 | 3000 | Possible Additional cost for increase in Steel Reo Cost | 199190
30 | 30 - TIMBER DOORS & FRAMES | Ricks Doors | 252679 | 252679 | 0 |  |  | 252679
31 | 31 - DOOR & SUNDRY HARDWARE | Able | 144710 | 144710 | 0 |  |  | 144710
32 | 32 - CEILINGS & PARTITIONS | Apex | 3016797 | 3016796 | -1 |  |  | 3016796
33 | 33 - CARPENTRY - MISCELLANEOUS | McNab | 124888 | 124888 | 0 |  |  | 124888
34 | 34 - TOILET PARTITIONS | JD Macdonald | 1557 | 1557 | 0 |  |  | 1557
35 | 35 - TILING SUPPLY | National Tiles | 155550 | 155550 | 0 |  |  | 155550
36 | 36 - TILING INSTALL | GT Tiling | 383457 | 383458 | 1 |  |  | 383458
37 | 37 - FLOOR COVERINGS | Floor Smart | 1057328 | 1057328 | 0 |  |  | 1057328
38 | 38 - JOINERY & BENCHTOPS | Corona Cabinets | 1497650 | 1497651 | 1 | -60000 | Opportunity for Scozia or Onestop Joinery | 1437651
39 | 39 - COMMERCIAL KITCHEN, SERVERY & EQUIPMENT | Lamberts | 266962 | 266962 | 0 |  |  | 266962
40 | 40 - COMMERCIAL LAUNDRY & EQUIPMENT | Connoisseur | 14304 | 14304 | 0 |  |  | 14304
41 | 41 - APPLIANCES |  | 0 | 0 | 0 |  |  | 0
42 | 42 - HYDRAULIC SERVICES | Peak | 2420741 | 2420741 | 0 |  |  | 2420741
43 | 43 - SANITARY HARDWARE/HYDRAULIC FFE | Reece - Carsledine Approved Savings | 735256 | 735256 | 0 |  | Opportunity for Scozia | 735256
44 | 44 - ELECTRICAL SERVICES | Monteur | 2186001 | 2186001 | 0 |  |  | 2186001
45 | 45 - NURSE CALL (Provisonal Sum) |  | Included in PS SUMS | Included in PS SUMS | Included in PS SUMS |  |  | Included in PS SUMS
46 | 46 - MECHANICAL SERVICES | Applied Air Services | 1556200 | 1556200 | 0 |  |  | 1556200
47 | 47 - FIRE SERVICES | Progress Fire | 618960 | 618960 | 0 |  |  | 618960
48 | 48 - LIFT SERVICES | Kleemann | 363688 | 363688 | 0 |  |  | 363688
49 | 49 - LANDSCAPING | Penfolds | 428931 | 428931 | 0 |  |  | 428931
50 | 50 - RUBBISH/LAUNDRY CHUTE SYSTEM | JD Macdonald | 20530 | 20530 | 0 |  |  | 20530
51 | 51 - PAINTING | BBC | 496356 | 496356 | 0 |  |  | 496356
52 | 52 - RENDER | Imperial Coatings | 283729 | 283727 | -2 |  |  | 283727
53 | 53 - SIGNAGE | McNab | 38210 | 38210 | 0 |  |  | 38210
54 | 54 - ROADS |  | Included in Concrete Trades | Included in Concrete Trades | Included in Concrete Trades |  |  | Included in Concrete Trades
55 | 55 - DESIGN FEES | McNab | 152640 | 139640 | -13000 |  | Removal of building certifier scope from design fees | 139640
56 | 56 - PROVISIONAL SUMS | McNab | 867000 | 867000 | 0 |  |  | 867000
57 | Preliminaries |  | 4104531.18 |  |  |  | $45,000 BG offer with only $22,500k value to be realised on 1x 2.5% BG | 4104531.18
| Subtotal Cost |  | 30684457.18 |  | -13000 | 13502.125 |  | 30684959.305
| Total Revenue (GMP Revenue) |  | 34192400 |  |  |  |  | 34192400
| Margin on Revenue ($) |  | 3507942.82 |  |  |  |  | 3507440.695
| Margin on Revenue (%) |  | 10.26% |  |  |  |  | 10.26%
Estimator Signature:
Project Budget (set by GM/CM)
Margin on Turnover:
PM Signature:
GM / CM Signature:
NOTE: PM to distribute the budget changes where the "Project Budget" differs from the "Estimator Budget Proposal"