## Sheet1
| 2021-06-09 | 13/09/21 | 20/09/21 | 27/09/21 | 2021-04-10 | 2021-11-10 | 18/10/21 | 25/10/21 | 2021-01-11 | 2021-08-11 | 15/11/21 | 22/11/21 | 29/11/21 | 2021-06-12 | 13/12/21 | 20/12/21 | 27/12/21 | 2022-03-01
Week
Construction Aspect | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Site establishment | bar: Week 1
Civils:
Site access
Temp plumbing & Hyd connections | bar: Week 1
Temp electrical and Energex connections | bar: Week 1
Sediment control | bar: Week 1
Bulk Cut | bar: Week 2
Structure:
Foundations | bar: Week 3
Frame | bar: Week 4 to Week 6
Brick External | bar: Week 6 to Week 8
Roof | bar: Week 8 to Week 10
Insulation | bar: Week 10 to Week 11
Internal Linings | bar: Week 10 to Week 11
Glazing | bar: Week 11 to Week 12
Facades | bar: Week 12 to Week 13
Carpentry fix-out | bar: Week 13 to Week 15
Services:
Plumbing | bar: Week 14 to Week 15
Electrical | bar: Week 14 to Week 15
HVAC | bar: Week 15 to Week 16
Drainage | bar: Week 15 to Week 16
Finishes:
Flooring | bar: Week 16
Paint | bar: Week 17
Joinery | bar: Week 18
Plumbing fit off | bar: Week 18
Electrical fit off | bar: Week 18
Drainage fit off | bar: Week 18
Hardscape
Landscape | bar: Week 18
Final Clean