CPCCBC4005A

Produce labour and material schedules for ordering

ASSESSMENT SUMMARY

The assessment activities for CPCCBC4005A Produce labour and material schedules for ordering cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Callum Quinn |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name | Chris Abbott |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Callum Quinn |
| --- | --- |
| Participant signature |  |
| Date | 22/11/2021 |

| Assessor name | Chris Abbott |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 30 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Concrete Suppliers | Earthworks Plant Operators |  |
|  | Pre Fabricated Frame & Truss | Carpenters |  |
|  | Window Suppliers. | Painters |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | It is important to schedule tasks, as builders will not always have employees on hand who have the specialist skills required to complete a project. Generally, a contractor is someone who runs their own business and provides services to other businesses or individuals. An employee works in and is part of a business. A builder can closely direct the work to be undertaken by an employee A contractor can decide what work they do, how it is to be carried out and the hours when the work is to be completed |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | The local council will need to be considered as they will be responsible for granting the building approval. The QBBC must be consulted also as they will in QLD provide the home warranty insurance on completion of the build. |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | The colour selections will form part of the contract and be require for ordering of most special-order building materials. The colour of a roof may also effect the energy efficiency of a roof or mean certain products cannot be warranted (such as painted external doors exposed to direct sunlight due to their likely warping. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | All necessary permits should have been obtained prior to scheduling labour and materials. The main condition of approval that can affect scheduling is the allowable working hours and working days, which varies between councils. If the local council stipulates that construction work be carried out only in the hours between 7:00am and 6:00pm on weekdays and Saturdays, your scheduling will have to be adjusted accordingly. |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Fixtures Fittings & Equipment schedule is | The FF&E schedule is where you will find the make and model of the oven along with the colour, the window coverings and the benchtop material type, thickness along with any other equipment and or fittings. |  |
|  | Window Schedule | As most windows are fabricated for each job the window manufacturers require specific information regarding the framing of the window, (timber/aluminium), the exact size, the size of the opening, which way the window opens and the type of screening it will have and colour and certain performance requirements are all often specified for each and every window as with out this it is very difficult to price a project. |  |
|  | Landscaping Schedule | Landscaping requirements can differ greatly and, in many developments, can be linked to the development approval. This plan and schedule will contain the exact species of plants, the pot sizes, their locations, grass types, fencing types etc. |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | Put it in writing, inform the client of any additional costs or delays & get agreement before commencing work. |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Colour Selection | Should a client wish to have a nonstandard colour bond roof from the factory now they may need to be prepared to wait 6 months as these colours are not available now due to material shortages. Painting the roof once installed may be one work around should the client wish to pay for the painting. . |  |
|  | Wider appliances. | Should a client decide mid build that they are no longer happy with just a 600 electric wide cooktop as they like cooking with woks, they would have to possibly pay the restocking fee on the old appliance, pay the difference in cost plus (including margin and admin fees). Their kitchen design may need revisiting and modification to house the wider appliance and this may delay the completion date of their build if it is a critical path item. |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Material shortage | Let’s say that 60mm ANTICON roofing blankets run out completely mid build, we may need to use traditional wrapping of the roof and bulk insulation to achieve the same performance but as it will be different to what was specified under the roofing section of the sales contract this would have to be documented as a change and agreed to by the client in this case at no extra cost to them it would also be unlikely that the builder could claim extra time in this case. |  |
|  | Rock as a latent ground condition. | Should undocumented un-rippable rock be discovered while performing earthworks, the extra costs and delays caused by this rock would form a variation to the contract for the extra costs to remove and possibly replace the rock with suitable fill, an extension of time to the completion date would also likely apply. |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 3 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 4 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 5 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | Overlay drawings are drawings that show further detail on top of any existing plans and specifications. Overlay drawings are generally designed to: - Provide more visual clarity about a building process - Provide advice if there have been changes that require subsequent engineering redesign/specialist changes (e.g. from architects, soil experts) |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | - Work - Time period - Agreed rates |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | Order Date and Delivery Date, Purchase Order Number, Supplier details, Delivery Details, Supplier Contact info, project manager details, product descriptions, Terms and Conditions, Total Order Cost, |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet is a sheet used to track when materials are needed and when they should be ordered. This tool allows site personnel to schedule and coordinate activities that are to be undertaken on-site. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | For construction plans, (including Safety In Design plans), Site Plans & Specifications. |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | 250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Pre fab Trusses | 4 wks | 1/03/2022 | 1/02/2022 | Please supply additional timber for bracing and packing out of the eves to take FC. |  |
|  | Skylight | 1 week | 8/03/2022 | 1/03/2022 | 600mm by 600mm wide, vented, please note that the roof type is tiled. . |  |
|  | Freestanding Oven 600 wide | 4 weeks | 30/04/2022 | 1/04/2022 | GAS type is natural gas as apposed to LPG, please ensure correct values are supplied. |  |
|  | Roller Door | 1 Week | 17/03/2022 | 10/03/2022 | Please supply the roller door without the motor optional extra as the client is needing to keep the building cost down but may have one fitted later so will ensure the door installed can take motor later. |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | The number of square metres is turned into sheets an then ordered with waste. | Many extra metres can be required due to sheet sizes and raking cuts, sheets can often be purchased in 600w 900w and 1200 mm wide and the correct sheets must be ordered to suit the stud spacing for e.g. 900wide sheets would span 2 studs but 600’s would mean one end of each sheet would be floating triggering extra expense in packing out or battening. |  |
|  | Wall frame | If choosing timber wall framing, 70 and 90 mm wall thicknesses are the two main options. | A home may be drawn in 70mm frame but have cavity sliders and insulation that must be installed in 90mm wall frames. This is often overlooked. |  |
|  | Windows | Confirm the suppliers quote by checking it against the actual plans to ensure all handing and correct. | BAL ratings, energy effiecney, and acutic requirements that may be applicable must always be checked if required to ensure they are include on the quotes before they are turned into orders. |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer | Dear Client, During the completion of your site scrape today the 22/11/2021 at 123 fake st, faketown 4570 a wet patch in the soils was discover. As this is the corner of the block that your house has been designed to be constructed on this soft material will require removal and replacement to ensure your building is founded into materials with the required KPA for bearing the designed building loads. The good news is that the softer patch was only 600mm deep and was limited to the rear corner only. The rectification of this soft ground will require some import of structural compactable fill under level 1 supervision in 200mm layers by a qualified civil contractor to ensure that the home can be build as designed the total for the extra costs to complete this work is $1500 including GST and will add 4 days to the initial agreed upon practical completion date provided you can reply with your agreement to this variation in the next 48 hrs in writing at which point we can book the contractors in to complete these extra required works. I would like to also note that while the geotechnical tests that you provided did test the block in 2 locations neither bore hole showed any such material or soft ground and as the material contained weeds and marketing brochures for the estate, we are happy to provide you with pictures of the material extracted from the ground should which to attempt to recoup these costs from your developer. Yours Sincerely, Construction Manager. |  |
| --- | --- | --- |

CPCCBC4005A

Produce labour and material schedules for ordering

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | Callum Quinn |
| --- | --- |
| Participant signature |  |
| Date | 22/11/2021 |

| Assessor name | Chris Abbott |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4005A

Produce labour and material schedules for ordering

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to produce schedules of resource requirements so that orders can be placed for materials and labour for projects, and costs can be recorded and tracked as they are incurred. - Occasion 1: Residential project - Occasion 2: Commercial project The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - A copy of a material/labour schedule or supplier list for a project - A copy of a purchase order for purchasing materials or other resources - A cost report - Site condition reports or dilapidation reports - Contract documents - Call forward sheets - Variations The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document. |  |  |  |
| Resources required: Contract documentation (including plans and specifications), computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: | Callum Quinn |  |  |
| Name of observer: | Damien Carroll |  |  |
| Role of observer (Confirm suitability to sign) | Direct Supervisor as senior estimator |  |  |
| Email address of observer | damien.carroll@murphybuilders.com.au |  |  |
| Signature of observer: |  |  |  |
| Date: | 22/11/2021 |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Consider all contract conditions in the schedules, including: - All contractual requirements - Local government and regulatory bodies’ conditions of approval - Colour selections - Variations to contracts, raised by the client or builder |  |  |  |
| - Produce material and labour schedules, including: - Details of nominated suppliers and contractors in work schedules - Application of contract rates |  |  |  |
| - Produce relevant overlay drawings. |  |  |  |
| - Include contract details and instructions on orders. |  |  |  |
| - Prepare site files, including: - All necessary site documents, including plans and specifications - Preparation of call forward sheets, detailing all orders |  |  |  |
| - Analyse project costs against estimates during construction. |  |  |  |
| - Analyse approved variation costs. |  |  |  |
| - Provide a final project cost analysis. |  |  |  |
| - Maintain data files of standard costs, including: - Approved variation cost increases - Changes to standard plans, specifications, and cost files |  |  |  |
| - Effectively communicate using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication |  |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments

Callum has worked in a role generating orders for our investment homes in NSW and QLD. This task is performed by Callum for 8 months and was his primary daily task. Every home required approximately 30 separate purchase orders containing exact requirements relating to each home from each supplier. These orders were then sent via the systems we use directly to the suppliers and were delivered to site as required by the trades. There is currently a project being completed on Frazer Island for which Callum is actively procuring items for daily. This project is particularly challenging as the client is changing the build on the go, the build is off grid and must withstand marine environments and all goods must be driven 6 hours by 4wd truck to the jobsite from rainbow beach which is already a few hours from most suppliers.