CPCCBC4029B

Apply construction information to the sales process

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Hamilton Hayden |
| --- | --- |
| Participant signature |  |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |

| Date | Click here to enter a date. |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 18 |  | Yes | No |

Assessor Comments

Outline the circumstances in which a building licence must be obtained before carrying out building work.

| Answer | For any building work valued over $3,300 For building work valued over $1,100 where it involves hydraulic services design. For building work of any value which involves: drainage, plumbing, gas fitting, termite management, fire protection, completed residential building inspection, building design – low rise, medium rise and open, or site classification. |  |
| --- | --- | --- |

Describe the steps involved in organising electricity supply to site. Provide approximate timeframes for this process.

| Answer | 1. Have the electrical contractor contact the distribution network to see if supply is available. 2. If supply is not available, have the distribution network advise the cost and timeframe to make it available. (approx. 20 days to received answer) 3. If supply is available, have the electrical contractor enter into an agreement with the distribution network service provider. (approx. 10 days to received network connection offer). 4. The electrical contractor will submit an Electrical Work Request (EWR) to the distribution network once the work is complete. 5. A copy of the EWR will be sent to the clients electricity retailer. 6. After work is complete, the distribution network service provider will visit the premises to inspect the work. (They typically need 5 days to do this). |  |
| --- | --- | --- |

True or False (Tick your response): Staged approval is one type of approval that may be sought for the building approval stage.

| Answer | ☒ | True |  |  |
| --- | --- | --- | --- | --- |
|  | ☐ | False |  |  |

True or False (Tick your response): Building provision approvals are issued by the local government (e.g. Brisbane City Council).

| Answer | ☒ | True |  |  |
| --- | --- | --- | --- | --- |
|  | ☐ | False |  |  |

Describe the steps involved in organising water supply to site. Provide approximate timeframes for this process.

| Answer | 1. Check the contractual or legal requirements. 2. Submit a Water Approval application to the local water utility provider. 3. Once approval is given, have the plumbing contractor make the connection. 4. Notify the Local Water Utility Provider that the connection has been made so that they can inspect if necessary. Standard connections for simple residential developments are usually completed in 5 days. |  |
| --- | --- | --- |

Which section of the Building Code of Australia outlines energy efficiency performance standards?

| Answer | Section J |  |
| --- | --- | --- |

Describe the long-term benefits of sustainable building solutions. List one (1) environmental benefit and one (1) benefit for the client.

| Answer | Topics | Definition |  |
| --- | --- | --- | --- |
|  | Environmental benefit | Lower environmental damage through choice of building materials etc. or emissions via operations of the structure. |  |
|  | Client benefit | Lower energy costs for running the asset. |  |

Match the insurance types and definitions by writing the appropriate letter next to each number in the centre column.

| Answer | Insurances |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Builder’s All Risk | 1 -B | A | Covers personal injury or property damage. |  |
|  | 2 | Indemnity | 2 -C | B | Covers accidental risks of physical loss or damage during construction, third party liabilities and advance loss of profits. |  |
|  | 3 | Public Liability | 3 -A | C | Covers costs where a contractor has caused building errors or omissions. |  |
|  | 4 | Workers’ Compensation | 4 -D | D | Covers death, injury or illness of employees. |  |

True or False (Tick your response): Insurance should be taken out by the contractor prior to starting construction.

| Answer | ☒ | True |  |  |
| --- | --- | --- | --- | --- |
|  | ☐ | False |  |  |

Select and describe five (5) trades involved in the construction process.

| Answer | Trade | Description |  |
| --- | --- | --- | --- |
|  | Excavation | Prepares the site for building by grubbing and excavating the foundations |  |
|  | Electrician | Arranges electricity to be connected; places wiring for lighting and power cables, fixes switches, installs power points, wires electrical systems. |  |
|  | Plumbing | Organises water supply; installs pipes and drains, installs roof and guttering, fits taps etc. ensures that downpipes and the swer is connected. |  |
|  | Gas Fitting | Places gas pipes to appliances |  |
|  | Concreting | Installs formwork and boxing; pours concrete (e.g. slabs). |  |

Order the following steps from 1 to 10 to identify an appropriate construction sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 3 | Floor frame |  |
|  | 5 | Windows and external door frames |  |
|  | 7 | Wall insulation |  |
|  | 1 | Set out |  |
|  | 9 | Painting |  |
|  | 6 | Electrical wiring |  |
|  | 2 | Plumbing of waste pipes |  |
|  | 8 | Internal linings |  |
|  | 10 | Landscaping |  |
|  | 4 | Wall frames |  |

For each of the main stages of construction listed below, identify the main trades involved and an approximate duration of each stage for a standard.

| Answer | Stage | Description |  |  |
| --- | --- | --- | --- | --- |
|  | 1: Clearing of the site | Trades | Demolition, Soil Testing, Civil Contractor |  |
|  |  | Duration | Varies depending on the site |  |
|  | 2: Slab or base stage | Trades | Excavation, Steel Fixer, Concretor |  |
|  |  | Duration | 1 – 2 weeks |  |
|  | 3: Frame stage | Trades | Plumber, Electrical, Carpenter, Roofer, Insulation |  |
|  |  | Duration | 3 – 4 weeks |  |
|  | 4: Lockup stage | Trades | Glazer, Carpenter, Electrician, Plumbing |  |
|  |  | Duration | 4 weeks |  |
|  | 5: Fit-out or fixing stage | Trades | Joinery, Tiler, Fixings and Fittings |  |
|  |  | Duration | 5-6 weeks |  |
|  | 6: Practical completion stage | Trades | Decorator |  |
|  |  | Duration | 7-8 weeks |  |

Identify five (5) factors that can affect the duration of each construction stage.

| Answer | Project size and location Project Function Height of the building Building complexity Quality Requirements |  |
| --- | --- | --- |

Describe how each of the following factors can affect construction times.

| Answer | Factor | Effect |  |
| --- | --- | --- | --- |
|  | Changed conditions | Can change construction methodology (different materials, labour, plant) and/or the program. |  |
|  | Labour availability | Different trades need to be sequenced so that personnel are used efficiently, i.e. painter not on site waiting for plasterer to finish. Other major construction jobs in the area could be soaking up the available labour. |  |
|  | Material availability | Material is to be sequenced so that it is on site when it is needed, but not too early where it clogs the site or can be damaged by weather or construction works. |  |
|  | Weather | Weather can delay works, wind will stop cranes, rain will stop outdoor works. |  |

Describe the site establishment requirements for each of the points listed.

| Answer | Requirement | Description |  |
| --- | --- | --- | --- |
|  | Earthworks | Contact dial before you dig to avoid any underground services |  |
|  | Electricity | Disconnect any previous power supply to the work zones and provide any needed temporary power |  |
|  | Neighbours | Advance notice of construction dates and contact numbers |  |
|  | Waste disposal | Set up designated rubbish bins and waste removal. Check if permits required to place bins on the street |  |
|  | Water connection | Book in a plumber to perform any required disconnections prior to demolition. |  |

Identify the section of the Work Health and Safety Regulations that outlines the site establishment requirements listed.

| Answer | Regulation section | Requirement |  |
| --- | --- | --- | --- |
|  | Section 40 | The layout of the work area must allow for persons to enter, exit and move about without risk to health and safety |  |
|  | Section 41 | Adequate facilities must be provided for workers, including toilets, drinking water, washing facilities and eating facilities. |  |
|  | Section 308 | A principal contractor for a construction project must install signs outside the work area that shows their name and telephone contact numbers and site office address. |  |

True or False (Tick your response): The owner is able to access the site at any time.

| Answer | ☐ | True |  |  |
| --- | --- | --- | --- | --- |
|  | ☒ | False |  |  |

Which of the following parties should the client contact to access the site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  | ☒ | Contractor |  |
|  | ☐ | Local Government |  |
|  | ☐ | Industry Regulator (e.g. Queensland Building and Construction Commission) |  |
|  | ☐ | Subcontractors |  |