## Rock Causeway Access
Rev 3 - Feb forecast update for remaining
Rock Causeway Construction | [10 empty] | Budget | 1104697.55
Rock Material Requirement | [10 empty] | CWIP | 569794.37
| Rock Requirement (m3) | MDD | Tonnage | [8 empty] | 3364222.3963
1:7 - 8m wide, 1:1 batters | 5100 | 2.5 | 12750
Water Estimate | 1000 | 2.5 | 2500
Diversion Estimate | 550 | 2.5 | 1375
Crane Access (11m wide) |  | 2.5 | 0
Comments | Description | QTY | UOM | RATE | TOTAL
| 70/150 Mt Marrow | 6609 | T | 35 | 231315
| Type 2.3 Mt Marrow | 1242 | T | 25
Placement Allowance
| Total Tonnage | 6609
| Tonne/Day | 500
| Days | 13.218
| Hours | 11.5
| Total Hours | 152.007
January 2023 comments: Likely 11,000T to go not required, estimate 7,500t, need to check post dewatering
Bulk Placement
| Description | QTY | UOM | RATE | TOTAL |  |  | Total | 860777.1012 | Rock Causeway
| 30T TKR | 152.007 | hr | 150 | 22801.05 |  |  |  | 78545.3314 | Abutment A
| Body Truck | 76.0035 | hr | 120 | 9120.42 |  |  |  | 24157.8571 | Abutment B
| CW3 Labour Spotter | 152.007 | hr | 50 | 7600.35 |  |  |  | 68423.4365 | Dewatering
| TKR D6 Dozer | 132.18 | hr |  | 0 |  |  |  | 18250 | Flashboards removal
Misc
Diversion Channel | [8 empty] | 1050153.7263 | Sum
| Description | QTY | UOM | RATE | TOTAL
250t/day trim and shape | 14t TKR Exc | 100 | hr | 110 | 11000 |  |  | Jan CTC | 750000
| Body Truck |  | hr | 110 | 0
| CW2 Labour Spotter | 63.25 | hr | 40 | 2530
| Blackmax | 1 | LS | 6399 | 6399 |  |  | Risk with CTC | -300153.7263
Shotcrete
|  | Diversion | Downstream Bund
| Length | 50 | 40 | 15m/3/day | 4.8
| Height | 3 | 4.5 | hours | 11.5
| (m2) | 300 | 180 | Total Hours | 55.2
| 150mm thick (m3) | 45 | 27
| m3 | 72
| Description | QTY | UOM | RATE | TOTAL
Meales | Shotcrete Pump | 55.2 | hr | 150 | 8280
Meales | Abrasive mix | 55.2 | hr | 10 | 552
Meales | Abrasive mix | 72 | m3 | 10 | 720
Meales | Compressor | 5 | day | 250 | 1250
3 | Labour (Niepe) - CW5 | 165.6 | hr | 65 | 10764
Boral | Concete N20 | 72 | m3 | 250 | 18000 |  | likely $280/m3
| Misc Materials |  | ls |  | 0
Additional Ramp Requirement for 11m Crane Access (need to determine from survey, assume 35% e/o 8m ramp for now
Comments | Description | QTY | UOM | RATE | TOTAL
| 70/150 Mt Marrow | 4462.5 | T | 35 | 156187.5 |  | qty unknown, will be changes to ramp as we dewater
Placement Allowance
| Total Tonnage | 4462.5
| Tonne/Day | 500
| Days | 8.925
| Hours | 11.5
| Total Hours | 102.6375
Bulk Placement
| Description | QTY | UOM | RATE | TOTAL
| 14t TKR Exc | 102.6375 | hr | 120 | 12316.5
| Body Truck | 102.6375 | hr | 110 | 11290.125
| CW2 Labour Spotter | 102.6375 | hr | 45 | 4618.6875
Removal of Causeway
| Total Tonnage | 21087.5
| Tonne/Day | 1000
| Days | 21.0875
| Hours | 11.5
| Total Hours | 242.5062
| Concrete (m3) | 72
Bulk Shifting | Description | QTY | UOM | RATE | TOTAL
| 14t TKR Exc | 242.5062 | hr | 120 | 29100.75 |  | likely 30t
| Body Truck | 242.5062 | hr | 110 | 26675.6875
| CW2 Labour Spotter | 242.5062 | hr | 45 | 10912.7812
Load from Stockpile | Tonnage | 10543.75 |  |  |  | Assume 50% will be utilised onsite *assumption*
| Tonne/Day | 1500 |  |  |  | Opportunity to stockpile to Seqwater yard TBA
| Days | 14.0583 |  |  |  | Worse case dump fees
| Total Hours | 161.6708
| 14t TKR Exc | 161.6708 | hr | 120 | 19400.5
6 | Truck and Dog | 970.025 | hr | 110 | 106702.75 |  | incorrect qty of truck and dog required - likely 6
| Concrete Waste Fee | 72 | m3 | 45 | 3240
| Rock Waste Fee | 10543.75 | tonne |  | 0 | unknown, could be risk item here
Allowance for maintainence not included |  |  |  |  | 50000 | Plug
Allowance for overtopping/scour not included |  |  |  |  | 100000 | Plug allow 50% E/O
Please notes rates and cost are an example only
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This was 16,625T - 5480 = ~11,145 - reduced to 7,500 ~(150k saving) Reply: 16,625T - 6935 = ~9,690T remaining March forecast to go 7500T - Feb placed (891) =6,609T

## Abutment Piling Pads
Abutment A Access | [5 empty] | 78545.3314 | Abutment B Access x 2 Pads | [5 empty] | 24157.8571
Material | [6 empty] | Material
| Description | QTY | UOM | RATE | TOTAL |  |  | Description | QTY | UOM | RATE | TOTAL
| Type 2.1 Mt Marrow | 529 | T | 26.44 | 13986.76 |  |  | Type 2.1 Mt Marrow | 264.5 | T | 30 | 7935
Comments | Geofabric A29 | [5 empty] | Comments
Geogrid
Excavation | [6 empty] | Excavation
| Length | 50 | [5 empty] | Description | QTY | UOM | RATE | TOTAL
| Width | 10 | [5 empty] | 14t TKR Exc | 24.6429 | hr | 130 | 3203.5714
| Depth | 1.5 | [5 empty] | Body Truck | 24.6429 | hr | 120 | 2957.1429
| M3 | 750 | [5 empty] | CW2 Labour Spotter | 24.6429 | hr | 50 | 1232.1429
| Days | 2.1429
| Total Hours | 24.6429 |  |  |  |  | Placement Allowance
[8 empty] | Total Tonnage | 264.5 |  | Length | 10
| Description | QTY | UOM | RATE | TOTAL |  |  | Tonne/Day | 150 |  | Width | 10
| 14t TKR Exc | 24.6429 | hr | 120 | 2957.1429 |  |  | Days | 2 |  | Depth | 0.5
| Body Truck | 24.6429 | hr | 110 | 2710.7143 |  |  | Hours | 11.5 |  | m3 | 100
| CW2 Labour Spotter | 24.6429 | hr | 40 | 985.7143 |  |  | Total Hours | 23
Placement Allowance | [6 empty] | Placement
| Total Tonnage | 529 | [5 empty] | Description | QTY | UOM | RATE | TOTAL
| Tonne/Day | 250 | [5 empty] | 5T Combo | 23 | hr | 130 | 2990
| Days | 2 | [5 empty] | Body Truck | 23 | hr | 120 | 2760
| Hours | 11.5 | [5 empty] | CW3 Labour | 46 | hr | 50 | 2300
| Total Hours | 23 | [5 empty] | Roller | 2 | day | 200 | 400
[8 empty] | Watercart | 2 | day | 190 | 380
Placement
| Description | QTY | UOM | RATE | TOTAL
| 14T Exc | 23 | hr | 120 | 2760
| Body Truck | 23 | hr | 110 | 2530
| CW3 Labour | 46 | hr | 40 | 1840
| Roller | 2 | day | 200 | 200
| Watercart | 2 | day | 190 | 190
Kelly Block Wall Install and Backfill
Allow 3 days
34.5
| Description | QTY | UOM | RATE | TOTAL
| 25T Franna | 34.5 | hr | 150 | 5175
| Kelly Block | 1 | ls | 15000 | 10000 | plug
| Temp Works Design | 1 | ls | 7500 | 5000 | plug
| 14t TKR Exc | 34.5 | hr | 120 | 4140
| Body Truck | 34.5 | hr | 110 | 3795
| CW3 Labour | 34.5 | hr | 50 | 1725
| Edge Protection | 1 | ea | 2500 | 1725 | plug
Pile High Additional Costs
5 Piles | Description | QTY | UOM | RATE | TOTAL
2m High | Liner Supply | 10 | m | 1505 | 15050
| Driving of Liner | 10 | m | 100 | 1000
| Excavation | 12 | m3 | 375 | 4500

## Dewatering Pile Caps DJC
Dewatering Pile Caps
Line No 366 Item No 32002.01 | Dewatering Pile Caps |  | item | 1 |  | Contributing | 2
1 | Note:
2 | Allowance to Place Gravel Sump to Pile cap base prior to blinding, allowance for 5 No Pile Caps for the duration of pile cap construction
3
4 | Calcs
5 | EE formula - =(Allow 5 weeks) Duration |  |  | 5
6
7 | Materials
8 | EE formula - =(5 No Pile Caps * (8.5m*6.8m*0.200mthk*1.8[#MDD_BEDDING])) Drainage Layer | QUARRY AGG 20MM | tonne | 104.04 | 31 |  | 3225.24 |  | 3225.24
9 | EE formula - =(5No * 0.5, long Sump Pipe * $250) | MISC MATERIALS | $ | 625 | 1 |  | 625 |  | 625
10 | EE formula - =(5 Pile Caps * $1500) Sand Bags | MISC MATERIALS | $ | 7500 | 1 |  | 7500 |  | 7500
11
12 | Place Gravel and Sand Bags
13 | EE formula - =(Allow 3hrs per pile cap * 5No) |  |  | 15
14 | EE formula - =(15[#lq13]) | G-EXC 15T | hr | 15 | 135 |  |  | 2025 | 2025
15 | EE formula - =(15[#lq13]*2No) | LABOUR CW3 | mhr | 30 | 64.77 | 1943.1 |  |  | 1943.1
16
17 | Setup Pumps and Dewater to each pile cap
18 | EE formula - =(5No Pile Caps * 1hr) |  |  | 5
19 | EE formula - =(5[#lq18]) | G-TELEHANDLER 10T | hr | 5 | 142.2643 | 374.15 | 110.25 | 226.9215 | 711.3215
20 | EE formula - =(5[#lq18] * 2No) | LABOUR CW3 | mhr | 10 | 64.77 | 647.7 |  |  | 647.7
21 | EE formula - =($200) Misc tools | MISC TOOLS | $ | 200 | 1 |  |  | 200 | 200
22
23 | Runing Costs of Pumps etc
24 | EE formula - =(5[#lq5] * 3 Pumps * 7 days) | G-PUMP 100MM & HOSES | day | 105 | 432.115 | 10201.275 | 11576.25 | 23594.55 | 45372.075
25 | EE formula - =(5[#lq5] * 3 Pumps * 7 days * 40 litres per day) | G-DIESEL SUPPLY | Litre | 4200 | 1.47 |  | 6174 |  | 6174
26
27 | EE formula - =st(8:25,5[#lq5]) |  |  |  | 13684.6873 | 13166.225 | 29210.74 | 26046.4715 | 68423.4365
[5 empty] | 68423.4365 | 13166.225 | 29210.74 | 26046.4715 | 68423.4365

## Flashboards
Flashboard Install | [5 empty] | 18250
Material
| Description | QTY | UOM | RATE | TOTAL
Z Purlins
| Misc | [5 empty] | Spent 10 on install with Atoll
| Days Required | 10
Atoll Logistics Quote
|  | QTY | UOM | RATE | TOTAL
| Mobilisation | 1 | ea | 6500
| Flashing Support Vessel | 10 | day | 2500
Safety Vessel
| Pontoon | 20 | ea | 150
| Demobilisation | 1 | ea | 4500
Install Labour
|  | QTY | UOM | RATE | TOTAL
Niepe | CW3 x 3 | 345 | hr | 85 |  | 2 install, 1 cutting and transporting
no allowance for overtopping
Removal
| Mobilisation | 1 | ea |  | 0
| Flashing Support Vessel | 5 | day | 2500 | 12500
| Demobilisation | 1 | ea |  | 0
Install Labour
|  | QTY | UOM | RATE | TOTAL
Niepe | CW3 x 2 | 115 | hr | 50 | 5750