## Sheet1
Lessons Learned
What went well | What didn't go well | Other learnings | action steps | responsible | due date
a | ✘ | ?
Successfully switch traffic on the KP McGrath Roundabout. | Ordered the wrong end terminal |  | Check procurement items throughly, Gain approval from project manager. | Engineer | 2022-05-03
Successfully installed 29 pipes in a day | Water management of live stormwater drainage |  | Follow wet weather procedure | Site Foreman | 2022-06-04
Built the southbound embankment with preload | Structural zone compaction and moisture issues |  | Constant communication with tester | Site Engineer | 2022-06-04