CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances. Answers will be documented and FT003 (Oral examination declaration form) must be completed. - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - If a participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a participant changes their response in writing, they must put their initials next to the written change. - If a participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | R L Malhabour |
| --- | --- |
| Participant signature |  |

| Assessor name | Brett Stoward |
| --- | --- |
| Assessor signature |  |

| Date | 30/03/2019 |
| --- | --- |

| Number of questions | Number of questions answered correctly | Satisfactory? |  |
| --- | --- | --- | --- |
| 30 |  | Yes | No |

Assessor Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | HARDWARE – TIMBER | CARPENTERS |  |
|  | AMBER – BRICKS | BRICK LAYERS |  |
|  | REECE-TOILETS | PLUMBERS |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | Contractors can decide what work they will do within reason, how to carry it out and the hours when work is to be completed whereas a builder can closely direct the work of an employee on what to do, how to do it and how long the work is to be completed. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Government-Local Council Regulatory-National Construction Code |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | It is included in the construction schedule because it forms part of the Building specifications (eg.In case of Heritage Building) which details all plans , products, colour floor and cover spaces which comprises a Contract. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | It is important to adhere to council requirements on working hours and days which could vary from council to council because this may create safety issues and/or create discontent from the community which may involve Council to issue stop work notice in the premises and or penalties. A disregard of these hours and days will affect ALL SCHEDULES from delivery of goods and services being carried out; costly labour hours; to penalties for breaches and ultimately pushing completion date out. |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | MATERIAL SPEC | TYPE, STRENGH, SIZE OF MATERIAL TO BE USED |  |
|  | ELEVATIONS | DRAWINGS OF THE BUILDING SHOWING WHAT IT LOOKS LIKE FROM NORTH SOUTH EAST AND WEST |  |
|  | PRODUCT SPEC | INCLUDES ITEMS SUCH AS WHITEGOODS, ELECTRICAL SUCH AS LIGHTS AND SWITCH TYPES |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | It must be in writing, dated and signed by all parties to the contract and copies given to all parties to the contract to avoid future disputes. |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | COLOUR | Depending on its availability, cost, texture and use. |  |
|  | PRODUCT | Depending on its availability, size, cost and use |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | EXTENSION OF TIME | Eg.Weather has delayed work which can push completion date further and/or additional labour cost will be incurred. |  |
|  | MANUFACTURER INCREASES PRICE ON MATERIAL | Eg. On a provisional sum or prime cost sum - that needs to be adjusted to actual price which can be more expensive. |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | These are drawings to show further detail on top of any existing plans and specification. This supplies more visual clarity. These drawings need to be given to all parties. |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | Task details Timelines Agreed rates |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | 1.Order date and delivery date 2. Purchase order number 3.Supplier details 4.Delivery details 5.Supplier contact information 6.Product description 7.Project Manager details 8.Terms and conditions 9.Total order cost |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | This is a documents used to track when materials are needed and when they should be ordered. This tool allows site personnel to schedule and coordinate activities that are to be undertaken on site. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Approved documents like reports and permits. Plans and drawings. |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -100 |  |
|  | Plumbing | 8,000 | 8,000 | 0 |  |
|  | Tiler | 4,500 | 4,750 | 250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | concrete | 1 WEEK | 18 JUNE | 11 JUNE | DRY DAY; 7AM |  |
|  | brick | 2 WEEKS | 28 JUNE | 14 JUNE | BRICKS ON PALLETS |  |
|  | Roof tiles | 4 WEEKS | 30 JULY | 1 JUNE | TILES ON PALLET |  |
|  | Internal walls | 6 WEEKS | 15 AUG | 4 JULY | GYPROCK MUST BE SEALED |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | PROVIDE SUPPLIER THE PLAN AND SPECS OF MATERIAL REQ’D;OBTAIN LEAD TIME AND QUOTE FROM SUPPLIER. ARRANGE DELIVERY OR YOU PICK UP. | AVAILABILITY,COST, QTY &QUALITY OF MATERIAL; OBTAIN FROM REPUTABLE AND RELIABLE SUPPLIER |  |
|  | Wall frame | PROVIDE SUPPLIER THE PLAN AND SPECS OF MATERIAL REQ’D; OBTAIN LEAD TIME AND QUOTE FROM SUPPLIER | AVAILABILITY, COST, QTY & QUALITY OF MATERIAL; OBTAIN FROM REPUTABLE AND RELIABLE SUPPLIER |  |
|  | Windows | PROVIDE SUPPLIER THE PLAN & SPECS OF MATERIAL REQ’D; OBTAIN A QUOTE AND LEAD TIME FROM SUPPLIER | PROS AND CONS OF THE TYPE OF WINDOW RELATED TO ENVIRONMENTAL &SUSTAINABILITY OF MATERIAL CHOSEN. AVAILABILITY, COST AND QTY SUPPLIER CAN DELIVER. RELIABILTY & REPUTATION OF SUPPLIER IN THE INDUSTRY. |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer | REQUEST FOR VARIATION Date: 19 March 2019 Dear Brett, While excavating the northwest corner of the site- along Sussex Street, we found the soil is unsuitable for supporting the foundation. The excavated corner will require suitable soil filled in to achieve stability prior to pouring foundation. Please advise if you agree to do remedial action as suggested as soon as possible. Price breakdown per below: Plant – 3 days hire $3000.00 Labour – 5 days 3 heads 10,000.00 Materials – 30 cubic meters $2000.00 Kind regards. Lynette – LM Building Contractors |  |
| --- | --- | --- |