1. Pre-Hire Setup

Before engaging plant or equipment:

- Identify needs: Type of machinery (e.g., excavator, scaffolding, compactor), duration, and site-specific requirements.

Obtain hire quotes: From 2–3 suppliers for comparison.

- Check credentials:

  - Ensure supplier has valid insurances (public liability, operator’s ticket if wet hire).

  - Review terms and conditions for dry/wet hire.

2. Recording Hire Details

Create a Plant & Equipment Hire Register with these details:

| Field | Example |
| --- | --- |
| Equipment Type | 1.7t Excavator |
| Supplier / Hire Company | Coates Hire |
| Hire Type | Dry Hire / Wet Hire |
| Start Date | 10/12/2024 |
| End Date (4 weeks) | 10/01/2025 |
| Rate ($ per day/week) | $450/week (dry) or $800/week (wet) |
| Operator Details (if wet) | Jimmy Chew Ticket No. 23456 |
| Insurance Provided By | Supplier (wet) / Builder (dry) |
| Fuel Responsibility | Site (dry) / Supplier (wet) |
| Hours of Use (Tracked) | 8 hrs/day avg. |
| Condition on Arrival | Good – minor cosmetic wear |
| Maintenance Needed? | No |
| Notes | Use for site cut & trenching |

3. On-Site Responsibilities

Dry Hire

- Site manager/operator:

  - Must be licensed & competent

  - Is responsible for fuel, maintenance, and safe use

  - Logs daily usage hours and condition checks

Wet Hire

- Operator:

  - Provided by supplier, handles all operation

  - Typically includes fuel and maintenance

- Site:

  - Supervises usage

  - Confirms attendance & logs hours

Daily Logbook or App Entry should include:

- Hours used

- Tasks completed

- Fuel usage (if applicable)

- Any damage or issues

4. Ongoing Monitoring

- Weekly review of usage vs budget

- Confirm:

  - Equipment still required?

  - Any breakdowns or servicing needed?

- Notify supplier if extension or early return is needed

5. End of Hire Process

- Clean equipment before return (dry hire)

- Final condition report with photos

- Log total hours used

- Confirm:

  - All attachments returned

  - No outstanding fuel or repair charges

- Update register with return date & invoice