Supervisor Notes - Kitchen, Laundry, and Pantry Renovation Project

Week 1 (5/3/23 – 11/3/23)

- Demo crew arrived on site and began demolition of the old kitchen, laundry, and pantry.

- Plumbing and electrical rough-in was started, and the new layout was marked out on the floor.

- The new kitchen cabinets, laundry tubs were delivered on schedule and stored to commence

Week 2 (12/3/23 – 18/3/23)

- Plumbing and electrical rough-in were completed.

- The drywall installation started.

- The cabinet installation started.

- Wet areas, walls, ceiling, doors/windows started

Week 3 (19/3/23 – 25/3/23)

- The drywall installation was completed.

- The cabinet installation was completed.

- Wet areas, walls, ceiling, doors/windows was ongoing

- Plasterworks and waterproofing was started

- The countertops were measured, and the order was placed.

Week 4 (26/3/23 – 2/4/23)

- The countertops were installed.

- Cabinets installation was ongoing

- Skirting/architraves installation was started

- Benchtop was started

- Wet areas, walls, ceiling, doors/windows was ongoing

- Plasterworks and waterproofing was ongoing

Week 5 (3/4/23 - 9/4/23)

- Cabinets installation was ongoing

- Skirting/architraves installation was ongoing

- Benchtop was ongoing

Week 6 (10/4/23 – 16/4/23)

- Cabinets installation was ongoing

- Skirting/architraves installation was ongoing

- Benchtop was ongoing

Week 7 (17/4/23 – 23/4/23)

- The flooring installation started.

- The backsplash installation started.

- Kitchen timber tile started

Week 8 (24/4/23 – 30/4/23)

- Tiling started

- The finishing touches, such as light fixtures and outlets, were installed.

- Electrical and plumbing fit-offs started

Week 9 ( 1/5/2023 – 5/5/23)

- Windows/doors started

- Accessories fit off started

- Caulking started

- Screen installation completed

- Clean up completed

- Final inspection by the building inspector was scheduled and passed.

Overall, the project was completed on schedule, and the quality of workmanship was of a high standard. The team worked well together, and communication was excellent. The project was well-organized, and all deadlines were met. There were no major issues or concerns, and the client was satisfied with the final outcome.