Assessment Workbook 2

BSB51415 Diploma

of Project Management

Constraint Management

Version 1.11 Produced 18 October 2018

Copyright © 2021 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following Training Package update | 1.0 |
| 22 June 2017 | Updated Table of Contents | 1.1 |
| 18 October 2018 | Change to Practical Assessment | 1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Written Questions	5

Part 1 – Project Scope	5

Part 2 – Project Time	17

Part 3 – Project Cost	26

Part 4 – Project Quality	30

Case Study	36

Instructions to Student	36

Introduction	37

Workbook Checklist	51

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 2 |  |  |
| --- | --- | --- | --- |
| TITLE: | Constraint Management |  |  |
| FIRST AND SURNAME: | Paul Reyne |  |  |
| PHONE: | 0479067100 |  |  |
| EMAIL: | Wangas17@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Paul Reyne |  | Signature: P. Reyne | Date: 20/1/2021 |

# The Written Questions

Part 1 – Project Scope

| - Which of the following are project initiation documentation required at the start of the project? Select all that apply. |  |
| --- | --- |
|  | - Communications log |
| X | - Project plan |
|  | - Work Breakdown Structure (WBS) |
|  | - Gantt Chart |
| X | - Project charter |
|  | - Risk management |

| - Which of the following are components of a project scope-management plan? Select all that apply. |  |
| --- | --- |
| X | - Project deliverables |
| X | - Project staff assignments |
| X | - Change request |
| X | - Project justification |
| X | - Product description |
| X | - Performance reports |
| X | - Project objectives |
| X | - Project funding requirements |
|  | - Quality metrics |
|  | - Budget forecasts |

- In your own words, discuss how project time and cost affect the project scope. Do not exceed 100 words.

The project time is duration of the time the project will take to complete and the cost is the estimation of the amount of money that it will be required to complete the project. An example of the project scope that can be affected is when the scope could change mid way through the implementation of the project, the cost and time will be affected in some way.

| - Which of the following are events or problem areas relating to project scope that could trigger the need for a formal change request? Select all that apply. |  |
| --- | --- |
| X | - The deliverables may not meet quality requirements. |
|  | - Grammatical and typo errors are found in the project initiation documents. |
| X | - The deliverables may not be what the client wanted, even though they were covered in the project plan. |
| X | - The stakeholder considers the change request and advises the project manager. |
|  | - Observance of non-working holidays affecting project time. |
| X | - Additional quality requirements (such as new legislation or changes in standards) will render the deliverables non-compliant. |
| X | - Failure of equipment needed to produce the deliverables. |
| X | - Missing documentations in the project’s information system. |
| X | - Raw materials are no longer available. |
|  | - Supplier or contractor closing business. |

| - Which of the following are procedures that typically must be followed under change control processes? Select all that apply. |  |
| --- | --- |
|  | - Project manager seeks advice from supervisor regarding changes in cost. |
|  | - Project manager assigns a project team member to recalculate for the critical path. |
| X | - Project manager provides the change request to the appropriate stakeholder for approval. |
| X | - The stakeholder considers the change request and advises the project manager. |
| X | - The project manager updates the project plan and other documentation where required. |
| X | - Project manager drafts the change request. |
|  | - Project manager delegates the authority to the project team members in advising other stakeholders of the changes. |
| X | - The project manager advises relevant stakeholders (sponsor, team members, etc.) of the changes. |
| X | - Details of the proposed change to be communicated to the project manager. |
|  | - The project sponsor and owner may automatically terminate the project contract. |

| - The following are methods of measuring work outcomes and progress against plans. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Method | Description |
| C | Units completed | - Also known as the ‘steps’ method, this is used for projects that involve subtasks that need to be completed in an orderly fashion. |
| A | Incremental milestones | - In this method, tasks that are being calculated tend to occur over a longer duration time and include multiple subtasks, where subtasks can have different units of measurements. |
| D | Start / finish | - This method is used when project tasks are done repeatedly. Assuming that each task is completed at the same amount of time, resources and effort, each task is counted and totaled. |
| B | Weighted or equivalent units | - This method is used to determine the percentage of the work completed and the percentage of the work that is still yet to be completed. |

| - Which of the following are activities involved in decomposition of the total work project? Select all that apply. |  |
| --- | --- |
|  | - Summarise project tasks in the form of a written report. |
| X | - Identify and analyse the deliverables and related work. |
| X | - Structure and organise the work breakdown structure (WBS). |
|  | - Arrange the smallest project tasks to form an aggregate representation of the total project task |
| X | - Decompose the upper work breakdown structure (WBS) levels into lower level detailed components. |
|  | - Calculate duration and resource effort for each project task. |
| X | - Develop and assign identification codes to the WBS components. |
|  | - Inspect whether work and deliverables meet requirements and product acceptance criteria. |
|  | - List resources required for each project task. |
| X | - Verify that the degree of decomposition of the work is necessary and sufficient. |

- List three (3) ways in which the Work Breakdown Structure (WBS) can be created.

- Using phases of the project life cycle as the first level of decomposition, with the product and project deliverables inserted at the second level - Using major deliverables as the first level of decomposition. - Using subprojects which may be developed by organizations outside the project team such as the contracted work.

| - The following are some problem areas in scope management. In your own words, briefly discuss each problem area. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Problem areas | Discussion |
| Scope creep | Scope creep is a change or continuous change in the project scope by the client and often the project manager is un aware of this. Its adding additional features or extra work that is not in the scope of works. Scope creep in the project can cause arguments and relationship breakdowns. |
| Sponsor / project owner approval | Sponsor/ project owner approval is the procedure that is necessary in the scope management to make sure the owner/ sponsor approves the current scope and any changes that maybe put forward. It's very important that the project manager seeks this approval because if the process is disregarded , this could lead to things like not getting paid for the change. |
| Project team accountability | Project team accountability is to make sure that the project team is in charge for the goals and requirements for the project. The project team needs to be aware of the scope while agreeing how the project goals will be met. |

- In your own words, discuss the significance of scope management. Do not exceed 150 words.

Scope management helps avoid the challenges that a project may face, like scope/growth but while also assisting with any problems that may arise. Scope management establishes control mechanisms to address factors that may result in changes during the project, without these the project team would not have an understanding of what is and what isn't included in the job.

| - The PMBOK Guide outlines the following processes in project scope management. List one (1) tool or technique used in each process. |  |
| --- | --- |
| Project Scope Management | Tool or technique |
| Collect requirements | Facilitated workshops |
| Define scope | Expert Judgement |
| Create WBS | Decomposition |
| Verify scope | Inspection |
| Control scope | Variance analysis |

| - Consider the roles and responsibilities of the project manager in project planning. List five (5) roles of the project manager in project planning and list at least one responsibility for each of these roles. |  |
| --- | --- |
| Roles (list five (5)) | Responsibilities (List at least one (1) for each role) |
| Understanding the project | Must fully understand and know why the project is being initiated. |
| Scope management | Must ensure that he/she had taken down all the requirements and turned them into work packages that will soon be deliverables. |
| Time management | To be responsible for scheduling the project and coming up with the schedule baseline. |
| Cost management | To be responsible for coming up with the cost baseline. |
| Quality management | Must define what good quality means in your project from your stakeholders. |

Part 2 – Project Time

| - The following are estimation tools and techniques used in determining duration. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| B | Analogous estimating | - This technique uses a statistical relationship between historical data and other variables to calculate an estimate for activity duration. |
| A | Parametric estimating | - This uses parameters such as duration, budget size, weight, and complexity, from a previous, similar project, as the basis for estimating the same parameter to measure for a future project. This technique relies on the actual duration of previous, similar projects as the basis for estimating the duration of the current project. |
| E | Three-point estimating | - This is guided by historical information. It provides duration estimate information or recommended maximum activity durations from prior similar projects. This can also be used to determine whether to combine methods of estimating and how to reconcile differences between them. |
| C | Expert judgement estimating | - Contingencies are accounted for into the overall project schedule to account for schedule uncertainties. |
| D | Reserve analysis | - This technique uses a mathematical formula to determine a weighted average of estimates. It uses the formula:Te=To +4 x Tm + Tp6 . |

| - The following are estimation tools techniques used in determining activity resource. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Estimation tools and techniques | Description |
| D | Expert judgment | - Several companies or organisations routinely distribute updated production rates and unit costs of resources for an extensive array of labour trades, material, and equipment for different countries and geographical locations within countries. |
| E | Alternative analysis | - In this technique, when an activity cannot be estimated with a reasonable degree of confidence, the work within the activity is decomposed into more detail. The resource needs are estimated. These estimates are then aggregated into a total quantity for each of the activity’s resources. |
| A | Published estimating data | - This tool has the capability to help plan, organise, and manage resource pools and develop resource estimates. |
| B | Bottom-Up estimating | - This technique is often required to assess the resource-related inputs to this process. Any group or person specialised with knowledge in resource planning and estimating can provide such expertise. |
| C | Project management software | - These include using various levels of resource capability or skills, different, size or type of machines, different tools (hand versus automated), and make-or-buy regarding the resource. |

| - In identifying the critical path, the following parameters need to be determined for each task. Discuss each parameter. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Parameter | Discussion |
| ES | ES is an abbreviation for Earliest start time, meaning the earliest time at which the task can be started. Need to make sure any previous task that may need to be completed earlier to a new task being started. Example of this is cabinetry must be completed prior to the fit off stage starting. |
| EF | EF is an abbreviation for Earliest finish time. EF is calculated by adding the ES + task duration time. EF is an important calculation for tasks that have another task following, and cannot be started without a previous task being started. |
| LF | LF is an abbreviation for Latest finish time. This is the latest time that a task can be completed. LF is used for tasks that do not have a following task that relies on the completion of a job being finalised. |
| LS | LS is abbreviation Latest start time. This is calculated by subtracting the task duration from the latest finish time. Ls is used to determine the latest start time for finishing tasks. |

| - Which of the following statements accurately explain the process of developing the project schedule, including the schedule baseline? Select all that apply. |  |
| --- | --- |
| X | - Developing the schedule is the process of analysing activity sequences, durations, resource, requirements, and schedule constraints to create the project schedule. |
| X | - The project schedule and schedule baseline are developed or established using the activity lists, activity attributes, project scope statement as the bases. |
| X | - Entering the activities, durations, and resources into the scheduling tool generates the schedule baseline. |
|  | - Tools and techniques used in developing the project schedule and schedule baseline include decomposition of the total project work. |
|  | - Developing the schedule baseline starts and ends in the planning phase of the project. |

| - Schedule control is the process of monitoring the status of the project to update project progress and mange changes to the schedule baseline. Which of the following are processes that are involved in schedule control? Select all that apply. |  |
| --- | --- |
| X | - Determining the current status of the project schedule. |
|  | - Defining activities or specific actions to be performed to produce project deliverables |
| X | - Influencing the factors that create schedule changes |
|  | - Decomposing total project work into its lowest levels. |
| X | - Determining that the project schedule has changed |
|  | - Estimating duration and resource effort for the project. |
| X | - Managing the actual changes as they occur. |

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Gantt Chart. Do not exceed fifty (50) words. - List three (3) project data generated from the Gantt Chart. - List three (2) limitations of the Gantt Chart.

- Gantt chart is used to oversee all aspects of your project while also actively tracking your progress, along with each individual task within the project and in the order each task takes to complete. - 1- To show the overall progress of the project. 2- To show a start and end date of the project. 3- To show relationships between the tasks. - 1- The area of the Gantt chart can be often difficult to print. 2- The progress of each task is very subjective, so a project manager can be tempted to exaggerate the progress of a task to make the Gantt chart look better.

- Consider the methods used in project time management. - In your own words, discuss the application/use of the Critical Path Method. Do not exceed fifty (50) words. - List three (3) project data generated from the Critical Path Method. - Discuss the limitation of the Critical Path Method. Do not exceed fifty (50) words.

- The critical path method (CPM) is another method used by the project managers to indentify step by step activities on the critical path to completion. The CPM breaks the project into individual tasks, and then works out the duration time for each task to then produce a flow chart which then works out the length of the project. - 1- Parameters of each task : ES, EF, LS, LF. 2- Critical path 3- Critical elements within the project. - Limitation of the (CPM), the only real problem is that it only produces tasks on the critical path. At times during a project some tasks don't impact other tasks, so they're not required in the CPM.

| - The following are tools and techniques used in project scheduling. Match each tool and technique to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Project scheduling tools and techniques | Description |
| B | Schedule network analysis | - This is the process of looking at all of the activities that must be completed, and calculating the 'best line' – or critical path – to take so that you'll complete the project in the minimum amount of time. The method calculates the earliest and latest possible start and finish times for project activities, and it estimates the dependencies among them to create a schedule of critical activities and dates. |
| A | Critical Path Analysis | - This is a graphic representation of the project's activities, the time it takes to complete them, and the sequence in which they must be done. Project management software is typically used to create these analyses. Common formats for this include Gantt Charts and PERT Charts |
| D | Schedule compression | - They expedite the scheduling process by generating start and finish dates based on the inputs of activities, network diagrams, resources, and activity durations. |
| C | Automated scheduling tools | - This tool helps shorten the total duration of a project by decreasing the time allotted for certain activities. It's done so that you can meet time constraints, and still keep the original scope of the project. |

| - Which of the following statements accurately explain the work breakdown structure (WBS) including its application in project schedules? Select all that apply. |  |
| --- | --- |
| X | - Work breakdown structure (WBS) is the subdivision of project deliverables and project work into smaller, more manageable components. |
|  | - The work breakdown structure (WBS) identifies project personnel who are responsible for each project task. |
| X | - Work breakdown structure (WBS) helps define activities of the project which provide the basis for estimating, scheduling, executing, and monitoring and controlling the project work. |
|  | - The work breakdown structure (WBS) is used to represent the full project scope of the project. |
| X | - The work breakdown structure provides the relationships among all components of the project and the project deliverables. |
| X | - The work breakdown structure (WBS) is used as the basis for the scope baseline which is used in identifying activities or specific actions to be performed to produce of the project deliverables. |
|  | - Project work at lowest levels are not included in the work breakdown structure (WBS) |

Part 3 – Project Cost

| - The following are processes involved in project cost management including budgeting the cost of the project. In your own words, discuss each. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Estimating costs | Estimating costs is the process of developing an estimation of the financials to complete the project activities. The estimate is a prediction that can only be worked out on with the information given at this point in time. This estimate will cover all cost to complete the project which includes labour and materials. |
| Determine budget | Determining budget is the process of accumulating the estimated costs of activities or packages to create a cost baseline. To learn the budget you combine the "work breakdown structure" of the project and also the estimated costs. |
| Control cost | Control cost is the process watching the value spent in relation to the status of the project. During this process regular updating of the budget once the expenses are known. |

| - The following are different tools and techniques used in cost management. Match each to its correct description. Write the letters that correspond in the spaces provided. |  |  |
| --- | --- | --- |
|  | Strategy | Description |
| B | Analogous estimating | - This is used to establish both the contingency reserves and the management reserves for the project with regards to cost. |
| C | Parametric estimating | - This strategy uses the values of costings from a previous, similar project as the basis for estimating the same parameter or measure for a current project. This is used when the current project is similar to a previous one in terms of defined parameters. |
| E | Cost aggregation | - This uses a statistical relationship between historical data and other variables to calculate and estimate for cost. This technique is used to produce higher levels of accuracy depending upon the sophistication and underlying data built into the model. Estimates made through this project can be applied to the whole project or to segments of a project. |
| A | Reserve analysis | - These are used to develop mathematical models to predict total project costs. |
| D | Historical relationships | - Cost estimates are combined by work packages in accordance with the Work Breakdown Structure. The work package cost estimates are then combined for the higher component levels of the WBS and ultimately for the entire project. |
| G | Earned value management | - In this technique cost performance measurements are used to assess the magnitude of variation to the original cost baseline. |
| F | Variance analysis | - This is commonly used as a performance measurement. It integrates project scope, cost, and schedule measure to help the project management team asses and measure project performance and progress. |

- List four (4) processes which are followed in monitoring the project costs against outcomes to ensure that additional expenses are not incurred.

- Using an effective tool for managing the project finances ( like a spreadsheet or financial management software package). - Sending invoices on a regular(or monthly) basis. - Paying invoices promptly. - Checking incoming invoices against contracts, quotes, agreements, etc.

- You are appointed as one of the Project Managers of Bigger than Big Corporation. As one of the Project Managers, it is essential that you have a full understanding of the organisation’s policies and procedures relevant managing projects within Bigger than Big. Review Bigger than Big Corporation’s Project Management Policy and Procedures (username: cstclearner password: CstcPty@123). - In your own words, discuss the organisation’s Project Management Policy, including its background, purpose, and its scope. - In your own words, discuss the organisation’s Project Management Procedures including their purpose and scope. - In your own words, list and discuss the Project Phases prescribed in the organisation’s Project Management Procedures. Do not exceed 100 words for each discussion.

- Bigger than Big Corporation project management policy shapes the responsibilities and principles with the management of the Bigger Than Big projects. Bigger Than Big has a standard approach to project management that considers the mission and worth of the company to maximise project benefits and minimise risk. The policy sets up a company-wide approach which is managed through all stages including initiation, planning, implementation and closure of projects. Each project needs to be adapted separately as not all projects require the same levels of documentation, governance and reporting. Bigger Than Big Corporations project management procedure requires the processes and responsibilities required by management that is carried out throughout the life of the project. The procedure also requires all projects to follow the same project management methodology from start to finish of the end date. 1. Pre-initiate Phase - builds the foundation of a project and can often be activated when an independent sees when an issue may need to be resolved, or implement a new service. This phase also identifies what the project wants to achieve. 2. Initiate Phase - begins the procedure of determining how the project will be accomplished by putting together a detailed model of the work and confirmation of the in-principle funding decisions and project arrangements. 3. Plan Phase - provides more in depth detail about the project will be controlled. The crucial activity in this phase is budget, and detailed schedule information. 4. Implement Phase - determines how the project will be delivered through an implementation plan which can be made up of all the activities related to systems, staff, processes and training that must be completed to achieve project outputs. 4. Close Phase - is the formal closure of the project and handover to the operations department, also the evaluation of the success of the project is completed.

Part 4 – Project Quality

| - In your own words, discuss each of the following key concepts in Quality Management. Do not exceed 100 words for each discussion. |  |
| --- | --- |
| Key Concepts in Quality Management | Discussion |
| Customer satisfaction | Customer satisfaction is a measure of the quality of the project. If the project was completed to a very high standard and the customers' expectations were all met, the customer will hold the project in hi regard. Customers play an important role and are crucial in keeping a service relevant so it is in the best interest of the business to ensure customer satisfaction, which will be a key part to securing on going works. |
| Prevention over inspection | Prevention over inspection is a phrase used in project management that refers to the cost of quality (COQ). This includes extra money being spent during the project to prevent failures and mistakes. |
| Continuous improvement | Continuous improvement is the continuing effort to improve products, services, processes of a project. This procedure is in place to improve the results of final projects and to steer clear of repeating the same mistakes again. Learn and apply to future projects. |

- In your own words, discuss the difference between Quality Assurance and Quality Control. Do not exceed 100 words.

The difference between (QA) quality assurance and (QC) quality control is (QA) quality assurance shapes a standard and techniques which is put in place before producing the product which is done to prevent defects. (QC) quality control is the process of testing and detecting defects at the end of the product which are reported to management to make the decision to allow or reject the product release.

| - The following are standards that could apply in various projects. In your own words, discuss each standard. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| People standards | Are the requirement for the people who are working on the project. People standards include experience, qualification and correct licenses to complete the tasks that are given. |
| Process standards | Is the standard for the operation in delivering the project, which will involve quality assurance auditing. This procedure within the project can run smoothly. |
| Product / service standards | They are the standards that look at the end product, involving quality control standards. This quality is in place so all regulations and standards are being followed to the legislation. |

| - The following are quality assurance and control methods, techniques and tools. Match each to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Methods, tools, techniques | Description |
| H | Benchmarking standards | - This is a distribution of dots comparing two variables. If the two variables are completely independent you would expect the dots to be evenly distributed randomly across the graph. If there is a strong relationship though, the graph will show a straight line or a mathematical curve going through it. |
| G | Brainstorming sessions | - These are graphical representations showing a visual impression of the distribution of data. Usually it shows the frequency up the Y axis of the bar graph and the measuring variable along the X axis. |
| D | Control charts | - It is a graph where the X axis is time dependent. This allows you to look for time-based cycles in processes. |
| F | Flowcharts | - These are also known as Shewhart charts or process-behaviour charts. These charts are used to statistically measure the quality characteristics of a process are under control. This is based on a statistical analysis where a centre line is drawn for the mean of the output, then an upper control limit and a lower control limit is created either side of the centre line. The process is then measured over a period of time and the results plotted on the graph. Once the graph has been created, it can be analysed to test the stability of the process and also any cycles of errors. |
| B | Histograms | - It is very similar to a histogram, but it includes a line over the graph indicating the cumulative distribution of the results. |
| E | Pareto charts | - A diagram that represents a process. It shows the steps visually as a series of boxes with arrows in between them showing the work flow. Rectangular boxes represent tasks and diamond shaped boxes represent decision points, where the flow can split into two or more directions. |
| C | Run charts | - It occurs when a group meets and is presented with a scenario where they creatively come up with a range of solutions. |
| A | Scatter grams | - These may be dictated to by legislation through Federal, State or Local Government regulations, and may be dictated by industry bodies. |

- Determining the quality standards for the project deliverables. - Determining the quality standards for the project processes. - Documenting all the required standards in the project plan. - Ensuring all organisational quality requirements are met for the delivery of the project. - Conducting, or coordinating, project audits.

| - The following are methods used in managing continuous improvement. In your own words, discuss each method. Do not exceed fifty (50) words for each discussion. |  |
| --- | --- |
| Six Sigma | Six Sigma is a tool used to process to improve the quality of the output of a procedure by identifying and removing the causes of defects and changing any issues in the manufacturing and business processes. |
| Lean Six Sigma | Lean Six Sigma is an approach that requires a whole project team effort to improve to eliminate any excess waste within the project. This can be in the form of Time, excess waste, defects, processes and skills. "TIM WOODS" is abbreviated to eliminate the eight kinds of waste Time, Inventory, Motion, Waiting, Overproduction, Over-processing, Defects, and skills. |
| Total Quality Management | Total Quality Management is a extensive and organised approach to project management that is used to improve the products and services quality through constant feedback from your working team. |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You have already provided advice to Awesome Landscapes in the previous workbook. Today is 24 July 20xx. The project will shortly progress into the implementation stage. You have now been provided with up-to-date project documentation below, including an updated Project Plan. The project steering committee have reviewed the Project Plan, but they wish to have you conduct an independent evaluation of the project prior to signing it off. As part of your consultancy services, you will be assisting the team in addressing issues around project constraints by answering the questions that follow this scenario. The documents you need to complete the succeeding tasks can be accessed through the following links: Project Charter version 2 (.pdf) Project Plan version 2 (.pdf) Project Gantt Chart version 2 (.mpp) Project Gantt Chart version 2 (.pdf) Project Network Diagram version 2 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- List the three (3) project deliverables in Phase 1.

- Removal of vegetation in areas being cleared and replanting/ maintaining the plants for replanting in stage 3. - Access roads through the existing forest for builders to access each building site. - Retaining walls to provide stability around the buildings. Includes three additional retaining walls as per updated site plan.

| - Discuss the project constraints in terms of scope, time, cost, and quality. |  |
| --- | --- |
| Scope | The scope constraints are in the project plan in section 2. -Scope Management Plan. This includes 2.1 - deliverables, 2.2 - inclusions and 2.3 - exclusions which covers all three phases of the project. |
| Time | Time constraints are in project plan 3. Time Management Plan. Appendix 5; Task Dependency Worksheet has a column with all the required time constraints, but all work must be completed in nine months and in line with the building construction works and Gantt chart (Appendix 2) |
| Cost | The project budget of $550 000 + gst must include all economic resources needed to finish the project on time. |
| Quality | The council have very strict guidelines to meet so they must be followed. The natural environment is very sensitive and must be looked after. |

| - Review the project schedule as set out in the Project Plan and the Gantt Chart Arrange the following tasks in the proper sequence as dictated in Phase 3 of the critical path. Write 1 – 12 in the spaces provided; where 1 go first and 12 go last. |  |
| --- | --- |
| 8 | Remove weeds |
| 11 | Plant additional plants |
| 2 | Move gravel to car park |
| 1 | Expand car park |
| 12 | Remove greenhouses |
| 9 | Plant plants from greenhouses |
| 3 | Seal car park |
| 6 | Soil preparation |
| 7 | Add boulders |
| 5 | Construct stone paving pathway |
| 10 | Purchase additional plants |
| 4 | Landscape over old access roads |

- Review the Project Plan. The change request has outlined one change in the scope of the project. - What is the change in scope? - How does this change in scope impact the overall duration of the project? - How does this change in scope impact the quality aspect of the project?

- Three new retaining walls need to be included due to a change in the construction plan, requiring more chalets to be built. - There will no impact of the overall duration of the project as J.P Digging have changed their procurement plan for more funding to cover the extra work. - This shouldn't change the level of quality that's to delivered for the project. J.P Digging is providing extra resources and extra funds available in the contingency.

- Why does the change request only list one change in project cost, yet when you look at the financial tables the costs seem to have increased in numerous parts of the project not even related to the item in the change request? Do not exceed 100 words.

The increase is the overall cost that is calculated to cover all the individual costs which is covered within the financial table. The changes that occur has a flow on effect to individual tasks required to construct the retaining walls. The additional costing's for the project management and project support are there to cover the costs that are required to manage and implement the change process.

- Who is responsible for working out these impacts of what initially seemed to be such a simple change, and ensuring all affected stakeholders understand the impact of such a change?

Sam NG ( Project Manager - Awesome Landscapes) will negotiate with Susan Wills (Program Manager - Massive Eco Developments) the final details that are going in to the change request. Once everything has been finalised , Sam Ng will need to communicate all changes to the stakeholders.

- Access and review the Gantt Chart version 2. - What important tasks are not included in the project Gantt Chart? - Discuss why these tasks must be included in the Gantt Chart? Keep your discussion within 100 – 200 words in length.

- Quality assurance, council inspections, defect rectification, installation of utilities. - The quality assurance process should be included as it's a important part of the construction process and needs time spent on them. Lots of audits outlined in the quality management plan that will need to be reported on for the final hand over, but this hasn't been updated to the Gantt chart and could become a problem at the end of the project. Council inspections will be a problem if left out of the Gantt chart as they will have to booked before council come to site to complete inspections. If they are missed or unorganised this could fracture the relationship with the council. Defect rectification has not been allowed for in the Gantt chart. If there are issues that need rectification, time labor and funds need to be available. Site sewer utilities will be a major part of the project, timeframes to be added to Gantt chart for reference and allocation of excavation subcontractors. Awesome Landscapes are not responsible for installing under ground sewer utilities, but they are in charge of the excavation subcontractor digging them.

- List the three (3) personnel who signed off on the change request.

- Susan Wills - Program Manager , Massive Eco Development Corporation - Stephen Lyons - Planning Manager, Cascade Peaks Shire Council - Kim Nguyen - Director, Awesome Landscapes Pty Ltd

- What is the total increase in cost of the project as a result of this change request?

The total increase in cost of the project is $17,900 +GST. The original price was $444,253 +GST, but due to the change request the new price is $462,153 +GST.

- List five (5) exclusions under Stage 2 – Building Support of the Scope Management Plan.

- Monitoring and maintaining partially and fully constructed buildings. - Installations of utilities. - Installations of pipes and tanks. - Construction of septic systems buildings or other infrastructure - Provision or delivery of pipes and tanks.

- Review the Project Plan. Does it follow the change management procedure? Explain your reasoning. Do not exceed 50 words.

No, The project plan does not follow the change management procedure completely, The change request is completed in (appendix 38) but was not fully completed IE -stakeholders are yet to sign off the change request. the change register (appendix 37) is not up to date.

- Access and review the Gantt Chart version 2. It shows double bars for each task. - What do the coloured bars represent? - What do the grey bars represent? - Why do the grey and coloured bards do not match up in the Gantt chart?

- The coloured bars on top represent the project schedule. - The grey bar represents the project baseline, the project schedule determined at the start of the project. - The two bars don't match up as the project schedule has changed as a result of the change request.

- Assuming the project runs on schedule, list two (2) tasks that should be in progress if Sam was to visit the site on Monday 22 August. Do not include the task ‘Project Management’.

- Stage 1.1 - move plants to glasshouse and dispose - Stage 1.3 - Delivery of granite boulders

- If Sam was to visit the site on Thursday, 22 September, he will see that two (2) tasks are in progress, namely: - Construction of retaining walls. - Install and compact soil behind walls. According to the procedure documents, these two activities cannot happen at the same time. The retaining wall has to be built first. Once construction is completed, the soil needs to be added behind. Why are these two tasks in progress on the same day?

The two tasks are in progress on the same day as there are retaining walls at each chalet. This can orchestrated by back filling behind the first boulder while the construction of the second boulder wall on the retaining wall is being built. J.P Digging have allocated extra resources, so the two tasks above can be completed at the same time, by overlapping the two tasks. This will help with meeting the deadline for the project.

- According to the Gantt Chart, if there is a delay in the completion of Task 57 ‘Construct stone paving walkway’, - Which tasks, if any, are immediately delayed? - Will this delay push out the completion of the project? Why or why not? - Discuss how this could affect the resourcing of the project. - List one (1) risk that could arise from this issue.

- Tasks that are immediately delayed is Task 59 erect signs and Task 62 soil preparation. - Yes as Task 57 is on the critical path. - Resources committed to these tasks maybe allocated to various other tasks or other projects. A delay in these tasks may affect the ability to complete other scheduled tasks. - Resources including labour maybe committed to other projects and may not be able to complete the assigned tasks on this project for this reason.

- What is the total budget for the project expenditure?

The total budget expenditure is $462,153 +GST which includes change request 1.

- Sam is very concerned about the cash flow of the project. - What is the problem? - What would you suggest be done to rectify the cash flow issue?

- Awesome Landscapes could have a cash flow issue, potential to spend $244,724 prior to their first initial project payment to be cleared in the bank. The first payment is expected on October 1. As per appendix 8 of the project plan, the adding expenses will be $248,671. This leaves Awesome Landscapes with a cash flow problem of -$23,947. - I'd suggest a change to be made in the payment dates. Payment 1 and 2 are very close together. By requesting to move payment 1 forward this will remove cash flow issues for the project.

- Discuss whether Awesome Landscapes should seek increased funding from Massive Eco-development Corporation to absorb some or all of these cost increases. Your discussion must be 200 – 300 words in length. Guidance: The change requests have incurred extra expense, yet the funding to be paid by Massive Eco-development Corporation has not changed. If you believe Awesome Landscapes should seek increase funding from Massive Eco-development Corporation, provide a strong argument for your case. If not, explain your reasoning.

I believe that Awesome Landscapes should seek extra funding to be paid by Massive Eco - development corporation. For the purpose of the project Sam Ng should be requesting a relaxation on the initial release of funds to cover the extra construction costs. Although the section 4.5 of the project plan states that "this is a fixed price contract so the funds provided shall be the same regardless of any project extensions, variations in scope, or increase of labor cost, procurement or purchases". That said, Awesome Landscapes and Massive Eco -Developments corporation will want to continue a strong relationship with hope of working relationship in the future. Massive Eco Developments Corporation will need to do some research on its contractor to see if those costs will affect them. Can they finish the job?, can the company continue to operate?. Massive Eco development need to take in consideration when making a decision, that it's a variation to the original scope of works ,which was outlined in the project plan, due to the construction of the extra chalets and to keep the project on the timeframe. Overall if Awesome Landscapes were able to apply for funds to be released early to help with the variation, it will be beneficial to the completion of the project.

- Complete the following Audit Template with the standards determined in the previous question (Case Study Question 18). This will be given to an internal auditor to audit the financial processes at various points along the project. Guidance: Complete only the fields highlighted in yellow. Do not complete the ‘Assessment’ and ‘Comment’ fields under ‘Audit of Management of Project’.

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Paul Reyne |  |  |  |  |  |  |  |  |
| Date: |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: | Overall Project Status: |  |  |  |  |  |  |  |
| Audit Date: | Audit Number: |  | Audit Leader: |  |  |  |  |  |
| Audit Team: |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To evaluate the financial process at various points of the project |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Payment calendar or schedule, are payments on time?. |  | Assessment: | Comment: |  |  |  |  |  |
| 2. invoices being paid on time? |  | Assessment: | Comment: |  |  |  |  |  |
| 3. Staff/wage budgets been allowed for due to change? |  | Assessment: | Comment: |  |  |  |  |  |
| 4. Invoices sent out on time? |  | Assessment: | Comment: |  |  |  |  |  |
| 5. Financial reporting been completed on time? |  | Assessment: | Comment: |  |  |  |  |  |
| 6. Invoices been checked against original quotes? |  | Assessment: | Comment: |  |  |  |  |  |
| 7. Have cash flow deficit problems been identified and adjusted to the change in scope? |  | Assessment: | Comment: |  |  |  |  |  |
| 8. Have all obtainment and expenditure costs as per quoted figures in provided quotes been updated due to the change in scope? |  | Assessment: | Comment: |  |  |  |  |  |
| 9. Have all financial changes been reported and approved correctly the required stakeholders? |  | Assessment: | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes |  | no |  |
| Name(s) of attachment(s): 1. 2. |  |  |  |  |  |  |  |  |
| Audit Report Submitted To: |  |  |  | Date: |  |  |  |  |

- Sam has provided you with the following audit from a previous project (landscaping the new Cascade Peak Shopping Centre). Evaluate the audit report below and answer the following questions: - What was the cause of the unsatisfactory results? - What action would you recommend to prevent the issue coming up again in this project?

- As stated in the overall assessment section, it states that tasks being communicated by the supervisor do not have the level of detail required by the site supervisor. Detailed plans are not provided with the task briefs. Some delays in commencing tasks have been experienced as the site supervisor has awaited clarification from the project manager. - Sam Ng is to prepare task briefs in enough time to add the required level of detail and are to be supplied with all relevant attachments, such as detailed plans. Sam Ng could make sure all supervisors have the required information by having weekly face to face meetings.

| Quality Audit Template |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |
| Prepared by: Sam Ng |  |  |  |  |  |  |  |  |
| Date: 17 August 2015 |  |  |  |  |  |  |  |  |
| Project Manager: Sam Ng, Awesome Landscapes |  |  |  |  |  |  |  |  |
| Project Phase: Implementation | Overall Project Status: On schedule |  |  |  |  |  |  |  |
| Audit Date: 17 August 2011 | Audit Number: 26 |  | Audit Leader: Sam Ng |  |  |  |  |  |
| Audit Team: Sam Ng, John Cowley, Ann Deak. |  |  |  |  |  |  |  |  |
| Goal(s) of This Specific Audit: To evaluate the communication and reporting processes. |  |  |  |  |  |  |  |  |
| Audit of Management of Project: |  |  |  |  |  |  |  |  |
| 1. Are tasks being communicated to site supervisor in a reasonable amount of time? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| 2. Are tasks being communicated to site supervisor of sufficient detail? |  | Assessment: Not satisfactory. | Comment: Tasks only being communicated as per Gantt chart. Site supervisor having to seek clarification regularly on requirements of tasks. |  |  |  |  |  |
| 3. Are tasks being communicated by the site supervisor to the team members and contractors done in a reasonable amount of time? |  | Assessment: Not satisfactory. | Comment: Timing of communication can be improved if there wasn’t the need for clarification of the details of the tasks. |  |  |  |  |  |
| 4. Are tasks being communicated by the site supervisor to the team members and contractors of sufficient detail? |  | Assessment: Satisfactory. | Comment: |  |  |  |  |  |
| Overall Assessment of Management of Project: Tasks being communicated to the supervisor do not have the level of detail required by the site supervisor. In particular detailed plans are not provided with the task briefs. Some delays in commencing tasks have been experienced as the site supervisor has awaited clarification from the project manager. |  |  |  |  |  |  |  |  |
| Recommended Action(s)/Lessons Learned Regarding Management of the Project: 1. Project manager to prepare task briefs in enough time to add the required level of detail. 2. Task briefs are to be supplied with all relevant attachments such as detailed plans. |  |  |  |  |  |  |  |  |
| Additional Audit Comments: 1. 2. 3. |  |  |  |  |  |  |  |  |
| Have you attached additional material(s)? |  |  |  |  |  | yes | x | no |  |
| Audit Report Submitted To: Kim Nguyen |  |  |  | Date: 24/08/2015 |  |  |  |  |

- The quality plan is very weak on cost management. Write a Cost Management Plan (of 200 – 300 words) for managing the quality of the financial processes while the project is in progress. Guidance: Your Cost Management Plan must cover the following quality objectives and criteria. - Meeting with contractual requirements. - Paying invoices on time. - Ensure invoices are sent out in time. - Ensuring financial reporting is done on time. - a calendar of when payments are likely to be due. - Comparison of actual cash flow against projected cash flow.

a. Meeting with contractual requirements Massive Eco - Development Corporation is paying a fixed sum of $550,000. The project budget as per this project plan is $462,153. This amount covers all of the required tasks set out in the project plan to deliver phase 1 to phase 3 of the Cascade Peaks Chalets Landscaping Project. Awesome Landscapes management must observe the progress and project milestones that are outlined in Clause 3.2 as the project, and communicate these key dates to all staff, as there is no allowance for variance in these dates. Invoicing b. Paying invoices on time. The contract Administrator is accountable for advising the project manager and payroll officer of invoices to pay. The contract administrator is to create a spreadsheet (easy to use ) that has recieval date and a payment date to make sure all invoices are paid on time to avoid any loss in productivity. Raising Invoices and cash flow Awesome Landscaping will raise an invoice on the first working day, following the due date of each progress payment. The terms of all invoices are 28 days from date of the invoice. All cash flow calculations are based on the funds being paid on the final day of the terms of the invoices. The project manager is responsible that all invoices are sent out on time to avoid delays in payment and assist with any cash flow deficit problems. The funding payments from Massive Eco- Development Corporation are to be due as follows and adhered to in order to control cash flow deficit : Phase of the project:; Expected payment date:; Payment; Proportion; Amount (pre-GST); Amount (GST incl.). Commencement of Phase 1; 1 October 2016; Payment 1; 50%; $275,000; $302,500. Completion of phase 1; 1 October 2016; Payment 2; 20%; $110,000; $121,000. Completion of phase 2; 1 February 2017; Payment 3; 20%; $110,000; $121,000. Completion of phase 3; 1 April 2017; Payment 4; 10%; $55,000; $60,500. TOTAL; 100%; $550,000; $605,000.

Financial Reporting

A financial report must be completed, monthly by Awesome Landscapes management, or immediately after a change request has been completed.

If a month passes following a change request or a previous report, another report will need to be completed. The report must be documented in the project plan and status reports, which will be communicated to Awesome Landscapes senior management with reasoning for any difference along with a rectification process.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Part 1 – Project Scope Part 2 – Project Time Part 3 – Project Cost Part 4 – Project Quality Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document