Assessment Workbook 5

BSB51415 Diploma

of Project Management

Integration Management

Version 1.01 Produced 18 October 2018

Copyright © 2021 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following assessment validation. | 1.0 |
| 18 October 2018 | Version 1.01 Change to Practical Assessment | 1.01 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Case Study	5

Instructions to Student	5

Introduction	6

Workbook Checklist	17

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 5 |  |  |
| --- | --- | --- | --- |
| TITLE: | Integration Management |  |  |
| FIRST AND SURNAME: | Rue Grimston |  |  |
| PHONE: | 0427 576 893 |  |  |
| EMAIL: | rue.grimston@seymourwhyte.com.au |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Rue Grimston |  | Signature: | Date: 07/03/2021 |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant advisor to the project team at Awesome Landscapes Pty Ltd. Specifically you are required to provide independent advice on seeing their current project through the entire life cycle. You have already provided advice to them in the previous four workbooks. The project manager has advised the project is now complete, and is about to archive all the project documentation. Your task is to evaluate the supplied project documentation and to ensure all due diligence has been completed. You will need to compare the project plan with the previous version to ensure it is ready for closure. Project Charter version 4 (.pdf) Project Plan version 4 (.pdf) Project Gantt Chart version 4 (.mpp) Project Gantt Chart version 4 (.pdf) Project Network Diagram version 4 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- Sam has asked to you check the Project Plan for anything that is missing. He has been very busy but appears to have done all the necessary finalisation of the plan ready for sign off. He has mentioned the final report or lessons learnt documentation has not been included, and the project archiving checklist have not been completed either. You will be assigned to complete these later. Examine the Project Charter (version 4) and Project Plan (version 4) and identify four (4) things that are missing. Guidance: - Assume the Project Gantt Chart and the financial figures in the summary/detailed costing tables are up to date as these have already been audited. Also remember this final project plan is in draft, and will not be signed off until the final acceptance meeting in a few days’ time. - Take note of the following: - Version control. - The updates from the project in the other workbooks you have completed in previous workbooks. - Check the project archiving checklist for everything that should be included

- Change request 3 - comments have not been added to the Project Charter - Change Request 3 - details of the new contractor and landscapers are not highlighted in the Project Plan - Change Request 3 - no evidence of risk management plan been updated in the Project Plan - While schedule is included in the project plan, there appears to be now schedule management plan included.

- Sam is in the process of developing a set of Lessons Learnt Documentation for the project. - Access and review the four (4) previous workbooks you have completed and derive three (3) different lessons learnt throughout the project. - Document each lessons learnt using the Lessons Learnt Documentation Template provided. Use one template for each lessons learnt.

| Lessons Learnt Documentation Template 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Rue Grimston |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 19/04/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 03 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Project Cost and Time |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Steering Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Cost and Time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Additional works (cost) but there was no negotiation of time or money |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | The additional duration of days has increased in Phase relating to project management, project support stff and project meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Review of Time when there was a change to scope |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Discussion around addition work to increase timeframe. Review of Gantt Chart |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The maturity of the team may need to reviewed prior to commencement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guidance and addition review of project prior to commencement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| This could be used on future projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Rue Grimston |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 19/04/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 02 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Delay in Task 57 - Construct stone paving walkway |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Project Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Time Management and Resources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Increase resourcing and cost to construct stone paving walkway on time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Delay to completion date |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Daily inspection of tasks ensure that delivery is on time |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | No over run into the continguency |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Daily and weekly reviews of task ensure project team are delivering ontime |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Add additional progress meetings to the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| More experienced team guiding the project team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of contractors and evaluation of risk outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets Landscaping Project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Rue Grimston |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 15/12/2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 01 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Abondoned project to recommence 7 January 2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Evaluate process |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Recurit two replacment landscapers Tender for replacment digging Contractors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Abandonment of project has cost interms of retaining staff and is likely to incur extra costs with repairing damaged work , and in recruiting two replacment contractors and the replacment digging contractor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Massive Eco-Development Corporation to complet contract prior to going into liquidation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | REview/ Audit of Massive Eco-Development Corporation finaces prior and during construction, and evaluate prayment schedule to ensure process payments will meet deliverables |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review payment schedule Evaluate contractors abiltiy to meet contract requirments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compete pre contract evaluation of contractor prior to executing a contract |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organisation Culture, Past History |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review of contractors and evaluation of risk outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Sam has asked you to write the final report for the project. Complete the final report using the template below, assuming the things missing from the project plan in the question above have been included. Guidance: - Access and carefully review the project documentation you were provided with along with the case study scenario and populate all the fields with the required information. - Provide a date that is later than the last date in the Project Gantt Chart version 4. - Assume that this report will be submitted to Terrence Mackay, Stephen Lyons, Kate Chan, and Kim Nguyen. - Provide a brief summary of the project in terms of the four project constraints (Scope, Cost, Time, and Quality). - Provide a detailed summary of the project covering the functions of project management listed below. Further guidance is provided for you within the template.

| Project Name: | Cascade Peak Chalets Landscaping Project |  |  |
| --- | --- | --- | --- |
| Prepared by: | Rue Grimston |  |  |
| Date: | 28/04/2017 |  |  |
| Project Summary |  |  |  |
| Scope (What was included and excluded) |  |  |  |
| Inclusions: The project inclusions for each deliverable include: Stage 1 – Pre-building •Removal of vegetation in areas being cleared and replanting/maintaining the plants for replanting in stage 3. o Supply and delivery of all vegetation removal equipment and tools. o Supply and erection of covered building to store and grow native plants collected from areas being cleared. o Irrigation, potting and chemicals for maintenance of plants. o Separation and disposal of weeds from native plants. o Ensuring the ongoing health of large plants and trees left in the ground. Access roads through the existing forest for builders to access each building site. o Supply and delivery of all excavation equipment and vehicles. o Removal of soil and storage in designated location on site for use for landscaping. o Supply and laying of road gravel along temporary access roads. o Building an unsealed car park at the front entrance. •Retaining walls to provide stability around the buildings. o Supply and delivery of granite boulders and all other raw materials used for retaining walls. o Construction of retaining walls. o Insertion of soil into retaining wall areas from excavations. o Compacting of soil behind retaining walls as required for foundation work. Stage 2 – Building Support •Monitoring the building site for erosion, subsidence or other environmental issues. o Managing any erosion or subsidence in the land where chalets are being built. o Maintaining the road access to the chalets. o Monitoring trees and other vegetation not removed. •Excavation for incoming utilities (electric cable, water supply, etc.). o Digging channels as per plans and installer requirements. o Filling in and compacting channels once utilities installed. o Ensuring surface infrastructure for utilities remain clear and uncovered. •Excavation of sewerage and septic system. o Excavation of holes for septic tanks. o Excavation of channels for sewerage pipes. o Filling in and compacting channels and holes once sewerage and septic system has been installed. o Ensuring surface infrastructure for sewerage and septic systems remain clear and uncovered. •Maintaining the plants removed in stage 1. o Supply of all chemicals and equipment needed to maintain the plants. o All maintenance of the green houses. o Maintenance of all plants. o Removing weeds and pests as required. •Repair of slip damage. Stage 3 – Planting and Landscaping •Diversion of stream and creation of water channels through resort in between the chalets. o Construction of stream channels as per plan. o Supply and delivery of granite boulders for landscaping and ground stability around the stream channels. o Excavation of channels diverting water from main stream. Construction of weir system used to divert water. o Construction of drainage system to return water to main stream downstream from chalets. o Testing and troubleshooting. •Conversion of most access roads into landscaped walking paths. o Expansion of car park along main road. o Removal of access road gravel and laying over car park. o Sealing of car park over gravel. o Restoration of soil around old access roads. o Construction of stone paved walking paths between chalets as per plan. o Compacting and ensuring no erosion or subsidence risk. •Erection of signage around resort. o Erecting signs provided by marketing project. o Concreting and additional landscaping around signs. •Detailed landscaping around chalets and paths. o Soil surface preparation. o Additional boulders placed in landscaping. o Removal of all weeds in resort. •Planting of native plants removed in stage 1 plus additional native plants back into landscaped areas to blend in with forest. o Planting of all healthy native plants removed in stage 1. o Purchasing and delivery of additional native plants to fill the gaps. o Planting additional plants. |  |  |  |
| Exclusions Stage 1 – Pre-building •Removal of vegetation in areas being cleared and replanting/maintaining the plants for replanting in stage 3. o Sourcing and maintenance of any additional native plants to be planted at the end of the project. o Removal of trees (these will remain in the ground, and buildings will be erected around them). o Planting of new trees. •Access roads through the existing forest for builders to access each building site. o Sealing of roads or car park. o Maintenance of main road up the mountain to the resort property. o Construction of any foot path Construction of any bridges, culverts. o Construction of any electrical services (e.g. street lighting, power access to chalet sites, etc.). •Retaining walls to provide stability around the buildings. o Construction of foundations. o Planting around retaining walls. Stage 2 – Building Support •Monitoring the building site for erosion, subsidence or other environmental issues. o Monitoring and maintaining partially and fully constructed buildings. o Monitoring and maintaining the main road. o Creation of additional retaining walls. o Onsite security (this is provided by the chalet development project). o Any building, decorating or furnishing of the chalets. •Excavation for incoming utilities (electric cable, water supply, etc.). o Installation of utilities. o Installation of service points at either road or chalet end. o Provision or delivery of utility raw materials or installation equipment. o Testing of the utilities (this will be done by the building contractors when the cables and pipes have been laid, but before they are buried. o Weather damage. •Excavation of sewerage and septic system. o Installation of pipes and tanks. o Construction of septic system buildings or other infrastructure. o Provision or delivery of pipes and tanks. •Maintaining the plants removed in stage 1. o Purchase and maintenance of additional native plants to replace any that had perished. o Removal of additional plants or weeds from the building sites. Stage 3 – Planting and Landscaping •Diversion of stream and creation of water channels through resort in between the chalets. o Nil •Conversion of most access roads into landscaped walking paths. o Construction of any roads within the resort. o Construction of any hand rails (this will be done by builders in the chalet development project once we have finished developing the paths. •Erection of signage around resort. o Sign design or sign writing. •Detailed landscaping around chalets and paths. o Any pot plants to go around or inside chalets. o Development of any ongoing maintenance plan. Planting of native plants removed in stage 1 plus additional native plants back into landscaped areas to blend in with forest. o Purchase, delivery of planting of any exotic species. o Development of any plant maintenance plan. |  |  |  |
| Cost (Budget vs. actual) |  |  |  |
| $514,892 vs $650,000 |  |  |  |
| Time (Estimate vs. Actual) |  |  |  |
| Initial estimate was 9 months from the 2nd April 2016, actual was the 12th April 2017, twelve month duration |  |  |  |
| Project Report Submitted to: |  |  |  |
| Name: Terrence Mackay |  | Title: General Manager | Date: |
| Name: Stephen Lyons |  | Title: Planning Manager | Date: |
| Name: Kate Chan |  | Title: Project Manager | Date: |
| Name: Kim Nguyen |  | Title: Director | Date: |
| Analysis of Project Guidance: - Process Review - Describe all of the processes used during the planning, implementation and closure stages. - Lessons Learnt - Describe what went right and or what went wrong and how effective were the management and the processes you used. If necessary, state how you overcame any problems. - Recommendations – Make recommendations as a result of the lessons learned. |  |  |  |
| Scope |  |  |  |
| Process Review PMBOK project management methodogy was used for this project, with adherence to AS/NZS ISO 31000 2009 standard |  |  |  |
| Lessons Learnt Change to scope of project. If the scope was clearly documented then you can use that as a solid base for renegotiating of the project e.g. additional retaining walls, fixed price contract with no scope for variations |  |  |  |
| Recommendations Clearly define inclusion and exclusion into the project scope. |  |  |  |
| Time |  |  |  |
| Process Review WBS, Gantt Chart Network Diagram, Effort and Duration of Task (three-point estimating), Task Dependency Worksheet |  |  |  |
| Lessons Learnt Executing - By procuring a new contractor to complete excavation works, incurred delays to the completion of works from 9 months to 12 months |  |  |  |
| Recommendations As this was a new project team, it might be worth considering using the expert judgement estimating in conjunction with the three-point estimating. |  |  |  |
| Cost |  |  |  |
| Process Review Estimating methodogy of all procurement and expenditure costs |  |  |  |
| Lessons Learnt No variation fixed contract was accepted by Awesome Landscaping. Planning - if there was a comprehensive financial review conducted on JP Digging there would have been an understanding of their current financial situation |  |  |  |
| Recommendations Clearly define inclusion and exclusion into the project scope and understanding what variations are inclusive and exclusive. |  |  |  |
| Quality |  |  |  |
| Process Review Project / service standards |  |  |  |
| Lessons Learnt |  |  |  |
| Recommendations There did not appear to be issue with the quality of the project, as non add been documented throughou the life of the project |  |  |  |
| Human Resources |  |  |  |
| Process Review Analyse of the WBS to determine skills needed to perform the tasks |  |  |  |
| Lessons Learnt Loss of knowledge due to resignation of a landscaper and site supervisor, resulting in lower quality work requiring rework and/or purchase of additiona plants towards the end of the project |  |  |  |
| Recommendations Hire long term landscaping employees into project Ensure landscaping employees are happy to be based up the mountain for long periods of time Ensure morale remains high throughout the project Give the employees a sens of ownership in the work they are doing |  |  |  |
| Communications |  |  |  |
| Process Review Communication Plan was delivered identifying key stakeholders, issues, communication methods for the project which included Management of Change. |  |  |  |
| Lessons Learnt |  |  |  |
| Recommendations Communication Management Plan meet the projects requirment |  |  |  |
| Procurement |  |  |  |
| Process Review Conduct procurement |  |  |  |
| Lessons Learnt Change in scope by the construction company and Massive Eco-development |  |  |  |
| Recommendations Change to start date of the project brought back one week. No other project timeframes have changed |  |  |  |
| Risk |  |  |  |
| Process Review PMBOK project management methodogy was used for this project, with adherence to AS/NZS ISO 31000 2009 standard |  |  |  |
| Lessons Learnt New sponsor and temporary abandonment of the project prompted a full risk review and updating of risk and issues register |  |  |  |
| Recommendations Risk review conducted. Additional risk identified and documented. All updated risk documentation added to project plan |  |  |  |
| Project Integration |  |  |  |
| Process Review Collective of scope, change, quality, time, cost, human resources |  |  |  |
| Lessons Learnt The was change to both scope and time within the project which affected the overall cost of the project |  |  |  |
| Recommendations Ensure all previous (above) mentioned factors are considered and reviewed and incorporated into the contract for future projects. |  |  |  |

- Sam has approved the report in the above question to be distributed. He has also updated the project plan following your advice. Now he is ready for the project closure meeting. He has assigned you the task of organising this meeting. Answer the questions that follow.

- Who will attend this meeting? Guidance: List the attendees by name, job title, and organisation).

Terrence Mackay - General Manager - Cascade Peak Hotel Kim Nguyen - Director - Awesome Landscape Pty Ltd Sam Ng - Project Manager - Awesome Landscape Pty Ltd Stephen Lyons - Planning Manager - Cascade Peak Shire Council Kate Chan - Project Manager - Timber Home Construction Ltd

- What information will each person need before the meeting?

Project completion report Final version of the project plan Project archives chekclist Formal acceptance and closure

- Which documents (and which version number of each document) will need to be printed off for the meeting?

Project Completion report - Version 1 Project Plan - Version 4 Project archives checklist - Version 1

- Which of these documents will require signatures?

The completion report, project plan and formal acceptance and closure must all be signed off by the sinatories of the project steering committee

- Who will need to sign off on these documents?

The completion report, project plan and formal acceptance and closure must all be signed off by the sinatories of the project steering committee

- Do you believe the project objectives aligned with the objectives of Awesome Landscapes throughout the entire project life cycle? Explain your answer.

Due to the broadness of the key objectives, it is the belief the objectives aligned with Awesome Landscapes throughout the entire project life.

- What needs to be done after the meeting to complete the closure of the project?

Raise an invoice for the final contract payment. Upon payment of the final contract payment all project documentation may be archived

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document