## Risk Data Import Sheet
|  | ECI WWMP NP2 RAMP Risk Register (Risk of cost changes that would not be contemplated as Scope Changes) | [14 empty] | #VALUE! | #VALUE! | [10 empty] | #REF! | #REF! | #REF! |  | #REF! | [22 empty] | 30.05
[8 empty] | INITIAL ASSESSMENT |  |  |  | PROPOSED TREATMENT | RESIDUAL ASSESSMENT |  |  |  | POTENTIAL IMPACT |  |  | ACTION |  | STATUS | COMMENTS |  | #REF! |  |  | MONTE CARLO | [9 empty] | #NAME? | [11 empty] | 0% |  |  |  |  | 412410.4222
| HDD-MT | Risk ID | Project | Description of Risk | Causes | Impacts (Consider the Benefits Case) | Comments | Likelihood | Consequence | Risk Score | Risk Rating | Proposed Treatments | Likelihood | Consequence | Risk Score | Risk Rating | Schedule | Critical | Cost | Owner | Response | Case Status | Comments |  |  | Direct Costs | Comments | Probability | Worst Case | Worst Case Comments | Most Likely | Most Likely Comments | Best Case | Best Case Comments | Result | Occurs | Risk | Result | Owner | Responsible | Status |  | Sub-Contractor Costs | Labour Costs | Design Costs | Project Management Costs | Plant & Equipment Costs | PMO Costs | Schedule Impact | Mark-up | Total | Worst Case Factor | Best Case Factor | Average | SumProduct
1 | HDD-MT | A01 | Jindalee SRM-19 Upgrade | Underground services where open cut / tunnelling is planned | No DBYD undertaken. No consideration of the power cable in the design. | Service disruption. Lost construction time. |  | Possible | Major | 6 | High | Early DBYD information acquired. Design incorporates the Energex cable location. | Unlikely | Minor | 3 | Low | 4 | Yes |  | FH | Mitigate | Closed |  | SCG | 0 | Yes | Unknown Services - defintion possibly SCG. Latent Conditions risks cannot be quanitified. Latent conditions are physical conditions on, underlying or adjacent to the site that could not be identified by the contractor by reasonable observations or investigations of the site or the site information provided in the Work Package Brief at the time that the RAMP for the Project was being prepared. |  | 0 |  | 0 |  | 0 | [7 empty] | complete | RSK - A01 | [7 empty] | 0 | 0 | 1.5 | 0.5 | 0 | 0
1 |  | A02 | Jindalee SRM-19 Upgrade | Staging of works may not align with DTMR road expansion works | No consultation with services providers. No cost sharing arrangement discussed. | Re-relocating of services |  | Possible | Major | 6 | High | Early consultation with service providers to determine likelihood. Presently in talks with DTMR. | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Accept | Closed | Through risk assessment to capture all possible issues with treatment actions. Currently being actively managed with DTMR. | SCG | 0 |  |  |  | 0 |  | 0 |  | 0 | [7 empty] | Complete | RSK - A02 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A03 | Jindalee SRM-19 Upgrade | DTMR conditions for approvals. Construction in road corridor | No consultation with stakeholders. In adequate Traffic Management Plan. | Delays in project, increased cost, increase in consultants scope. |  | Possible | Moderate | 5 | Medium | Ensure all stakeholders are consulted and their concerns appropriately dealt with. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Transfer | Closed |  | SCG | 0 | No | Transfer to UU, SCG/risk for alignment within DTMR Corrdior at Sinamon road Project Change is an alteration to time, scope and/or cost due to stakeholder needs. |  | 0 |  | 0 |  | 0 | [7 empty] | Complete | RSK - A03 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A04 | Jindalee SRM-19 Upgrade | Contamination of the existing site. | No search undertaken of possible site issues. STEP to identify potential sites. Residual risk for areas not tested. | Delays in project. Assessment, quantification and remediation as a variation to project. |  | Likely | Minor | 5 | Medium | Identify site contamination issues, during the STEP process and develop an action plan. Incorporate the assessment into the Project Plan. | Possible | Minor | 4 | Medium |  |  |  | FH | Avoid | Open | Testing complete and awaiting results. Residual risk for areas not tested. Testing required for HDD works |  | 17947.5 | No |  | 30% | 89737.5 | Residual risk for areas not tested, and subsequently prove to be contimanted, 1,260 Meters x depth x width (m3) x bulking x $150 a Tn | 59825 | 1260 linear meters, 1 wide, 1.5 deep, x bulking factor x $150 a TN x 10% (area) | 29912.5 | 1260 linear meters, 1 wide, 1.5 deep, x bulking factor x $150 a TN x 5% (area) | #NAME? | #NAME? | #NAME? | #NAME? |  |  | Complete | RSK - A04 | 56700 |  |  |  | 3125 |  |  | 0 | 59825 | 1.5 | 0.5 | 59825 | 17947.5
1 |  | A05 | Jindalee SRM-19 Upgrade | Cultural heritage issues. | No cultural heritage search. No planning. | Delays to project. Possible variations required for additional studies and consultation. |  | Possible | Minor | 4 | Medium | Undertake cultural heritage search as part of the STEP assessment. Appropriate consultation, action plans and cultural heritage management plans if required. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Nothing identified in the STEP. Residual risk, to be identified in CWMS and mitigated during construction. | SCG | 0 | No |  |  | 0 | Residual risk for cultural heritage (hard to quntify delays) SCG | 0 |  | 0 | [7 empty] | Complete | RSK - A05 | [5 empty] | 0 |  | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A06 | Jindalee SRM-19 Upgrade | Acid sulphate soil. | No acid sulphate soil testing, cross contimate with drilling fluids. This risk is purely ASS related | Delays to project. Possible variations required for additional studies and ASS disposal. |  | Possible | Moderate | 5 | Medium | Undertake ASS testing. If found develop appropriate treatment strategies. | Unlikely | Moderate | 4 | Medium | 3 |  |  | FH | Monitor | Open | Any change in scope will need appropriate funding for implementation. Pending review of contaminated land results. |  | #REF! | No |  | 50% | #REF! | Refer A04 - Cross contimate with drilling fluids. This risk is purely ASS. Additional cost for reworks, replacement of subgrade works, disposal, treatment works = worst case assumes 100% imported fill. Delay to HDD works, pending on date of known occurrence | #REF! | Additional cost for reworks, replacement of subgrade works, disposal, treatment works = worst case assumes 100% imported fill. Delay to HDD works, pending on date of known occurrence | #REF! | Additional cost for reworks, replacement of subgrade works, disposal, treatment works = worst case assumes 100% imported fill. Delay to HDD works, pending on date of known occurrence | #NAME? | #NAME? | #NAME? | #NAME? |  |  | Complete | RSK - A06 |  | #REF! |  |  |  |  | 3 | #REF! | #REF! | 2 | 0.5
1 | HDD-MT | A07 | Jindalee SRM-19 Upgrade | Flooding of work site | Construction works in flood zone. Wet Historic flood map, all 3 sites 5m underwater (2011 flood) | Equipment damaged due to flood waters. Delay to project. |  | Possible | Major | 6 | High | Environmental Controls & ground water management in place, pumps if required | Possible | Minor | 4 | Medium | 13 |  |  | FH | Mitigate | Open | Contractors works insurance ? Excess to be confirmed $100k P&E, $300k PI Keep key equipment clear of flood levels, where possible Risk ID A100 Brisbane flood map, flood risk & level. Risk of being within work zone during the flood event. |  | 20736 | No | Contracts works insurance? Insurance claims | 12% | 293760 | Allowance for the costs of construction of temporary works to take into account flood heights or the cost of delays arising from flooding. (20 days) Replacement of washed out materials, shoring, pipe, sanitation etc. | 172800 | Non claimable event under insurances excess - 5 days for clean up and access road. Replacement of washed out materials, shoring, pipe, sanitation etc. | 86400 | Allowance for 8 days | #NAME? | #NAME? | #NAME? | #NAME? |  |  | Complete | RSK - A07 | 8800 | 14000 |  | 60000 | 90000 |  |  | 0 | 172800 | 1.7 | 0.5 | 184320 | 22118.4
1 |  | A08 | Jindalee SRM-19 Upgrade | Flora and fauna issues. | No search undertaken of possible flora and fauna issues. | Delays to project. Possible variations required for additional studies and consultation. |  | Unlikely | Minor | 3 | Low | Identify flora and fauna key issues during the planning phase. Develop action plan to address the issues identified. Incorporate the assessment into the REF. | Rare | Minor | 2 | Low | 10 |  |  | FH | Avoid | Open | Any possible need for land resumptions will be identified early in the project to ensure the required funding is approved with the initial request. Ecology report complete - water dragon bredding areas / significant trees - NALL approval required. Engage accredited contractor and engage Level 5 Arborist Delineate/create exclusion zone for significant trees Do not clear outside of ROW Develop SWMS |  | 6000 | No |  | 30% | 30000 | Changes to the design/report, the residual risk is changes to alignment Allowance for 20 days flora and fauna spotters, plus delination fencing | 20000 | Allowance for 10 days flora and fauna spotters, risk on additonal tree removal costs. | 10000 | Allowance for 3 days flora and fauna spotters | #NAME? | #NAME? | #NAME? | #NAME? |  |  | Complete | RSK - A08 | 20000 |  |  |  | 0 | 0 | 10 | 0 | 20000 | 1.5 | 0.5 | 20000 | 6000
1 | HDD-MT | A09 | Jindalee SRM-19 Upgrade | Elevated construction costs due to urgent nature - Design | Urgent nature of the procurement and design process which may lead to overall cost increases | Cost over-runs and need for variations. Errors or omission in quantities/rates etc will increase project cost. |  | Likely | Major | 7 | High | Designer to ensure sufficient check processes are undertaken as part of the cost estimates. Accountable risk assessment strategy in place. Suitable ranges used for rates/quantities, risks are included, contingencies included etc. | Possible | Moderate | 5 | Medium | 5 |  |  | FH | Avoid | Open | Follow ECI process Potential for additional design cost during construction contingency in the HDD pricing |  | 84280 | No |  | 20% | 632100 | Specialised Subcontractors not adhering to original prices, due to change in econmic environment. T&C's sent but not agreed at this stage (07/05/2020) 30% on residual cost on design HDD Contingency on direct costs of quote - 10% Civil works subbie - 10% | 421400 | Specialised Subcontractors not adhering to original prices, due to change in econmic environment Value of HDD Subbie ( 10% ) | 273910 | Specialised Subcontractors not adhering to original prices, due to change in econmic environment Value of HDD Subbie ( 5% ) | #NAME? | #NAME? | #NAME? | #NAME? |  |  | complete | RSK - A09 | 350000 |  | 11400 | 60000 |  |  |  | 0 | 421400 | 1.5 | 0.65 | 442470 | 88494
1 | HDD-MT | A10 | Jindalee SRM-19 Upgrade | Inaccurate inflation and contingency allowance. | No contingency planning | Increase in project cost. |  | Unlikely | Moderate | 4 | Medium | Ensure adequate estimate reviews and allowances for escalation to construction year | Unlikely | Minor | 3 | Low |  |  |  | FH | Transfer | Closed | A number of internal approval "Gates" need to be achieved before the procurement process can begin. Due diligence by FH during ECI phase |  | 0 | No |  | 0% | 0 | Consolidated against A40, Specialised Subcontractors not adhering to original prices, due to change in econmic environment. T&C's sent but not agreed at this stage (07/05/2020) Value of HDD Subbie ( 15% ) | 0 | Specialised Subcontractors not adhering to original prices, due to change in econmic environment Value of HDD Subbie ( 10% ) | 0 | Specialised Subcontractors not adhering to original prices, due to change in econmic environment Value of HDD Subbie ( 5% ) | [6 empty] | complete | RSK - A10 | [7 empty] | 0 | 0 | 1.5 | 0.5 | 0 | 0
1 | HDD-MT | A11 | Jindalee SRM-19 Upgrade | Financial approval delayed / not gained. | No prior approval of the project. | Project will not commence. Delay in start of process and delay to project progress. Potential claims from consultant for delay costs. Construction cost increase. |  | Unlikely | Moderate | 4 | Medium | Ensure effective communication is adopted with the authority granting financial approval. Ensure the project team establishes a robust Business Case. | Unlikely | Minor | 3 | Low |  |  |  | UU | Mitigate | Closed | Follow ECI process - Bronze, Silver Gold reviews |  | 0 | No | N/A | [13 empty] | complete | RSK - A11 | 5000 | [6 empty] | 0 | 5000 | 1.5 | 0.5
1 |  | A12 | Jindalee SRM-19 Upgrade | Change to project priority. | The customer has changed project priorities. | Timeframes will change and may increase the overall project costs. |  | Unlikely | Moderate | 4 | Medium | Resource changes due to impact of timing. | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Mitigate | Closed | Agreed to close out at Risk Workshop 1 - 17/04/2020 |  | 0 | No | N/A | [13 empty] | complete | RSK - A12 | 12000 | [6 empty] | 0 | 12000 | 1.25 | 0.5
1 |  | A13 | Jindalee SRM-19 Upgrade | Politically unacceptable option. | No consultation with key stakeholders. | Project will not commence. |  | Unlikely | Major | 5 | Medium | May result in project no longer being required. Provide information to the Local and State Members early in the project to identify sensitive issues. Proper use of the Community Engagement Planner. Adopt normal QUU planning processes - suitable for the level of planning being undertaken (i.e. Concept Planning). Include a more detailed communication strategy in the following components of design/delivery process. | Rare | Moderate | 3 | Low |  |  |  | UU | Mitigate | Closed | Briefing Concilor 17/04/2020 Stakeholder affect design risk and changes | SCG | 0 | No | N/A | 0% | 0 |  | 0 |  | 0 | [7 empty] | complete | RSK - A13 | [7 empty] | 0 | 0 | 1.5 | 0.5 | 0 | 0
1 |  | A14 | Jindalee SRM-19 Upgrade | Major changes to project scope. (Connenction Points) | Orginal concept designs are very much in it's inception. | Increase in scope will affect other project management elements, re-design, increase in planning costs. |  | Possible | Catastrophic | 8 | Extreme | Obtain support and approval for project scope. Justify any changes to project scope detailing cost and time impacts. Develop Communication Plan. | Possible | Moderate | 5 | Medium | 5 |  |  | FH | Mitigate | Open | Investigation works scheduled. Pump Station 28/4. Fortrose 28/4 Sprinkbrae inspection during works delivery, only 1 year old (residual risk to be carried forward) SRM-19 downstream, assessment report completed previously (residual risk to be carried forward) - look into further. |  | 30000 | Yes |  | 25% | 180000 | Market feedback was that FC cost $300k to implement for 1 connection. FH allowing for Hydra Stop Valve to reduce risk & time during connections – to be included in RAMP. Need to ensure availability & cost to install. Potential interconnecting risks A41, A89, A90 & A104 Interface risk separate item potentially. $1.2m of connection costs @ 10% unknown contingency | 120000 | $1.2m of connection costs @ 10% unknown contingency | 60000 | $1.2m of connection costs @ 5% unknown contingency | #NAME? | #NAME? | #NAME? | #NAME? |  |  | Complete | RSK - A14 | 120000 | [5 empty] | 5 | 0 | 120000 | 1.5 | 0.5 | 120000 | 30000
1 |  | A15 | Jindalee SRM-19 Upgrade | Change of Political Landscape _ Councillor elections in March |  | Acceleration of project |  | Unlikely | Moderate | 4 | Medium | Contingency | Unlikely | Minor | 3 | Low |  |  |  | UU | Mitigate | Closed | Refer to A12 risk |  | 0 | No | N/A |  |  |  | 0 |  | 0 | [7 empty] | complete | RSK - A15 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A16 | Jindalee SRM-19 Upgrade | Changes to key personnel during project relating to the contractor. | No planning for project completion. | Project continuity and flow of knowledge may be hindered. Delays in project delivery. |  | Almost Certain | Minor |  | High | Ensure documentation is maintained and filed effectively for successive project staff. Arrange for succession planning/project handover meetings if necessary. Prepare suitable documentation, planning and design report. | Possible | Minor | 4 | Medium |  |  |  | FH | Mitigate | Open |  |  | 2500 | No |  | 5% | 75000 | Senior FH to cover Management gap while replacemnts are secured. | 50000 | Senior FH to cover Management gap while replacemnts are secured. | 25000 | Senior FH to cover Management gap while replacemnts are secured. | #NAME? | #NAME? | #NAME? | #NAME? |  |  | Complete | RSK - A16 |  |  |  | 50000 |  |  |  | 0 | 50000 | 1.5 | 0.5 | 50000 | 2500
1 | HDD-MT | A17 | Jindalee SRM-19 Upgrade | Project not meeting timeframes. | Inadequate project scheduling. Not all activities captured in the project schedule. | Delays in approvals, and completion of project. |  | Possible | Major | 6 | High | Ensure appropriate Project Program. Regular liaison. Focus on interim timeframes. Have recovery/contingency plans in place. | Possible | Major | 6 | High |  |  |  | FH | Mitigate | Open | Refer time delays across each risk |  | 60000 | No |  | 20% | 450000 | Management | 300000 | Management | 150000 | Management | #NAME? | #NAME? | #NAME? | #NAME? |  |  | Complete | RSK - A17 | 300000 | [6 empty] | 0 | 300000 | 1.5 | 0.5 | 300000 | 60000
1 |  | A18 | Jindalee SRM-19 Upgrade | Inadequate risk management and control of identified risks and treatments. | No implementation of mitigation measures identified. | Delays in project, increased cost, increase in sub consultants scope. |  | Unlikely | Minor | 3 | Low | Adequate risk management undertaken throughout design/delivery of project. Risk assessments reviewed and monitored for all stages of project. | Unlikely | Minor | 3 | Low |  |  |  | FH | Mitigate | Closed | Close out of risk / workshop prior to RAMP submission |  | 0 |  |  |  | 0 |  | 0 |  | 0 | [7 empty] | complete | RSK - A18 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A19 | Jindalee SRM-19 Upgrade | Project Reports not suitable for approval. | Not all requirements completed. | Delay in detailed design progress. Project cancelled. |  | Unlikely | Minor | 3 | Low | Peer review to occur to ensure all needs are met and quality reviews maintained. Regular liaison with PCG and project team to ensure all issues are being considered within reports. | Unlikely | Minor | 3 | Low |  |  |  | UU | Mitigate | Closed | Closed out 17/4/2020 |  | 0 | [15 empty] | complete | RSK - A19 | [7 empty] | 0 | 0
1 | HDD-MT | A20 | Jindalee SRM-19 Upgrade | Communication not maintained through project. | Communication plan not capturiung all known community requirements. Residual risk over and above doirect costs allowed. | Could 'derail' project. Delays, cost increase. |  | Unlikely | Minor | 3 | Low | Establish communication plan identifying responsibilities and lines of communication. Maintain communication with contractor monitoring progress and issues. | Possible | Minor | 4 | Medium | 5 |  |  | FH | Mitigate | Open | Responsibility for community notifications - UU |  | 4000 | No |  | 10% | 60000 | Additional costs for community stakeholder management plan and purchase movie tickets or the like to distract noise or intrusive times of work, stringing of pipe etc. Some stakeholders in alternative accommodation. Golf course lost fees. Additional supervisor/ engineering/Community liaison costs If access is needed in emergency (old folks), keep steel plates available and machine to move. 1.8M Security fencing to site, holes to be covered. | 40000 | Purchase movie tickets or the like to distract noise or intrusive times of work, stringing of pipe etc. Extra Supervisor for 3 weeks while work is at it's peak | 20000 | Minor costs | #NAME? | #NAME? | #NAME? | #NAME? |  |  | complete | RSK - A20 | 25000 |  |  | 15000 |  |  |  | 0 | 40000 | 1.5 | 0.5 | 40000 | 4000
1 |  | A21 | Jindalee SRM-19 Upgrade | New easements required - BCC | Design will outline new easement requirements. Need to ensure early consultation with land owners. | Delays in project, increased cost, increase in sub consultants scope. Allow 0 - 30% contingency for estimate of cost for resuming land (30%x$30m) |  | Almost Certain | Major | 8 | Extreme | Ensure that the resumption issues are well documented in the Project Management Plan. Adopt standard QUU Process. Highlight potential affected areas within the project, identify affected stakeholders and implement communication strategy. | Possible | Moderate | 5 | Medium |  |  |  | UU | Mitigate | Closed | Rfer A02 for SCG |  | 0 | No | N/A |  | 0 | TBC | 0 |  | 0 | [7 empty] | complete | RSK - A21 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A22 | Jindalee SRM-19 Upgrade | Change of Stakeholder key personnel | No follow-up or maintenance communication with established stakeholders | Change of scope |  | Likely | Minor | 5 | Medium | Ensure all communication with stakeholders is documented including meeting. These records will document decisions and agreements. | Possible | Minor | 4 | Medium |  |  |  | UU | Mitigate | Closed |  | SCG | 0 | No | N/A |  | 0 | TBC | 0 |  | 0 | [7 empty] | complete | RSK - A22 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A23 | Jindalee SRM-19 Upgrade | Proposed project conflicts with emergency and essential services | Disruption caused by construction activities. No consideration of as-constructed services locations. | Major redesign required. Significant project delays. Increase project costs. |  | Possible | Major | 6 | High | QUU to undertake pre-construction stakeholder briefings | Unlikely | Major | 5 | Medium |  |  |  | FH | Avoid | Closed | PSCP developed. Contract emergency services prior to peak construction on-site. |  | 0 | Yes |  |  | 0 | BAU, no quantum risk | 0 |  | 0 | [7 empty] | complete | RSK - A23 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A24 | Jindalee SRM-19 Upgrade | Some stakeholders not initially identified. | No review of stakeholder list by project team. | Delays in project, increased cost. |  | Unlikely | Minor | 3 | Low | Feedback/Communication with the key stakeholders. Appropriate use of stakeholder management plan/Community Engagement Planner | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Refer A20. |  | 0 | No |  |  | 0 | Refer A20. | 0 |  | 0 | [7 empty] | complete | RSK - A24 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A25 | Jindalee SRM-19 Upgrade | Stakeholders may reject the proposal and potential for scope variations. (e.g.. DTMR, BCC, residents, local members). | No consultation with stakeholders. | Scope may be redefined. Delays in project, increased cost, increase in consultants scope. |  | Unlikely | Minor | 3 | Low | Adopt standard QUU planning process. Address in community engagement plan | Unlikely | Minor | 3 | Low |  |  |  | UU | Avoid | Closed | Addressed previously, refer to A03, A13, A21 |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [7 empty] | complete | RSK - A25 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A26 | Jindalee SRM-19 Upgrade | Community does not accept project (e.g. land owners, businesses, developers, service authorities, public). | No early communication of the derived project benefits. | Delays in project, increased cost, increase in consultants scope. |  | Unlikely | Minor | 3 | Low | Proper use of the Community Engagement Planner. Adopt normal QUU planning processes - suitable for the level of planning being undertaken (i.e. Concept Planning). Include a more detailed communication strategy in the following components of design/delivery process. | Unlikely | Minor | 3 | Low |  |  |  | UU | Mitigate | Closed | Addressed previously, refer to 13 stakeholder affect design risk and changes |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [7 empty] | complete | RSK - A26 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A27 | Jindalee SRM-19 Upgrade | Tunnelling, trenching, trenchless rehab unsuitable to ground conditions. Environmental harm from fluid loss. | Lack of geotechnical information | Major redesign required. Significant project delays. Increase project costs. |  | Possible | Major | 6 | High | QUU to undertake detailed geotechnical analysis and issue this report with the RFO | Unlikely | Moderate | 4 | Medium | 15 |  |  | FH | Mitigate | Open | Risk transfer if possible - pending to subcontractor RFQ response and pricing. |  | 75000 | No |  | 15% | 800000 | 80% within direct costs to capture current known information, however specifc tooling residual risks whether ground conditions are adverse to geotech relied upon. Allow for costs of additional geotechnical tests and reports and for use of equipment appropriate for the geologic conditions where investigation considered insufficient. Connecting risk A102 for Rock. This is specific for change of tooling equipment. ($500k) plus 10 days delay | 500000 | This is specific for change of tooling equipment. ($350k) plus 5 days delay | 275000 | This is specific for change of tooling equipment. ($200k) plus 2 days delay | #NAME? | #NAME? | #NAME? | #NAME? |  |  | complete | RSK - A27 | 350000 |  |  | 150000 |  |  | 5 | 0 | 500000 | 1.6 | 0.55 | 525000 | 78750
1 |  | A28 | Jindalee SRM-19 Upgrade | Compliance issues with Natural Asset Legislation (NALL) | Proposed project affects natural assets | Major redesign required. Significant project delays. Increase project costs. |  | Unlikely | Major | 5 | Medium | QUU review design | Possible | Minor | 4 | Medium |  |  |  | FH | Mitigate | Closed | Covered above A08 |  | 0 | No |  |  | 0 |  | 0 |  | 0 | [7 empty] | complete | RSK - A28 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A29 | Jindalee SRM-19 Upgrade | Open trenching creates environmental issues. | Resdiual risks over and above allowance in direct costs due to high water level and excess water. | Adverse publicity. Poor community relations. Delays due to environmental issues |  | Unlikely | Moderate | 4 | Medium | Use tunnelling techniques where possible. Ensure adequate Environmental Management Plan fully addresses open trenching. | Possible | Moderate | 5 | Medium | 20 |  |  | FH | Mitigate | Open | Liaising with authorities included in Communication Plan Allowance for 1 flex drive pump, if additional flex drive required due to high water level significantly change allow under SCG |  | 18792 | Yes |  | 15% | 175392 | Resdiual risks over and above insufficient allowance in direct costs. 100 Meters out of Drive 1, 300 meters on Dirve 2 8 x 4 inch pumps plus dewatering x 16 weeks. Where there is open trenching, additional cost for dewatering, Specialist dewatering equipment will be required to enable works, 8 x 4 inch pumps plus settlement tank etc. | 125280 | Allowance for 12 weeks of 8 x 4 inch pumps Pumping and labour for 1 person 1 day per week | 100224 | Allowance for 8 weeks of Pumping and labour for 1 person 1 day per week | #NAME? | #NAME? | #NAME? | #NAME? |  |  | complete | RSK - A29 |  | 10080 |  |  | 115200 |  | 12 | 0 | 125280 | 1.4 | 0.8 | 133632 | 20044.8
1 | HDD-MT | A30 | Jindalee SRM-19 Upgrade | Possible conditions from DTMR to include night works | No consultation as to DTMR requirements. |  |  | Possible | Major | 6 | High | Obtain all easement approvals prior to awarding contract. Utilise legal avenues to gain alignment routes | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Night work requirement to be included in ECI submission | SCG | 0 | Yes | Unless conditions over and above DTMR |  | 0 | TBC - Unless conditions over and above DTMR | 0 |  | 0 | [7 empty] | complete | RSK - A30 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A31 | Jindalee SRM-19 Upgrade | Condition of the connection points is unknown. | No assessment undertaken prior to the works |  |  | Almost Certain | Moderate | 7 | High | Complete condition assessment prior to design being complete, ensure suitable tie in points | Unlikely | Insignificant | 2 | Low |  |  |  | FH | Mitigate | Closed | Covered above A14 |  | 0 | No |  |  | 0 |  | 0 |  | 0 | [7 empty] | complete | RSK - A31 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A32 | Jindalee SRM-19 Upgrade | Third party claims resulting from property damage. | Contractor not protecting property | Increased cost due to claims and legal costs. Adverse PR and community relations |  | Possible | Moderate | 5 | Medium | Detailed assessment of contractors capabilities at RFO assessment. | Unlikely | Moderate | 4 | Medium | 15 |  |  | FH | Avoid | Open | Dilap Survey pre and post to be conducted. Include in RAMP. |  | 5000 | Yes |  | 5% | 125000 | Subject to clause 41.5(b), the excesses or deductibles payable in the event of a claim under the Contractor’s Insurances in respect of a Program will be a Direct Cost and the excesses or deductibles payable in the event of a claim under the Principal’s Insurances in respect of the Program will be treated as a Direct Cost. ($100k) | 100000 | Subject to clause 41.5(b), the excesses or deductibles payable in the event of a claim under the Contractor’s Insurances in respect of a Program will be a Direct Cost and the excesses or deductibles payable in the event of a claim under the Principal’s Insurances in respect of the Program will be treated as a Direct Cost. ($100k) | 70000 |  | #NAME? | #NAME? | #NAME? | #NAME? |  |  | complete | RSK - A32 | 100000 | [6 empty] | 0 | 100000 | 1.25 | 0.7 | 98333.3333 | 4916.6667
1 |  | A33 | Jindalee SRM-19 Upgrade | Changes to design standards. | Outdated design is used. | Delays in project, increased cost, increase in sub consultants scope. |  | Unlikely | Minor | 3 | Low | Monitor design standards and ensure compliance with current standards. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Monitor | Closed | Designed to current standards. Residual risk into construction |  | 0 | Yes |  |  | 0 | Design to current Std's, technical departure not correct. Refer risk item A09 | 0 |  | 0 | [7 empty] | complete | RSK - A33 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A34 | Jindalee SRM-19 Upgrade | Additional protective measures required by DTMR (Concrete barriers). | Inadequate Traffic Management Plan. Resdiual risk over and above additonal traffic control measuers. | Increase in cost |  | Possible | Moderate | 5 | Medium | Provide appropriate design for barrier in accordance with current design standards. Carry out design and constructability review. | Unlikely | Minor | 3 | Low | 10 |  |  | FH | Mitigate | Open | Engage TM Contractor, requirements required and TGS approval Refer to A66, 88. |  | 1000 | Yes |  | 10% | 20000 | Additonal traffic control measuers, DTMR not approving the TMP Provide T2 barriers. Carry out RPEQ Approval design and constructability review. | 10000 | Provide T2 barriers. Carry out RPEQ Approval design and constructability review. | 7000 | Very minimal allowance needed | #NAME? | #NAME? | #NAME? | #NAME? |  |  | complete | RSK - A34 | 10000 | [6 empty] | 0 | 10000 | 2 | 0.7 | 12333.3333 | 1233.3333
1 |  | A35 | Jindalee SRM-19 Upgrade | Maintenance / operations management issues (air valves/ flushing/ bypass). | The maintenance of the completed asset not considered in the design of the structure. | Delays in project, increased cost of design and/or construction, increase in consultants scope. |  | Possible | Minor | 4 | Medium | Appropriate design measures and standards adopted. Peer Reviews. Identify issues in Feasibility Report. | Unlikely | Minor | 3 | Low |  |  |  | UU | Avoid | Closed | Resolve within 2 weeks regarding hydraulics future O&M requirements. Covered within RFI Capture in basis of design and ramp report to ensure PMT are fully aware of risk ownership. | SCG | 0 | No | SCG to be drafted, QUU Operations – QUU Operational support will be excluded from all RAMPs and managed financially by QUU. |  | 0 | TBC | 0 |  | 0 | [8 empty] | RSK - A35 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A36 | Jindalee SRM-19 Upgrade | Geotechnical issues. (Ground conditions and suitability, additional sampling and analysis). | Insufficient checks on the geotechnical conditions of the work locations. | Delays in project, increased cost, Increase in consultants scope. Additional geotechnical investigation required. |  | Possible | Major | 6 | High | Ensure adequate geotechnical investigation is undertaken at concept phase. Review adjacent sites. Ensure sufficient construction management. | Possible | Moderate | 5 | Medium |  |  |  |  | Avoid | Closed | Covered above A04, A05, A06, A27 |  | 0 | No |  |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A36 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A37 | Jindalee SRM-19 Upgrade | Visual Issues. | No public consultation | Visual improvements may be required to be included in the project. |  | Rare | Minor | 2 | Low | Assess the environmental requirements | Possible | Minor | 4 | Medium |  |  |  | FH | Accept | Closed | This option will result in less damage claims in future significant events. Essential Construction banners to be installed. Permanent fencing in Golf Course, agreed with GC |  | 0 | No |  |  | 0 | Temporary asthics is covered under direct costs and Permenant design change cannot be quantfiied, can be closed | 0 |  | 0 | [8 empty] | RSK - A37 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A38 | Jindalee SRM-19 Upgrade | Minor scope changes. | Non-adherence to project scope change process. | Additional minor scope works could affect other project management elements, increase in planning costs. |  | Likely | Minor | 5 | Medium | Ensure all scope changes are justified and will provide improved outcomes for the project. As minor changes of scope arise, identify the residual impacts on the project. | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Avoid | Closed | General Access to downstream manhole - permanent maintenance track. | SCG | 0 | No | Asset requirements, access road for downstream gravity manhole? |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A38 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A39 | Jindalee SRM-19 Upgrade | Disrupted access to local residences and businesses | Lack of consultation with residence and businesses. | Compensation claims for loss of business etc. Adverse PR and community relations |  | Unlikely | Moderate | 4 | Medium | QUU to undertake pre-construction stakeholder briefings | Possible | Moderate | 5 | Medium |  |  |  | UU | Avoid | Closed | UU commitments to be transferred to FH. |  | 0 | No | Refer A20 |  | 0 | Refer A20 | 0 |  | 0 | [8 empty] | RSK - A39 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A40 | Jindalee SRM-19 Upgrade | Tunnelling operation by inexperienced contractor | Residual risk for wrong procurement selection. | Geotechnical issues Increased costs Delays due to slow progress |  | Possible | Major | 6 | High | Detailed assessment of contractors capabilities at RFO assessment including the use of sub-contractors. | Unlikely | Moderate | 4 | Medium | 10 |  |  | FH | Avoid | Open |  |  | 90000 | Yes |  | 10% | 1080000 | Residual risk for wrong procurement selection. 30% on $3m HDD package Expert trenchless due diligence to be completed by Bamser to confirm %/ allowance | 900000 | Residual risk for wrong procurement selection. 30% on $3m Expert trenchless due diligence to be completed by Bamser to confirm %/ allowance | 450000 |  | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A40 | 900000 | [6 empty] | 0 | 900000 | 1.2 | 0.5 | 810000 | 81000
1 |  | A41 | Jindalee SRM-19 Upgrade | Unable to complete live cut ins of new work. - Flow control | Unable to transfer existing flows | Project delays, increased costs, loss of service. |  | Possible | Major | 6 | High | QUU to acquire commitment from internal resources. QUU to undertake connection to existing works at the expense of the contractor. | Possible | Moderate | 5 | Medium |  |  |  | UU | Mitigate | Closed | To be discussed offline. RACI Matrix for Flow Control Plan. |  | 0 | Yes | The DC based on Flow control Plan FC13699 Rev 4, which cover 80% of what we currently know. 20% of direct costs: $150k |  | 0 | TBC, Refer A35, A89, A90 & A104 | 0 |  | 0 | [8 empty] | RSK - A41 | [7 empty] | 0 | 0 | 1.5 | 0.5 | 0 | 0
1 |  | A42 | Jindalee SRM-19 Upgrade | Ongoing availability of skilled personnel. Contractors, consultants and sub consultants. |  | Delays to project. Reduce quality of design and construction. |  | Unlikely | Moderate | 4 | Medium | Implement human resource strategies, adequate tendering processes. | Possible | Minor | 4 | Medium |  |  |  | FH | Mitigate | Closed | Covered above 16 |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A42 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A43 | Jindalee SRM-19 Upgrade | Road reserve and properties without native title extinguished. | No searches completed. | Delay in project. |  | Rare | Major | 4 | Medium | Adequate assessment at Concept Planning Stage and Business Case. Adequate consultation with Political Members and indigenous groups. | Unlikely | Major | 5 | Medium |  |  |  | UU | Mitigate | Closed | Covered in STEP |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A43 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A44 | Jindalee SRM-19 Upgrade | Negative influence from BCC departments | Lack of consultation with BCC | Major redesign required. Significant project delays. Increase project costs. |  | Unlikely | Major | 5 | Medium | QUU to ensure BCC is fully informed of project and concerns considered. | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Avoid | Closed | Covered above A21 BCC item |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A44 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A45 | Jindalee SRM-19 Upgrade | Project conflicts with public amenities. (bike path / golf course) | Lack of consultation with stakeholders | Major redesign required. Significant project delays. Increase project costs. |  | Possible | Moderate | 5 | Medium | QUU to undertake pre-construction stakeholder briefings | Possible | Minor | 4 | Medium | 5 |  |  | FH | Mitigate | Open | To be addressed by temp and permanent design. Amendments made with GC or Bike Path to be addressed, covered in RAMP |  | 20000 | Yes | Risk is cycle way approval, project delays to connections. BCC & TMR | 40% | 80000 | Temporary footpath costs TBC pending outcome | 50000 |  | 30000 |  | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A45 | 50000 | [6 empty] | 0 | 50000 | 1.6 | 0.6 | 53333.3333 | 21333.3333
1 |  | A46 | Jindalee SRM-19 Upgrade | Proposed project doesn't accommodate major stakeholder requirements / constraints | Lack of consultation with stakeholders | Major redesign required. Significant project delays. Increase project costs. |  | Unlikely | Major | 5 | Medium | Complete stakeholder report as part of the project's Communication Plan | Unlikely | Minor | 3 | Low |  |  |  | UU | Mitigate | Closed | Covered above 13 |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A46 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A47 | Jindalee SRM-19 Upgrade | Proposed crossing of Centenary Highway not acceptable by TMR | Lack of geotechnical information lack of invert level survey Lack of topographical survey details | Major redesign required. Significant project delays. Increase project costs. |  | Possible | Major | 6 | High | QUU to undertake detailed geotechnical analysis and issue this report with the RFO | Unlikely | Major | 5 | Medium |  |  |  | UU | Avoid | Closed | Covered above 03 |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A47 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A48 | Jindalee SRM-19 Upgrade | Project design life not achieved creating serviceability issues. | Unsuitable design and / or materials. | Increased whole of life costs. Project objectives not achieved. Early failure of system. |  | Possible | Major | 6 | High | Ensure design and materials comply with QUU Standards | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Mitigate | Closed | All materials meet design life requirements | SCG | 0 |  | Pipe, size and type of pipe are selected components by UU. FH cannot alter the selected material. Scope change guidelines (SCG) to identify boundary limit example pigging. |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A48 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A49 | Jindalee SRM-19 Upgrade | Traffic management issues. (Working under traffic). | Unsuitable traffic management plan. Difficult or busy location. | Delays in project, increased cost, variations issued to contractor. |  | Almost Certain | Moderate | 7 | High | Ensure appropriate traffic management plans are prepared, approved and implemented. Liaise with construction technicians. Peer review. | Unlikely | Moderate | 4 | Medium | 5 |  |  | FH | Mitigate | Open |  |  | 3000 | Yes |  | 10% | 60000 | 20% of circa $300k Allowance for traffic management | 30000 | 10% of circa $300k Allowance for traffic management | 15000 | 5% of circa $300k Allowance for traffic management | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A49 | 30000 | [6 empty] | 0 | 30000 | 2 | 0.5 | 35000 | 3500
1 | HDD-MT | A50 | Jindalee SRM-19 Upgrade | Limited option for disposal of tailings/spoil from excavation | Material unsuitable for recycling. Landfill unavailable / unacceptable | Increased disposal costs |  | Likely | Moderate | 6 | High | Plan early for suitable disposal strategy. | Possible | Moderate | 5 | Medium |  |  |  | FH | Accept | Closed | Contractor input from RFQ to RAMP. Close before RAMP. |  | 0 | Yes |  |  | 0 | No quantum risk Check mud lines daily, have a selected area to contain Bentonite, clean up equipment readily available and Disposal to Trade Waste Facilities to be nominated by Subcontractor and approved by FH | 0 |  | 0 | [8 empty] | RSK - A50 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A51 | Jindalee SRM-19 Upgrade | Unavailability of specialist construction equipment / contractor | Design requires equipment that has limited availability. Equipment and or contractor working on other projects. | Project delayed awaiting availability |  | Unlikely | Major | 5 | Medium | Undertake review of contractor's methodology. Contractor to ensure availability of required equipment. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Audits to be conducted. |  | 0 | Yes |  |  | 0 | Refer A40, Expert trenchless due diligence to be completed by Bamser. | 0 |  | 0 | [8 empty] | RSK - A51 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A52 | Jindalee SRM-19 Upgrade | Road Authorities and Public Utilities plant issues. | Plant and resources not available for other utilities to undertake necessary works | Delays in project, increased cost, lack of Authority response, variations issued to contractor. |  | Possible | Major | 6 | High | Early liaising with authorities. Appropriate Work Method statements. Scheduled activities to include time contingency. | Possible | Minor | 4 | Medium |  |  |  | FH | Mitigate | Closed | Risk is transferred to the Contractor. Review the contractors work plan to ensure the acquisition of materials is undertaken early in the schedule. Known services accounted for, residual risk to unknown service. |  | 0 | Yes |  |  | 0 | Energex refer Risk No dealt with in under risks | 0 |  | 0 | [8 empty] | RSK - A52 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A53 | Jindalee SRM-19 Upgrade | Choice of subcontractor. | The chosen contractor has a number of projects currently underway. | Quality, time and/or budget issues depending on contractor chosen. |  | Possible | Moderate | 5 | Medium | Adequate tender assessment processes to include availability of contractor. | Unlikely | Minor | 3 | Low |  |  |  | FH | Avoid | Closed | Delays to the project timing would impact on cost. Ensure additional resources are allocated for the change in scope. |  | 0 | Yes |  |  | 0 | Allowed under other risks, A17 | 0 |  | 0 | [8 empty] | RSK - A53 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A54 | Jindalee SRM-19 Upgrade | Earthworks issues. (survey/set out issues) (latent condition). | A difficult worksite chosen or no other suitable worksite is available. | Delays in project, increased cost, variations issued to contractor. |  | Possible | Major | 6 | High | Detailed Design competence. Design to include site parameters. | Possible | Minor | 4 | Medium |  |  |  | FH | Mitigate | Closed |  | SCG | 0 | Yes | Latent means unknown, therefore SCG to be drafted. Latent Conditions |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A54 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A55 | Jindalee SRM-19 Upgrade | Material supply issues. (relevant to UU). | A large number of construction projects using the same materials resulting in supply issues. Supply issues for raw resources. Manufacturing issues. | Delays in project, increased cost, variations issued to contractor. |  | Possible | Moderate | 5 | Medium | Advance notice to secure the required materials. Place the once on the Contractor to secure supply of materials. | Unlikely | Minor | 3 | Low | 10 |  |  | FH | Mitigate | Open | Early procurement to be progressed as necessary |  | 5000 | Yes |  | 10% | 90000 | Value of supplied items excluding PE Pipework, $250k x 20% and transport Pipework, Valves and fittings Site visits to supplier facilities included in managements costs. UU costs to be added if any. | 50000 |  | 25000 |  | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A55 |  |  |  |  | 50000 |  |  | 0 | 50000 | 1.8 | 0.5 | 55000 | 5500
1 |  | A56 | Jindalee SRM-19 Upgrade | Additional works (variations). | The project scope increased by management to include other priorities. | Delays in project, increased cost, variations issued to contractor. |  | Possible | Moderate | 5 | Medium | Scope control. Adequate and accurate documentation and contract supervision | Possible | Minor | 4 | Medium |  |  |  | UU | Transfer | Closed | Covered Above 38 |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A56 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A57 | Jindalee SRM-19 Upgrade | Risk for Flow Control Connections - due to network suitability | Flow control | Delays in project, increased cost, variations issued to contractor. |  | Possible | Moderate | 5 | Medium | Contract out the risk. Program for construction in dry period (if possible). | Possible | Moderate | 5 | Medium | 5 |  |  | FH | Accept | Open | Risk for Flow Control Connections - max 10mm rainfall + 3 day delay to program for each period relating to network suitability |  | 49320 | No |  | 50% | 177552 | network suitability flow effects (4 days min), 4 hours min x 12 tankers Crew cost and Management costs | 98640 | network suitability flow effects (3 days min), 4 hours min x 12 tankers Crew cost & Management costs | 49320 | Wet weather flow effects (1 days min), 4 hours min x 6 tankers Crew cost Management costs | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A57 | 8640 |  |  | 90000 |  |  |  | 0 | 98640 | 1.8 | 0.5 | 108504 | 54252
1 |  | A58 | Jindalee SRM-19 Upgrade | All permits not obtained. (UU). | Required approval not identified early. Late application process. | Potential delay claim from construction contractor. |  | Possible | Moderate | 5 | Medium | Ensure all permits requirements are identified, planned and obtained. | Possible | Moderate | 5 | Medium |  |  |  | FH | Mitigate | Closed |  | SCG | 0 | No | DTMR - In relation to Friday and Saturday working hours (TBC) |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A58 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A59 | Jindalee SRM-19 Upgrade | Contractor liquidation. | Insufficient checks on the financial health of the contractor | Change in contractor. Time delays. |  | Unlikely | Major | 5 | Medium | Adequate tender assessment processes. Request for suitable bank guarantee. | Unlikely | Major | 5 | Medium |  |  |  | FH | Mitigate | Closed | Due diligence during ECI Phase. |  | 0 | No |  |  | 0 | Residual risk allowed above for HDD Subcontractor. No associated costs, external credit report if required that may have costs only if initial assessment is not satisfied. | 0 |  | 0 | [8 empty] | RSK - A59 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A60 | Jindalee SRM-19 Upgrade | Proposed construction sequence does not accommodate major stakeholder requirements/constraints | Lack of consultation with major stakeholders. No flexibility in construction sequence. | Major redesign required. Significant project delays. Increase project costs. |  | Unlikely | Major | 5 | Medium | Comprehensive RFO document incorporating major stakeholder issues. Ensure contractors address stakeholder concerns in the RFO response document. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed |  |  | 0 | No |  |  | 0 | Refer community costs above, A20 | 0 |  | 0 | [8 empty] | RSK - A60 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A61 | Jindalee SRM-19 Upgrade | Unable to provide adequate technical supervision | Failure of pipeline (included welds) under final hydrotest. 10% is as per standard, however some industry standards have suggessted 100% of welds to reduce the risk. | Unable to substantiate contractors claims and concerns. Project delays |  | Unlikely | Major | 5 | Medium | Highlight early the required resources for the delivery of the project. If required hire appropriately skilled contractor to manage on QUU's behalf. | Unlikely | Moderate | 4 | Medium | 15 |  |  | FH | Mitigate | Open | Continuous mitigation of risk items required input from DTMR/Weld inspector supervision during works & availability. |  | 70000 | Yes |  | 10% | 1050000 | Failure of pipeline (included welds) under final hydrotest Weld testing .... Cost of Bamser for trenchless allowed above, however the residual risk (costs) is based on the delay associated with the defective workmanship. The subcontractor welding bear the costs of direct costs associated with the repair/defect. Delay costs x 15 days | 700000 | Failure of pipeline (included welds) under final hydrotest Cost of Bamser for trenchless allowed above, however the residual risk (costs) is based on the delay associated with the defective workmanship. The subcontractor welding bear the costs of direct costs associated with the repair/defect. Delay costs x 10 days | 350000 | Cost of Bamser for trenchless allowed above, however the residual risk (costs) is based on the delay associated with the defective workmanship. The subcontractor welding bear the costs of direct costs associated with the repair/defect. Delay costs x 5 days | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A61 | 250000 |  |  | 300000 | 150000 |  |  | 0 | 700000 | 1.5 | 0.5 | 700000 | 70000
1 | HDD-MT | A62 | Jindalee SRM-19 Upgrade | Tunnelling leads to contamination of waterways | Inappropriate construction techniques. Inadequate stakeholder consultation. Lack of environmental management system. | Adverse publicity. Poor community relations. Delays due to environmental issues |  | Possible | Major | 6 | High | Review contractors construction methodology. Ensure tunnelling is dealt with in the Environmental Management Plan. | Unlikely | Moderate | 4 | Medium | 10 |  |  | FH | Mitigate | Open |  |  | 100000 | Yes |  | 20% | 900000 | In the event of a frac out, Provisional item has been recived which is included in direct costs. The additional duration for PM Team and Site runnning costs x 10 days Enviromental potential fines Pending review of contractors construction methodology. | 500000 | The additional duration for PM Team and Site runnning costs x 5 days | 250000 | The additional duration for PM Team and Site runnning costs x 2 days | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A62 | 200000 |  |  | 300000 |  |  | 5 | 0 | 500000 | 1.8 | 0.5 | 550000 | 110000
1 | HDD-MT | A63 | Jindalee SRM-19 Upgrade | Tunnelling operation stopped due to adverse ground conditions | Unsuitable tunnelling methodology | Increased costs, project delays |  | Possible | Major | 6 | High | QUU to undertake detailed geotechnical analysis and issue this report with the RFO | Possible | Moderate | 5 | Medium |  |  |  | FH | Mitigate | Closed | Geotechnical Risk as above; Shutdown due to community requirements - separate risk |  | 0 | No |  |  | 0 | Covered elsewhere, to be considered after Bamser reports and market submissions. | 0 |  | 0 | [8 empty] | RSK - A63 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A64 | Jindalee SRM-19 Upgrade | Tunnelling in the vicinity of existing infrastructure causing property damage or foundation issues. | No as-constructed plans of existing infrastructure. Contractors methodology involves additional and unnecessary risks. | Re-design required. Project delays. Damage to existing infrastructure / buildings. Increase in project costs. |  | Possible | Major | 6 | High | Acquire detailed plans of the location. Review the contractor's construction methodology. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Avoid | Closed | Refer also Financial - delay to project |  | 0 | No |  |  | 0 | Covered elsewhere, to be considered after Bamser reports and market submissions. | 0 |  | 0 | [8 empty] | RSK - A64 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A65 | Jindalee SRM-19 Upgrade | Tunnelling methodology not suitable proposed pipeline length | Length of drilling not able to be achieved. | Increased costs, project delays |  | Possible | Major | 6 | High | Contract size of tunnelling machine that would allow man entry to cutter head. | Possible | Moderate | 5 | Medium | 10 |  |  | FH | Avoid | Open | Due diligence during ECI Phase. |  | 12500 | No |  | 5% | 312500 | Residual risk of upgrading the HDD machine may cost circa $350k | 250000 | Residual risk of upgrading the HDD machine may cost circa $250k | 208333.3333 | Residual risk of upgrading the HDD machine may cost circa $200k | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A65 | 250000 | [6 empty] | 0 | 250000 | 1.25 | 0.83333 | 256944.4444 | 12847.2222
1 | HDD-MT | A66 | Jindalee SRM-19 Upgrade | Tunnelling under footpaths / roadways interferes with existing utilities | Lack of as-constructed plans of the existing utilities | Re-design required. Project delays. Damage to existing utilities. Increase in project costs. |  | Possible | Moderate | 5 | Medium | Acquire detailed plans of the location. Seek information from "Dial before you dig" | Possible | Moderate | 5 | Medium |  |  |  | FH | Avoid | Closed | Issues to be mitigated by construction contractor. |  | 0 | Yes |  |  | 0 | Risk for unknown services covered elsewhere | 0 |  | 0 | [8 empty] | RSK - A66 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A67 | Jindalee SRM-19 Upgrade | Public utility plant issues. (Unknown plant / unknown location). | No investigation into the public services located in the area. | Delays in project, increased cost, increase in consultants scope. |  | Possible | Moderate | 5 | Medium | Detailed investigation of service locations during the subsequent stages of the design/delivery of the project. | Unlikely | Minor | 3 | Low |  |  |  | FH | Avoid | Closed | Surveyor to mark all services, Spotter in place for all excavation works, competent operator only to use plant, refer to assets owner for requirements when working around their services. bladed bucket only to be used when digging around services Allow for cost of repairs to existing pipelines, civil structures, or other damaged or disconnected services. |  | 0 | Yes |  |  | 0 | Risk for unknown services covered above and elsewhere | 0 |  | 0 | [8 empty] | RSK - A67 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A68 | Jindalee SRM-19 Upgrade | Proposed design not constructible | Lack of constructability consideration undertaken during hydraulic design | Increased cost, project delays |  | Possible | Catastrophic | 8 | Extreme | QUU to review hydraulic design prior to releasing RFO document. Appointment of contractor to undertake concept plan to ensure constructability. | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Avoid | Closed | Scope change Guideline reccomended for Hydraulics | SCG | 0 | No |  |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A68 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A69 | Jindalee SRM-19 Upgrade | Construction methodology introduces safety issues for workers and general public | Safety considerations not included in design | OHS issues Public safety issues Insurance issues |  | Possible | Catastrophic | 8 | Extreme | Review design prior to releasing the RFO to ensure safety is paramount. | Possible | Moderate | 5 | Medium | 5 |  |  | FH | Avoid | Open | COVID-19 risk to be addressed separately |  | 10000 | Yes |  | 10% | 150000 | Quantum risk - Addditonal costs in relation to confined space, purging existing mains, (Gas and Asbestos coating issues) Refer A81 for COVID-19 Additonal costs and time related component to the three items identified. | 100000 |  | 50000 |  | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A69 | 100000 | [6 empty] | 0 | 100000 | 1.5 | 0.5 | 100000 | 10000
1 | HDD-MT | A70 | Jindalee SRM-19 Upgrade | Noise, air quality, vibration, dust, odour issues during construction. | Poor construction methods. No environmental management plan. | Noise suppression may be required to be included in the project. Increase in cost. |  | Likely | Major | 7 | High | Monitor Community Consultation and Complaints register. Implement environmental management plan and maintain liaison with local residents during construction. | Possible | Moderate | 5 | Medium |  |  |  | FH | Avoid | Closed | Covered in EMP Vibration monitoring during tunnelling - highway /aged care? - RFQ DTMR area prep - ground movement Noise / Dust / Light monitoring |  | 0 |  |  |  | 0 | Refer A93 | 0 |  | 0 | [8 empty] | RSK - A70 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A71 | Jindalee SRM-19 Upgrade | Sediment and Erosion issues / water quality. | No or poor environmental management plan. | Pollution of waterways. Possible complaints from the community, or implications from authorities such as the EPA. |  | Possible | Minor | 4 | Medium | Incorporate appropriate sediment and erosion controls in design. Construction contractor to perform water quality testing where appropriate. | Possible | Moderate | 5 | Medium |  |  |  | FH | Mitigate | Closed | Covered in EMP |  | 0 | Yes |  |  | 0 | Covered under A62 | 0 |  | 0 | [8 empty] | RSK - A71 | [7 empty] | 0 | 0 | 1.8 | 0.5 | 0 | 0
1 |  | A72 | Jindalee SRM-19 Upgrade | 3rd party global influences on the price of materials | No monitoring of price fluctuations | Increase in commodity prices |  | Unlikely | Moderate | 4 | Medium | Contingency. Monitor the cost of materials to ensure that the initial estimate is still accurate. | Possible | Minor | 4 | Medium |  |  |  | FH | Mitigate | Closed | Manage what is currently unknown. |  | 0 |  |  |  | 0 | Allowed under other risks | 0 |  | 0 | [8 empty] | RSK - A72 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A73 | Jindalee SRM-19 Upgrade | Conflict with other UU infrastructure works | No liaising with management within QUU on conflicting projects | No coordination with other projects in QUU. Unsuitable construction sequencing |  | Unlikely | Moderate | 4 | Medium | Project delivery team to liaise with all areas in QUU to determine conflicting projects. | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Mitigate | Closed | FH engage discussion with UU operations / maintenance. |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A73 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A74 | Jindalee SRM-19 Upgrade | Operational maintenance requirements in the design. | No consideration of pipeline maintenance requirements in the design for the new pipeline and connections points. | Urban Utilities unable to maintain the new section sewer pipeline. |  | Possible | Moderate | 5 | Medium | Ensure maintenance requirements are considered in the design specification and invite Maintenance Section to design meetings. | Unlikely | Moderate | 4 | Medium |  |  |  | UU | Avoid | Closed | Refer to above 35 |  | 0 | No | N/A |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A74 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A75 | Jindalee SRM-19 Upgrade | No enveloper proposed if HDD for the Centenary Hwy crossing | No consultation with DTMR and their requirements. | DTMR don't approve the design for the replacement sewer rising main. |  | Possible | Catastrophic | 8 | Extreme | Early liaising with DTMR concerning design requirements. | Unlikely | Catastrophic | 7 | High |  |  |  | FH | Avoid | Closed | Enveloper Required. |  | 0 |  |  |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A75 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A76 | Jindalee SRM-19 Upgrade | Contractors adopts unsuitable commissioning method | Commissioning plan not reviewed / approved. Contractors deviates from approved plan / method | Project delays. Loss of service. |  | Possible | Major | 6 | High | QUU review commissioning methodology and ensure compliance. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Co-ordination with UU Ops. Commissioning Plan to be developed for NAP. |  | 0 |  |  |  | 0 | Staging / Commisioning risk may result in retesting (hydro test etc) lies with subcontractor. | 0 |  | 0 | [8 empty] | RSK - A76 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A77 | Jindalee SRM-19 Upgrade | Clearing / works outside approved construction boundary. | Construction area incorrectly marked out by survey | Fines, penalties, infringements legal action |  | Possible | Major | 6 | High | Ensure survey is correct (hold point), flag off area. Used approved clearing contractor | Unlikely | Major | 5 | Medium | 2 |  |  | FH | Avoid | Open | Clearing area not yet defined for HDD string area. Arborist survey of trees and vegetation, report next week for NALL submission on 8/5/2020. Potential for 4 week NALL approval (worst case) - 5/6/20 |  | 1125 |  |  | 5% | 33750 | Survey to re surey, crew delay 2 days | 22500 | Survey to re surey, crew delay 1 days | 11250 | Survey to re surey, crew delay 0 days | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A77 | 22500 | [6 empty] | 0 | 22500 | 1.5 | 0.5 | 22500 | 1125
1 |  | A78 | Jindalee SRM-19 Upgrade | Asbestos found on existing plant / services and buried areas. | Unknown conditions, potential dumping point previously. Section of golf course is used as a material laydown dump and load point. | Fines and reputational damage plus delays and costs to project if not dealt with correctly |  | Possible | Major | 6 | High | Asbestos testing allowance for pipe / pump station / pits / linings. | Unlikely | Major | 5 | Medium |  |  |  | FH | Mitigate | Open | UU Asbestos Register request. Coating to be tested during condition assessment works 28/4 prior to RAMP. |  | 19500 | No |  | 60% | 65000 | Asbestos pipe within pump station. Plus lots of contaminated / rubble buried. High chance of asbestos. | 32500 | Assume 5 days for Hygienist and allowance for disposal and PPE | 16250 |  | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A78 | 32500 | [6 empty] | 0 | 32500 | 2 | 0.5 | 37916.6667 | 22750
1 | HDD-MT | A79 | Jindalee SRM-19 Upgrade | Pressure testing failure | Potential for public to vandalise pipe between shifts. Not completing proper quality checks. Not securing end plates correct. Not setting up exclusion zones. | Could be catastrophic in terms of a death, flooding work areas / plant / equipment / local roads or golf course |  | Possible | Major | 6 | High | Complete quality checks (air pressure test section), exclusion zones in place around test ends. HP checks for end plates. Secure storage and CCTV of pipe storage. | Unlikely | Major | 5 | Medium |  |  |  | FH | Mitigate | Closed | Secure storage costs post pipe manufacture. |  | 0 |  |  |  | 0 | Secure storage costs allowed under direct costs / pipe manafacture | 0 |  | 0 | [8 empty] | RSK - A79 | [7 empty] | 0 | 0 | 1.5 | 0.5 | 0 | 0
1 | HDD-MT | A80 | Jindalee SRM-19 Upgrade | Overseas materials / material failures due to poor quality | Availability due to current COVID-19 restrictions | Time and cost |  | Possible | Major | 6 | High | Utilise Australian suppliers, known with good history or quality. Complete inspections. | Rare | Major | 4 | Medium |  |  |  | FH | Avoid | Closed | Offsite Testing Inspections - Hydrostatic Testing Valves |  | 0 |  |  |  | 0 | Allowed elsewhere | 0 |  | 0 | [8 empty] | RSK - A80 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A81 | Jindalee SRM-19 Upgrade | COVID-19 | COVID-19 affect currently unknown impact on supply. | No coverage under the Contract, costs and time at large. A lot of unknowns. Slow construction to adhere with social distancing requirements |  | Likely | Major | 7 | High | Local Suppliers, Early engagement. Allowance for social distancing / slow production risk | Possible | Moderate | 5 | Medium |  |  |  | FH | Mitigate | Closed | Flowmeter - lead times. Material selection based on best & readily available, UU approved. Labour movement interstate (quarantine period), all subcontractor works. Any personnel - COVID-19 shutdown project. Key mitigation to keep crews separated, additional crib sheds / toilets / offices. Fulton Hogan COVID response - to be reviewed by DM and amend if required, discuss with MTP PST upgrade team. Aged Care Centre - potential outbreak - lockdown internal or external? Will this impact access agreement? FH RAMP Allowance for current known legislation situations. Any changes covered under SCG - legislation change or UU direction. |  | 0 |  |  |  | 0 | Primary concern - 4m2 working rule, sanitations, crib sheds and lead items. Direct costs has allowed for COVID-19 If one person has COVID-19, fresh crew for mitigation to provide resuqeuncung/mob fee. Any additional change in Law will be under SCG. Contract clauses to be applied. | 0 |  | 0 | [8 empty] | RSK - A81 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A82 | Jindalee SRM-19 Upgrade | Design creep | Additional cost or lack of spec compliance. Clash with unknown services requiring change. Connection points | Time and cost |  | Possible | Major | 6 | High | Early condition assessment, contingency add to RAMP for design support | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Design is moving very quickly, residual risk going forward of design scope growth. |  | 0 |  |  |  | 0 | SMEC/ Bamser to advise. Rfer contingnency above | 0 |  | 0 | [8 empty] | RSK - A82 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A83 | Jindalee SRM-19 Upgrade | Theft / damage to plant, materials or equipment | Site not secure and fenced adequately. DTMR laydown area has been broken into several times | Time and cost |  | Possible | Moderate | 5 | Medium | Site security - fencing / CCTV installation. Correct lock up plant / equipment. Tie down, utilise containers | Rare | Moderate | 3 | Low |  |  |  | FH | Mitigate | Closed | Sufficient ramp inclusion for fencing / CCTV of compounds. |  | 0 |  |  |  | 0 | Fencing in required areas and CCTV allowed under direct costs, theft allowed under A32 | 0 |  | 0 | [8 empty] | RSK - A83 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A84 | Jindalee SRM-19 Upgrade | Energex Power Pole Stay within new alignment at Pump Station 19 | Existing Energex Stay clashes with proposed new pipe alignment. Due to future proposed TMR road corridor. | Additional relocation cost for temp / permanent solution. EGX engagement required, potential to push out program due to availability. |  | Almost Certain | Moderate | 7 | High | Early engagement with EGX to get pricing & schedule works. Install Temp Stay with concrete block during works. Proposed Sidewalk stay as part of final works. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Avoid | Closed | RAMP price for permanent solution. Potential Risk allowance for temporary works during construction. Including potential for EGX pole to also be replaced, currently unknown. |  | 0 |  |  |  | 0 | Covered under direct costs. | 0 |  | 0 | [8 empty] | RSK - A84 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 | HDD-MT | A85 | Jindalee SRM-19 Upgrade | Culvert bridge in Golf Club requiring upgrade | Unknown load rating, | Potential cost to upgrade the bridge to work area |  | Possible | Moderate | 5 | Medium | Condition assessment - RPEQ Chase plans from JGC or BCC | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | RAMP allowance for barricading / upgrade if required. Temp bridge to span existing culvert based on RPEQ feedback. Will be included in RAMP as direct cost. |  | 0 | No |  |  | 0 | Existing bridge repair and fail | 0 | Temp bridge to span existing culvert based on RPEQ feedback. | 0 | [8 empty] | RSK - A85 | [8 empty] | 0 | 2 | 0.5 | 0 | 0
1 |  | A86 | Jindalee SRM-19 Upgrade | Existing Scour Valve condition (operability) | Unknown if valve operates | Unable to dewater line from scour point |  | Possible | Major | 6 | High | Complete check on scour under NAP to ensure it operates. Require UU trained operator | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Mitigation measure in place if valve cannot be closed once tested. Current scour MH overflows to creek. | SCG | 0 |  |  |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A86 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A87 | Jindalee SRM-19 Upgrade | Existing Scour Access to pit location | Currently no safe way to access scour valve and pit for dewatering | Access track to be constructed from on-ramp to scour pit location |  | Almost Certain | Moderate | 7 | High | Construct Access Track | Unlikely | Minor | 3 | Low |  |  |  | FH | Mitigate | Closed | Further investigation required. Arborist assessment of trees in area Other scour point?? Available and known? | SCG | 0 |  |  |  | 0 |  | 0 |  | 0 | [8 empty] | RSK - A87 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A88 | Jindalee SRM-19 Upgrade | Construction impact on Cycleway - footpath | Work area will require cycleway to be diverted or closed | Negative feedback from community, additional time and cost to manage cycleway |  | Almost Certain | Moderate | 7 | High | Early Traffic Guidance engagement for solutions. Community Liaising with Brisbane cycle group. TMR request and approval Temp diversion in place | Possible | Minor | 4 | Medium |  |  |  | FH | Avoid | Closed | Include TGS / plan to be included in RAMP. Notification of works to community and key stakeholders, residual risk if proposal is accepted. Early engagement. Permit from BCC 4-6weeks. |  | 0 |  |  |  | 0 | Use approved TMPs and Approved Traffic Management Company, additional traffic controller for duration, pending market methodologies, refer A66. | 0 |  | 0 | [8 empty] | RSK - A88 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A89 | Jindalee SRM-19 Upgrade | Isolation shutdown period - Flow control | Shutdown period currently unknown, drain down time unknown. | Reduced working time for connection, over run of works / extended isolation required - additional tankers / resources |  | Likely | Major | 7 | High | Trial drain down period. | Rare | Major | 4 | Medium |  |  |  | UU | Mitigate | Closed | Further discussion & planning required | SCG | 0 |  |  |  | 0 | TBC pending flow control. A35, A41, A89, A90 & A104 | 0 |  | 0 | [8 empty] | RSK - A89 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A90 | Jindalee SRM-19 Upgrade | Isolation - failure to isolate line - flow | UU isolation fail due to damaged / poor condition of existing asset. 10mm rain = cancelled works + 3 days as per Flow Control Plan | Failed connection / cut-over works. Cost in Tankers / Traffic Control / Work Crew / Supervisor Program delays. |  | Possible | Major | 6 | High | Exercise Valves prior. Trial drain down period. | Rare | Major | 4 | Medium |  |  |  | UU | Mitigate | Closed | Scope Change Guideline for cancellation 1+? Or additional allowance in RAMP? Cost of Trial vs. Risk Further discussion & planning required. Cross reference with A41, A89, A104 | SCG | 0 | No | Scope change guideline (SCG) |  | 0 | Trial shut goes wrong, suggestion to have repair collars in place and the like, Would be good to have this material on hand (ex-stock), nearby or in UU yard in the event of a strike. | 0 |  | 0 | [8 empty] | RSK - A90 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A91 | Jindalee SRM-19 Upgrade | Weather & Flooding | Historic flood map, all 3 sites 5m underwater (2011 flood) | Flooding of all site, plant, equipment. Environmental impacts, delays to program and costs |  | Possible | Catastrophic | 8 | Extreme | Monitor weather. Contractor insurances. Wet weather mitigation & response plan | [7 empty] | FH | Mitigate | Closed | Consider full risk, no scope change - Cost Forecast assessment of BOM data - include in RAMP SCG for anything outside RAMP allowance, similar to MTP |  | 0 |  |  |  | 0 | Refer A07 | 0 |  | 0 | [8 empty] | RSK - A91 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A92 | Jindalee SRM-19 Upgrade | Re pressurisation causing damage to existing main | Unknown condition or main. Potential burst or collapse during recharge. | Traffic / Community and reputation impacts, additional cost to repair main. |  | Possible | Major | 6 | High | Installation of hydras tops to reduce drain down section of pipe to help prevent collapse. Contingency spare parts to be allowed for | Unlikely | Major | 5 | Medium |  |  |  | UU | Mitigate | Closed |  | SCG | 0 | No | N/A |  | 0 | TBC | 0 |  | 0 | [8 empty] | RSK - A92 | [7 empty] | 0 | 0 |  |  | 0 | 0
1 |  | A93 | Jindalee SRM-19 Upgrade | Community complaints / claims | Noise, vibration, dust, light from works | Negative feedback from community, additional time and cost. Reputational damage. |  | Possible | Moderate | 5 | Medium | Enviro Baseline monitoring noise, vibration, dust to be undertaken prior to construction | Unlikely | Moderate | 4 | Medium | 5 |  |  | FH | Avoid | Open | Noise / Dust / Light / Vibration/Settlement monitoring. Cost to be covered in RAMP submission. Pricing due back 1/05/2020. |  | 50000 | Yes |  | 2% | 3125000 | Noise / Dust / Light / Vibration/Settlement monitorin covered in direct costs. Actual rectification risks $3.1m repairing aged care centre, underpin building | 2500000 | Actual rectification risks $2.5m repairing aged care centre, underpin building | 1250000 | Actual rectification risks $1.25m repairing aged care centre, underpin building | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A93 | 2500000 | [6 empty] | 0 | 2500000 | 1.25 | 0.5 | 2291666.6667 | 45833.3333
1 |  | A94 | Jindalee SRM-19 Upgrade | Risk of grouting decommissioned pipe, once cut overs complete. - 1200lm (150m3). | Too much or not enough grout vs. estimated quantity. UU asset unable to be located (Scours / Air Valves) | Possible scour point at damaged section of the pipes. Pipe collapse below highway - future sinkhole |  | Possible | Moderate | 5 | Medium | Flushing line & CCTV prior to grouting. Decommissioning sequence / methodology to be developed. DTMR approval of methodology. | Unlikely | Moderate | 4 | Medium |  |  |  | FH | Mitigate | Closed | Allowance for flushing & CCTV line. Restricted by jet rod distance. | SCG | 0 | Yes | Flushing line & CCTV prior to grouting included in direct costs. Excavate in area to plug where leaking, open cut an additional area. GPR X-Ray and shut off main cannot be performed to ascertain a reasonable assement of the main. SCG to be drafted. |  | 0 | Excavate in area to plug where leaking, open cut an additional area. Risk of DTMR not approving methdoology. Worst case reline the main and bleed points | 0 | Excavate in area to plug where leaking, open cut an additional area. Reline a section of the main Say 20% of 1.2km and bleed points. Risk of DTMR not approving methdoology. | 0 | [8 empty] | RSK - A94 | [7 empty] | 0 | 0 | 1.2 | 0.5 | 0 | 0
1 | HDD-MT | A95 | Jindalee SRM-19 Upgrade | Existing pipe burst at Micro tunnel exit shaft | HDD under existing main | Burst, impact to UU network. Environmental incident - overflow into water ways |  | Possible | Major | 6 | High | Temporary works assessment. Move shaft further up toward Aged Care, Offset new main further away from existing to reduce disturbance. | Unlikely | Major | 5 | Medium | 2 |  |  | FH | Avoid | Open |  |  | 3250 | Yes |  | 5% | 81250 | Risk of existing sewer main Hot tap to be inserted prior to exit of pipe. Last drive at low peak. Crew costs, mgt repair, tankering and associated fittings | 65000 | Risk of existing sewer main Hot tap to be inserted prior to exit of pipe. Last drive at low peak. Crew costs, Mgt repair, tankering and associated fittings | 32500 | Risk of existing sewer main Hot tap to be inserted prior to exit of pipe. Last drive at low peak. 50k of crew costs, repair, tankering and associated fittings | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A95 | 25000 |  |  | 30000 | 10000 |  | 1 | 0 | 65000 | 1.25 | 0.5 | 59583.3333 | 2979.1667
1 | HDD-MT | A96 | Jindalee SRM-19 Upgrade | Damage to DTMR culverts | MD or HDD hitting culverts | Program delays, additional re-works to fix culverts - costs. DMTR relationship and approvals. |  | Possible | Major | 6 | High | Specialised tunnelling experts, Survey tracking head - accurate | Unlikely | Major | 5 | Medium |  |  |  | FH | Avoid | Closed |  | SCG | 0 | Yes | The unknown ground conditions underneath or strucutrual assesment on the culvert would revert to a SCG scenarrio. The risk range cannot be quantified at the moment. The effect is unknown. | [14 empty] | RSK - A96 | [7 empty] | 0 | 0
1 | HDD-MT | A97 | Jindalee SRM-19 Upgrade | Geotechnical - HDD Fract out | Frac out, tanker availability for works outside normal operating periods | Environmental impact, impact to community and stakeholders |  | Possible | Major | 6 | High | Specialised tunnelling experts. Safety in design mitigation. | [7 empty] | FH |  | Closed | Sharing of Lessons Learnt from UU from Bartley's Hill HDD & Jindalee Crossing MT. |  | 0 | No |  |  |  | Residual risk allowed elsewhere To be discussed with Bamser, discussion with Subcontractors on size of drilling rig intended for use and option of pipe reaming in two passes reducing the risk of 'frac out.' Areas identified for potential frac out have environmental controls | [11 empty] | RSK - A97 | [7 empty] | 0 | 0
1 | HDD-MT | A98 | Jindalee SRM-19 Upgrade | HDD getting stuck | Enountering unknown obstructions | Delay to project | [13 empty] | FH |  | Closed |  | SCG | 0 | No | SCG to be drafted. |  |  | TBC pending market methodologies/price. | [11 empty] | RSK - A98 | [7 empty] | 0 | 0
1 | HDD-MT | A99 | Jindalee SRM-19 Upgrade | Defects Liability Period - 2 yr. No O&M allowance - hydraulics / grit | [15 empty] | UU | Mitigate | Closed | UU Risk | SCG | 0 | No | N/A | [14 empty] | RSK - A99 | [7 empty] | 0 | 0
1 | HDD-MT | A100 | Jindalee SRM-19 Upgrade | Adverse Weather | Wet Season An extreme weather event would prevent some activities from being conducted at site. If the event occurs when civil works are underway the delay associated with this activity will be greater than for MEP works. An adverse weather event is as agreed on site between FH/Subbie and QUU and can consist of rain. Wind/heat | 1. labour unable to work 2. Lost time due to rectification of works 3. damage of materials and plant |  | Likely | Minor | 5 | Medium | 1. If possible relocate employees 2. look at short term weather forecast 3. protect work area were possible | Likely | Minor | 5 | Medium | 12 |  |  | FH | Accept/Retain | Open | Review the BOM data and understand the exposure and allow for in the RAMP direct costs. Allowance to be included in the RAMP risk above the BOM data. Contractor allowance is for FH staff. FH confirm standard position is Subcontract receive time but no cost. Cost incurred will be the increase in FH staff costs Risk of subbie negotiations PE welding condition risk covered A119. |  | #REF! | No |  | 12% | #REF! | Allowance for 20 days, no allowance in direct costs for flood management or mitigation. | #REF! | Allowance for 12 days delay to drilling, crew and management | #REF! | Allowance for 5 days | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A100 | #REF! | 30000 |  | 360000 | 30000 |  |  | #REF! | #REF! | 1.5 | 0.5
1 | HDD-MT | A101 | Jindalee SRM-19 Upgrade | Not suitable atmospheric humidity conditions | Refers specifically to welding of pipes on site | 1. Labour unable to perform the tasks 2. The right sequence of work on site is interrupted 3. Not considered on critical path |  | Likely | Minor | 4 | Medium | 1. Try to do work in advance 2. Allow for large storage area | Likely | Minor | 5 | Medium |  |  |  | FH | Accept/Retain | Closed | Allowed for 2 days interruptions for welding crew and plant Allowance for extra staff and plant Refer to above. |  | 0 | No |  |  | 0 | Allowance for 6 days, ambient temperature an humidity may not be suitable if large storage area used. Need to review internal debeading methodologies. | 0 | Allowance for 4 days (based on BOM data) | 0 | Allowance for 2 days | [7 empty] | RSK - A101 | [7 empty] | 0 | 0 |  | 0.75 | 0 | 0
1 | HDD-MT | A102 | Jindalee SRM-19 Upgrade | Drilling in Rock | A geotechnical report was done, however might be sections of the pipeline where rock is harder than anticipated. | 1. longer site duration by HDD/TB subcontractor 2. higher rates as extra over rates over 100 MPa 3. total project duration will be longer than anticipated as HDD/ TB is on critical path | Total site duration is anticipated to be of 72 days for HDD/ TB. Allow extra 15 days for HDD/ TB Allow for 15 days extra as PM and site facilities | Likely | Major | 12 | High | 1. Do further geotechnical investigation 2. Prepare for longer HDD/ TB durations | Likely | Major | 7 | High | 15 |  |  | FH | Mitigate | Open | Allowance for extra over rates and extra project management costs. Still investigating the current quotes and possible others. Ranges from 30 mpa to 60 mpa, extra over and rates TBC. |  | 0 | Yes |  | 0% | 1005000 | % of drilling in rock is included up to 100mpa - 150mpa If the same tooling can be used, time based durations are applied, tooling costs are referred under A27. Allowance for an additional duration of 25 days for extra over rate for rock over 100 mpa, Mitigated by othe works (50%) equates to 12.5 days | 804000 | % of drilling in rock is included up to 100mpa. If the same tooling can be used, time based durations are applied, tooling costs are referred under A27. Allowance for an additional duration of 20 days for extra over rate for rock over 100 mpa. Mitigated by othe works (50%) equates to 10 days | 603000 | % of drilling in rock is included up to 100mpa. If the same tooling can be used, time based durations are applied, tooling costs are referred under A27. Allowance for an additional duration of 15 days for extra over rate for rock over 100 mpa | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A102 | 504000 |  |  | 300000 |  |  | 10 | 0 | 804000 | 1.25 | 0.75 | 804000 | 0
1 | HDD-MT | A103 | Jindalee SRM-19 Upgrade | Digging holes for 1 valve pits, 2 starting pit and 1 exit pit (shallow) | A geotechnical report was done, however might be sections of the pipeline where rock is harder than anticipated. | 1. longer site duration for civil crews 2. total project duration will be longer than anticipated | Only allow 20 days extra for a Civil crew. No requirement for PM or site facilities increase as they are not on the critical path If total HDD solution taken, then pit risks will be reduced | Likely | Minor | 5 | Medium | 1. Do further geotechnical investigation 2. Prepare extra civil crews | Likely | Minor | 5 | Medium | 5 |  |  | FH | Mitigate | Open |  |  | 2122.4 | No |  | 10% | 33958.4 | Digging holes for 1 valve pits, 2 starting pit and 1 exit pit (shallow) Circa 70 m3 x $450 per m3 | 21224 | Digging holes for 1 valve pits, 2 starting pit and 1 exit pit (shallow) Circa 50 m3 x $450 per m3 | 15918 | Digging holes for 1 valve pits, 2 starting pit and 1 exit pit (shallow) Circa 35 m3 x $450 per m3 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A103 |  | 9096 |  |  | 12128 |  |  | 0 | 21224 | 1.6 | 0.75 | 23700.1333 | 2370.0133
1 |  | A104 | Jindalee SRM-19 Upgrade | Flow Control Coordination for the Cut Over and connections | At this point in time we only have approximate data regarding how the cut over connections and new pipeline arrangements should be done. Proper design inputs are required. | 1. possible longer site durations for labour, traffic controllers and tankers 2. some rework activities are possible | Allow for extra 5 days labour and traffic control. Allow for some extra tankerage for sludge | Likely | Minor | 5 | Medium | 1. Do further site investigation 2. Do proper design in relation to the pipe connections, pits and cut over activities that need to be done. 3. Investigate, optimise and plan with UU the best times to do the work. | Likely | Minor | 5 | Medium |  |  |  | FH | Mitigate | Closed | At this point in time the scope of works in relation to cut over activities is not precisely defined |  | 0 | Yes |  |  | 0 | Covered under A41 | 0 |  | 0 | [8 empty] | RSK - A104 | [7 empty] | 0 | 0 | 1.5 | 0.5 | 0 | 0
1 | HDD-MT | A105 | Jindalee SRM-19 Upgrade | Potential for 2 separate mobilisations. | Dependently of how fast the work needs to be done, we might need to employ 2 different subcontractors or 2 different crews from the same subcontractor. Also the is the possibility to use HDD for BOTH section | 1. There will be additional costs for two separate mobilisations. | Allow for 1 extra mobilisation Review upon the selected option | Likely | Minor | 5 | Medium | 1. Need to establish exactly what is the time allocated for doing this work 2. Need to know exactly if we are going to do only HDD or HDD + TB 3. Need to select the subcontractors that will perform the work | Likely | Minor | 5 | Medium |  |  |  | FH | Mitigate | Closed | One subcontractor all HDD |  | 0 | No |  |  | 0 | Allowance for 1 extra mobilisation | 0 |  | 0 | [8 empty] | RSK - A105 | [7 empty] | 0 | 0 | 1.5 | 0.75 | 0 | 0
1 | HDD-MT | A106 | Jindalee SRM-19 Upgrade | Pipe Handling and Welding - additonal area required due to methodology change | Residual risk is 5% contingency for another laydown / stringing area, pending on HDD methodology. | 1. Extra time on site for labour, pipe welder, NDT | Allow for extra 10 days Review based on selected option | Likely | Minor | 5 | Medium | 1. Need to have a reliable planning of all site activities 2. Need to have a better understanding of site durations for welding and NDT | Likely | Minor | 5 | Medium | 5 |  |  | FH | Mitigate | Open | The current estimate included for pipe handling and welding happening before each section of drilling. We might expect delays or interruptions of welding activities |  | 3175 | Yes |  | 5% | 101600 | Residual risk is 5% contingency for another laydown / stringing area, remove gear etc $100k | 63500 | Residual risk is 5% contingency for another laydown / stringing area, remove gear etc $60k | 50800 | Residual risk is 5% contingency for another laydown / stringing area, remove gear etc $40k | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A106 | 27500 | 10500 |  | 15000 | 10500 |  |  | 0 | 63500 | 1.6 | 0.8 | 71966.6667 | 3598.3333
1 |  | A107 | Jindalee SRM-19 Upgrade | Miscellaneous Pipe & Fittings, MSCL supply and install around the valve pits | At present we do not have the full design in relation to these items. | 1. Expect variations and addition to the current scope of works | Allow for extra supply and install | Likely | Minor | 5 | Medium | 1. Need to have proper design inputs, including detailed BOM and drawings | Likely | Minor | 5 | Medium |  |  |  | FH | Mitigate | Closed | Discussion with SMEC to take place on detailed drawings. Detailed BOM data to be finalised. Reducing lead times. |  | 0 | Yes |  |  | 0 | Risk included elsewhere | 0 |  | 0 | [8 empty] | RSK - A107 | [7 empty] | 0 | 0 | 2 | 0.75 | 0 | 0
1 |  | A109 | Jindalee SRM-19 Upgrade | Access to the work site | Access to the pump station, pits, valves, etc. (short and long term) not considered in the design | Increased cost, project delays |  | Likely | Minor | 5 | Medium | Maintain access pre physical construction activiites. | Likely | Minor | 5 | Medium | 1 |  |  | FH |  | Open |  |  | 23250 | No |  | 15% | 248000 | Disruption to FH works with necessary UU Maintenance works, planned connections etc. Wrap up with A57 | 155000 | Disruption to FH works with necessary UU Maintenance works, planned connections etc. | 77500 | Disruption to FH works with necessary UU Maintenance works, planned connections etc. | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A109 | 45000 | 45000 |  | 30000 | 35000 |  |  | 0 | 155000 | 1.6 | 0.5 | 160166.6667 | 24025
1 |  | A110 | Jindalee SRM-19 Upgrade | Overhead power lines and other services: - Sinnamon Rd connection (OH line) | Insufficient consideration during design to avoid clashes with above ground third party infrastructure | Increased cost, project delays | [15 empty] | Closed | Combine/Refer to A01 and A84? |  | 0 | Yes | Combine/Refer to A01 and A84? | [14 empty] | RSK - A110 | [7 empty] | 0 | 0
1 |  | A111 | Jindalee SRM-19 Upgrade | Working in excavated or confined spaces. | Working in trenches and other poorly ventilated confined spaces. | Hot works or grinding whilst undertaking live cut-ins in trenches where there is a high concentration of flammable or noxious gasses resulting in death or serious injury to personnel. |  | Likely | Catastrophic | 16 | Extreme | 1) Shut Plan to be received from QUU prior to any connections taking place, 2) Only authorised personnel. may operate valves 3) Shut plan to be implemented prior to any connection taking place 4) Confirmation to be relayed to FH that the main is off line and the connection may take place by way of gas blow out and confirmation. | Likely | Moderate | 6 | High |  |  |  | FH | Mitigate | Closed | Additional gas monitoring costs. |  | 0 | No |  |  |  | Refer risk item A69 | [11 empty] | RSK - A111 | [7 empty] | 0 | 0
1 |  | A112 | Jindalee SRM-19 Upgrade | Tunnelling below existing rising main (southern connection) | Insufficient cover provided to the existing rising main | Overhead pipework leaking and/or breaking resulting in injury, infection and/or engulfment. | [13 empty] | FH |  | Closed | TBC Pending methodology. |  | 0 | Yes | Refer risk item x | [14 empty] | RSK - A112 | [7 empty] | 0 | 0
1 | HDD-MT | A113 | Jindalee SRM-19 Upgrade | Working with live pressure mains (water, sewer or gas) | Insufficient cover / clearance to live services. Mechanical excavation above or adjacent to pipework | Hazards resulting from contact and breakage of the pipe wall | [13 empty] | FH |  | Closed | TBC Pending methodology on the proximities of existing infrastructure. |  | 0 | Both | Refer risk item x | [14 empty] | RSK - A113 | [7 empty] | 0 | 0
1 |  | A114 | Jindalee SRM-19 Upgrade | Rushing of works due to condition of existing sewer rising main | - Pressure on Contractor and Designer to complete construction or submit design due to urgent repair or relocation works required - Contractor or subcontractor experience in type of works, particularly under emergency conditions | Harm to the contracting team or others resulting from missed elements (design and construction) when accelerating program of works due to delays | [13 empty] | FH |  | Closed | Combine/Refer to A09 and A82? |  | 0 | Both | Combine/Refer to A09 and A82? | [14 empty] | RSK - A114 | [7 empty] | 0 | 0
1 |  | A115 | Jindalee SRM-19 Upgrade | Lifting and Handling Equipment and Structures (Incl. Suspended Loads) | Failure of lifting devices, weight underestimated, poor planning, no exclusion zones, instability of elements during lifting and erection of elements, operator error, lack of communication etc. Lifting of boring machine into shafts | Impact of suspended load with by standing personnel whilst constructing and removing, demolishing and/or transferring the load resulting in serious injury. | [13 empty] | FH |  | Closed |  |  | 0 | Yes | No quantum risk | [14 empty] | RSK - A115 | [7 empty] | 0 | 0
1 | HDD-MT | A116 | Jindalee SRM-19 Upgrade | Pipe stringing for HDD | Lack of room available for pipe stringing of the HDD drive | Pipework intruding on public spaces outside of the nominated laydown area | [13 empty] | FH |  | Closed | Bamser/FH to review stringing methodology. |  | 0 | Yes | Refer risk item x | [14 empty] | RSK - A116 | [7 empty] | 0 | 0
1 |  | A117 | Jindalee SRM-19 Upgrade | Golf balls | - Golf club open during construction. - Construction barriers do not sufficiently protect workers from golf balls. - Access to site crosses two fairways. - No hard hats worn. | Personnel hit by golf ball during construction leading to injury. | [13 empty] | FH |  | Closed | Combine/Refer to A37 and A20? |  | 0 | No | BAU, No quantum risk | [14 empty] | RSK - A117 | [7 empty] | 0 | 0
1 |  | A118 | Jindalee SRM-19 Upgrade | 24hr working (drilling, etc.) | 24hr drilling activities leading to fatigue in operators | Injury and/or environmental impacts |  | Possible | Minor | 6 | Medium | FH management is to monitor and control upper limit on hours worked in a month. Implement additional breaks throughout the day particularly when hot. Job rotation. | Unlikely | Minor | 3 | Low | 2 |  |  | FH |  | Open | Subcontractor Fatigue management plan to be reviewed, if not specific to be incorporated into Project Management Plan/SWMS |  | 7500 | Yes | Risk management of fatigue in direct costs, the occurencne of an event of a serious accident (5 days) if deemed due to fatigued | 5% | 300000 | Risk management of fatigue in direct costs, the occurence of an event of a serious accident (10 days) if deemed due to fatigued | 150000 | Risk management of fatigue in direct costs, the occurence of an event of a serious accident (5 days) if deemed due to fatigued | 90000 | Risk management of fatigue in direct costs, the occurence of an event of a serious accident (3 days) if deemed due to fatigued | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | RSK - A118 |  |  |  | 150000 |  |  |  | 0 | 150000 | 2 | 0.6 | 180000 | 9000
1 | HDD-MT | A119 | Jindalee SRM-19 Upgrade | Leaking joint mid-span | Failure of a joint during trenchless installation | Environmental impacts |  | Possible | Major | 12 | High | 1) Quality standards to go 'over and above' the standard practice. 2) Ensue the best selection of pipe material 3) Ultrasonic testing of every test weld 4) Pre installation pressure test. 5) Nova Sirus encapsulated fitting for any exposed/golden weld to be reviewed by Designers. | Unlikely | Minor | 3 | Low |  |  |  | FH |  | Closed |  |  | 0 | Yes | Refer risk item x | [14 empty] | RSK - A119 | [7 empty] | 0 | 0
1 | HDD-MT | A120 | Jindalee SRM-19 Upgrade | Inappropriate traffic loads on new pipes in ground | Other construction in area (e.g. when removing old pipeline) | Design checked to ensure minimum cover requirements are complied with. Ensure DBYD is updated and GIS is updated with latest information. Ensure pipe designed for expected vehicular loads in operation. | [13 empty] | FH |  | Closed |  |  | 0 | Yes | Residual risk is Subcontractors, Quantum risk for FH, | [14 empty] | RSK - A120 | [7 empty] | 0 | 0
1 |  | A121 | Jindalee SRM-19 Upgrade | Remaining section of rising main (beyond downstream connection) | Failure of the existing rising main after works completed | Benefit can be provided by providing allowance for a future connection | [13 empty] | UU |  | Closed |  | SCG | 0 | No | Not in Project scope (boundary limits) Recommend SCG if required. 3.1 General Assumptions on QUU owned items a) Shutdown costs – QUU operational costs associated with each shutdown for the purpose of the Contractor completing a cut in are not included in the RAMPs. | [14 empty] | RSK - A121 | [7 empty] | 0 | 0
1 |  | A122 | Jindalee SRM-19 Upgrade | 1) Soil Samples testing hasn’t been undertaken – risk that HDD contractor may request (check - as this might be covered by the info/ requests that have come through from the contractors recently) Did we not ‘locate/receive’ the soil samples (OTR) that BCC took? What testing should have been / was carried out? Do we believe that OTR samples are of significance to HDD? or MT solutions (more relevant?) or both? | [17 empty] | Closed |  |  | 0 | [16 empty] | RSK - A122 | [7 empty] | 0 | 0
1 |  | A123 | Jindalee SRM-19 Upgrade | 2) LIDAR survey used for part of the surface profile (CM in Drive2) However this may be negated by the depth if HDD Proposal goes deep but dependant on final option (HDD/MT) Worth adding to the list, maybe of most significance to MT if selected solution (Drive 2 under Jindalee Creek section) | [15 empty] | FH |  | Closed |  |  | 0 | Yes |  |  |  | Direct costs has allowed this. | [11 empty] | RSK - A123 | [7 empty] | 0 | 0
1 |  | A124 | Jindalee SRM-19 Upgrade | 3) Air Management - Additional operational or maintenance requirements may be required by United Utilities networks operations – FHU Scope does not cover for the networks operational hydraulics and management so there may be a risk, that when air movement/ grit movement analysis is carried out a request may be made by Urban Utilities to include automatic air valves (AAVs) or a pigging station to facilitate operation/ maintenance – FHU/SMEC have advised AAVs could be added at a later date but Urban Utilities may request FHU to include in RAMP. RFI No: BWWCAA03A54-FHU-RFI-000001…….Has been raised and issued for action under WWMP-TB , and requested for Resolution before RAMP submission. If not resolved then this should be defined as an SCG covering (any) additional UU Approval, Design, Construction , Commissioning and Handover inputs and costs. | [15 empty] | UU |  | Closed |  | SCG | 0 | No |  |  |  | $50k for the costs of the equipment | [11 empty] | RSK - A124 | [7 empty] | 0 | 0
1 |  | A125 | Jindalee SRM-19 Upgrade | Tooling loss downhole | Inappropriate downhole tolling used. 2nd hand tolling not inspected properly | Unable to recover tooling from borehole and have to redrill borehole on new alignment. Dealys and Cost | [5 empty] | Ensure appropriately experienced contractor and methodology addresses this risk. Avoid higher risk methodologies such as Forward reaming | [12 empty] | 0 |  |  |  |  | Subcontractor risk, if tooling chnages refer Risk item A27 | [11 empty] | RSK - A125 | [7 empty] | 0 | 0
1 |  | A126 | Jindalee SRM-19 Upgrade | Loss of drilled borehole/deviation in alignment | Tail string not utilised during reaming | Design profile not maintained, potential loss of borehole. Dealys and extra cost | [5 empty] | Ensure appropriately expereinced contractor and methodology addresses this risk | [12 empty] | 0 | [16 empty] | RSK - A126 | [7 empty] | 0 | 0
1 |  | A127 | Jindalee SRM-19 Upgrade | Borehole collapse at entry or exit in OTR material | Unstable formation leads to collapse | Drilling fluid fracout (environmental), damage to Sinnamon road, Delays to redrill, Cost to install casing | [5 empty] | Ensure contractor has allowed for utilisation of temporary casing (Both Pilot and Full diamater) if required. | [12 empty] | 0 | [16 empty] | RSK - A127 | [7 empty] | 0 | 0
1 |  | A128 | Jindalee SRM-19 Upgrade | Unable to stabilise borehole collapse at entry | Cannot obtain appropriate temporary steel casing or have equipment to install | Delay to project | [5 empty] | Ensure address in contractors methodology annd have contingency in place to manage | [12 empty] | 0 |  |  |  |  | 40k allowed for this (bring back entry Pit) | [11 empty] | RSK - A128 | [7 empty] | 0 | 0
1 |  | A129 | Jindalee SRM-19 Upgrade | Pipe gets stuck in Borehole during Pullback | Multiple Pipe Strings, delay in Pullback operation while welding performed. | Loss of Borehole, Redrill Delay to completion. Possible loss of pipe need to purchase new pipe | [5 empty] | As borehole in both instances majority rock this is low. Risk to be put back to subcontractor. | [12 empty] | 0 | [24 empty] | 0 | 0
1 |  | A130 | Jindalee SRM-19 Upgrade | Drill string gets stuck down hole | Hydrolock due to extended stoppages | Unable to remove string string. Loss of drill string. Have to redrill borehole Time and Cost | [5 empty] | Due to rock should be a low risk and if casing used even lower. Cost borne by contractor however could cause substantial delay | [12 empty] | 0 | [29 empty] | 0
1 |  | A131 | Jindalee SRM-19 Upgrade | Major equipment breakdown | Inadequate servicing or preventative Maintenance | Delay to project | [5 empty] | Ideally engage contractor with multiple drill rigs or ensure contingency plan in place. Adequate critical parts available. Address with contrcatoir prior to works | [12 empty] | 0 | [29 empty] | 0
1 |  | A132 | Jindalee SRM-19 Upgrade | Thrust restraint fails | Not designed appropriately for pull loads | Potential pipe getting stuck during pullback. Delay and cost | [5 empty] | Ensure design basis appropriate (i.e. take into account rig capacity and geology)and reviewed during design | [12 empty] | 0 | [29 empty] | 0
1 |  | A133 | Jindalee SRM-19 Upgrade | Unable to Ballast pipe appropriately | Procedure for introduction of water not adequate | Potential pipe getting stuck during pullback. Delay and cost | [5 empty] | Ensure contractor methodology reviewed. | [12 empty] | 0 | [29 empty] | 0
1 |  | A134 | Jindalee SRM-19 Upgrade | Continual loss of fluid to formation | Large voids or fractures in formation or gravel layers | Unable to maintain fluid return hence issuse with borehiole stability, lubrication.Possible abandon ment of Bore Potential delays/cost | [5 empty] | This is a low risk and impacts are high. If contractor has to continually mix new fluid significant cost impact | [12 empty] | 0 | [29 empty] | 0
1 |  | A135 | Jindalee SRM-19 Upgrade | Encountering differing geology | Indicated Profile for HDD2 goes below current borehole depths | Cost and delays | [5 empty] | Perform additional geotech or get contractor to accept risk upto 100Mpa | [12 empty] | 0 | [29 empty] | 0
1 |  | A136 | Jindalee SRM-19 Upgrade | Unidentified Risk - Due to emergency nature of this project. | Changes that have not been identified due to the urgent nature of this project. This is also supported by Expert trenchless advisor report suggesting additional risks that has not been captured. The residual risk and proposed probability is as low as 10% to reflect the detailed risk register and associated inputs to date. | Cost and delays | [13 empty] | FH |  | Open | Unidentified Risk - Contractors risk if not identified |  | 0 | No | [23 empty] | 0 | 0 | 1.8 | 0.5
1 |  | A137 | Jindalee SRM-19 Upgrade | Bamser Risk - Due to emergency nature of this project and type of Methodology. | Historical Data suggests and as provided by Bamser proves this type of work is a high risk project, | Significant Cost and delays | [13 empty] | FH |  | Open |  |  | 375000 | No |  | 10% | 6750000 | Value of project x 30%, propose Scope change guideline in lieu of contract clause to provide transparent unidentified risks | 3750000 | Value of project x 10% | 1875000 |  | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  |  | 3750000 | [6 empty] | 0 | 3750000 | 1.8 | 0.5 | 4125000 | 412500
1 | [54 empty] | 0
0
Note on BD2: KOTHARI, Kunal: No Mark-up on Risk items
Note on AW3: KOTHARI, Kunal: confirmed costs from sub-contractors (in writing)
Note on AX3: KOTHARI, Kunal: confirmed costs from sub-contractors (in writing)
Note on AY3: KOTHARI, Kunal: Design Team to price each scenario
Note on AZ3: KOTHARI, Kunal: If additional resource required for couple of days, if he time impact is going to delay the project
Note on BA3: KOTHARI, Kunal: P&E costs if additional or longer duration
Note on BB3: KOTHARI, Kunal: KOTHARI, Kunal: Normally covered for each work package. Items with significant schedule impact to be reviewed on case by case basis. Include Site facilities and running costs if PMO allowed.
Note on BC3: KOTHARI, Kunal: in Weeks
Note on BG3: KOTHARI, Kunal:
Note on BH3: KOTHARI, Kunal:
Note on AC10: KEHOE, Mark: BOM exercise to confirm %
Note on BA10: KEHOE, Mark: Access Road repair
Note on AC13: KEHOE, Mark: Consolidated against A40
Note on AW20: KEHOE, Mark: Gap in Lds vs loss, 330k vs 600k cost of FHU
Note on AC30: KEHOE, Mark: 1 in 5, nature of trenchless
Note on AW37: KEHOE, Mark: $30 per meter x 250 linear meters + RPEQ
Note on AW97: KEHOE, Mark: 1200lm x 1,500 per linear meter
Note on AC103: KEHOE, Mark: BOM Mt Cootha histroical data
Note on AX104: KEHOE, Mark: Labour and Plant for welding only.
Note on AW105: KEHOE, Mark: Based on SMEC's Geotech report circa 400 meters
Note on AZ105: KEHOE, Mark: Mitigate 50%
Note on AW109: KEHOE, Mark: Materials
Note on AW120: KEHOE, Mark: Subcontractor risks not applied

## Risk Rating Table
Consequence | Likelihood |  |  |  |  | Likelihood | Timeframe | Description
| Rare (1) | Unlikely (2) | Possible (3) | Likely (4) | Almost Certain (5) | 5 |  | There is likely to be an event at least once a year or frequently.
[6 empty] | Almost Certain | < 1 year | The event:
Catastrophic (5) | Medium | High | High | Extreme | Extreme |  |  | · has a high number and regularity of recorded events and /or stong anecdotal evidence of events and would be expected to occur again.
| 5 | 10 | 15 | 20 | 25 |  |  | · occurs with regularity, e.g. monthly, every summer, every time it rains heavily.
Major (4) | Medium | Medium | High | High | Extreme |  |  | · occurs with predictability, e.g. at the time of the commencement of a particular operation or combination of conditions.
| 4 | 8 | 12 | 16 | 20 | 4 | 1 year | There is likely to be an event on average every 1 to 3 years.
Moderate (3) | Low | Medium | Medium | High | High | Likely | to | The event:
| 3 | 6 | 9 | 12 | 15 |  | < 3 years | · has regular record of events occuring and /or stong anecdotal evidence of events and would be expected to occur again in most circumstances.
Minor (2) | Low | Low | Medium | Medium | High |  |  | · occurs with some annual regularity e.g. in a particular season, end of year.
| 2 | 4 | 6 | 8 | 10 |  |  | · will occur under most circumstances or scenarios.
Insignificant (1) | Low | Low | Low | Medium | Medium | 3 | > 3 years | There is likely to be an event on average every 3 to 10 years.
| 1 | 2 | 3 | 4 | 5 | Possible | to | The event:
[7 empty] | < 10 years | · has irregular, random, recorded history of events and /or limited anecdotal evidence of events and is likely to occur in narrow or limited range circumstances
· occurs in a narrow or limited range of circumstances or scenarios.
[6 empty] | 2 | > 10 years | It is possible there will be an event every 10 to 50 years.
[6 empty] | Unlikely | to | The event:
[7 empty] | < 50 years | · Limited history of event occurring or limited anecdotal evidence of events and would be expected to occur under specific circumstances.
· may have occurred previously.
· would occur under specific circumstances or scenarios e.g. cyclone or storm surge, external accident.
[6 empty] | 1 |  | It is theoretically possible there will be an event occurring no more than once every 50 years on average.
[6 empty] | Rare | > 50 years | The event:
· no recorded history of events and /or very limited or no anecdotal evidence of events and would only be expected to occur under specific circumstances.
· may not have occurred previously but is a possibility.
· would only occur under specific circumstances or scenarios e.g. cyclone or storm surge, external accident.
Appendix C Consequence Descriptors (normalised for SID) Extracted from PRO84 Section 8 Risk Criteria, for Safety in Design application
[7 empty] | Health & Safety Employees, contractors & public are impacted in terms of injury, illness | Environment Further guidance on consequence ratings of environmental impacts, please see Environmental Aspects and impacts Guide (PRO249) | Financial Performance Financial losses or unplanned expenditure is incurred by QUU
[6 empty] | Catastrophic | Fatality and/or amputation of a limb/appendage. Long term/terminal illness resulting in a lost time injury greater than 1 month Permanent disability. | Long term (>5 years) impact to the natural environment; and Widespread impact and public concern. There is a duty to notify the Regulator of this event. | >50% of project budget
[6 empty] | Major | Serious/hospitalisation injury resulting in a lost time injury greater than 2 days Long term disability. | Medium to long-term (1-5 years) impact to the natural environment; and localised (catchment or suburb) impact and a high level of public concern. There is a duty to notify the Regulator of this event. | >30% to ≤50% of project budget
[6 empty] | Moderate | Illness < 4 days resulting in a lost time injury of 1 to 2 days. Near miss relating to high risk activity. Short term disability / suitable duties injuries Medical Treatment Injury | Temporary (1 month to 1 year) impact to the natural environment; and Controlled site impact with a moderate level of public concern. There is a duty to notify the Regulator of this event. | >20% to ≤30% of project budget
[6 empty] | Minor | First Aid Near miss relating to non-high risk activities, including manual handing near miss Short term illness | Transient (< 1month) impact to the natural environment; and Controlled site, single local impact with low level of public concern. There is a duty to notify the Regulator of this event. | >10% to ≤20% of project budget
[6 empty] | Insignificant | Other Near miss events. | No impact or potential impact. No public concern. No offence. There is no duty to notify the Regulator of this event. | <10% of project budget

## Pick Lists
Status | Likelihood | Consequence | Risk Rating | Action | Likelihood | Consequence | Combined Likelihood & Consequence | Score | Rating | Rating Picklist
Open | Rare | Insignificant | Low | Accept/Retain | Rare | Catastrophic | RareCatastrophic | 6 | High | Low
Closed | Unlikely | Minor | Medium | Avoid | Rare | Major | RareMajor | 4 | Medium | Medium
Realised | Possible | Moderate | High | Mitigate | Rare | Moderate | RareModerate | 3 | Low | High
| Likely | Major | Extreme | Monitor/Review | Rare | Minor | RareMinor | 2 | Low | Extreme
| Almost Certain | Catastrophic |  | Share | Rare | Insignificant | RareInsignificant | 1 | Low
|  |  |  | Transfer | Unlikely | Catastrophic | UnlikelyCatastrophic | 7 | High
[5 empty] | Unlikely | Major | UnlikelyMajor | 5 | Medium
[5 empty] | Unlikely | Moderate | UnlikelyModerate | 4 | Medium
[5 empty] | Unlikely | Minor | UnlikelyMinor | 3 | Low
Project | Owner |  |  |  | Unlikely | Insignificant | UnlikelyInsignificant | 2 | Low
Jindalee SRM-19 Upgrade | FH |  |  |  | Possible | Catastrophic | PossibleCatastrophic | 8 | Extreme
| UU |  |  |  | Possible | Major | PossibleMajor | 6 | High
| Customer |  |  |  | Possible | Moderate | PossibleModerate | 5 | Medium
| Customer |  |  |  | Possible | Minor | PossibleMinor | 4 | Medium
[5 empty] | Possible | Insignificant | PossibleInsignificant | 3 | Low
[5 empty] | Likely | Catastrophic | LikelyCatastrophic | 9 | Extreme
[5 empty] | Likely | Major | LikelyMajor | 7 | High
[5 empty] | Likely | Moderate | LikelyModerate | 6 | High
[5 empty] | Likely | Minor | LikelyMinor | 5 | Medium
[5 empty] | Likely | Insignificant | LikelyInsignificant | 4 | Medium
[5 empty] | Almost Certain | Catastrophic | Almost CertainCatastrophic | 10 | Extreme
[5 empty] | Almost Certain | Major | Almost CertainMajor | 8 | Extreme
[5 empty] | Almost Certain | Moderate | Almost CertainModerate | 7 | High
[5 empty] | Almost Certain | Minor | Almost CertainMinor | 6 | High
[5 empty] | Almost Certain | Insignificant | Almost CertainInsignificant | 5 | Medium
913.6
4568

## Output AF2 (hidden)
@RISK Output Report for Result AF2
Performed By:
Date:
Simulation Summary Information
Summary Statistics for Result
| Statistics |  | Percentile
| Minimum |  | 5%
| Maximum |  | 10%
| Mean |  | 15%
| Std Dev |  | 20%
| Variance |  | 25%
| Skewness |  | 30%
| Kurtosis |  | 35%
| Median |  | 40%
| Mode |  | 45%
| Left X |  | 50%
| Left P |  | 55%
| Right X |  | 60%
| Right P |  | 65%
| Diff X |  | 70%
| Diff P |  | 75%
| #Errors |  | 80%
| Filter Min |  | 85%
| Filter Max |  | 90%
| #Filtered |  | 95%
Change in Output Statistic for Result
| Rank | Name | Lower | Upper
1
2
3
4
5
6
7
8
9
10

## RiskSerializationData (hidden)
1 | 0
0
#NAME? | TRUE | 0 | 1 | GF1_rK0qDwEAEADxAAwjACYAYwBvAIMAhACnALUAywDtAOcAKgD//wAAAAAAAQQAAAAAL18oKiAjLCMjMC4wMF8pO18oKiAoIywjIzAuMDApO18oKiAiLSI/P18pO18oQF8pAAAAAQZSZXN1bHQBAAEBEAACAAEKU3RhdGlzdGljcwMBAQD/AQEBAQEAAQAAAAAAgIQuwQAAAABovlVBAQUA6wMBAAQAAAABAQEBAQABAQEABAAAAAG5AAIOAAZSZXN1bHQAAC8BAAIAAgDTAN0AAQECAZqZmZmZmak/AABmZmZmZmbuPwAABQABAQEAAQEBAA== | 1 | 0 | 0 | >75% | <25% | >90% | #NAME? | 1 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
0
FALSE | 15680 | 7345 | 3520 | 0
FALSE | 15680 | 7345 | 3520 | 0
FALSE | 15680 | 7345 | 3520 | 0
FALSE | 15680 | 7345 | 3520 | 0
FALSE | 15680 | 7345 | 3520 | 0
0
0 | FALSE | FALSE | 10 | 0.95 | 1