Material Inspection Checklist

| Inspected by: | Lucy Muston |
| --- | --- |
| Date: | Dates as per date delivered below. |

| # | Material | Date delivered | Quantity | Quality | Comment |
| --- | --- | --- | --- | --- | --- |
|  | Machinery fuel & consumables | 17/05/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Fuel and consumables delivered on time and in required quantities. Quality check confirmed compliance with specifications. Adequate buffer stock available to prevent disruptions to machinery operation. |
|  | Soil testing services booked | 30/05/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Soil testing conducted as scheduled. Results received and classification confirmed. No issues identified affecting project requirements. |
|  | Trucks for material export | 01/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Trucks arrived as scheduled on 01/07/2024. Capacity and condition checked meeting project requirements. No delays anticipated for material export. |
|  | Pipes, pits, and manhole materials |  | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | All materials delivered as scheduled. Checked for damage and compliance with specifications. No issues reported. |
|  | Bedding material (gravel, sand) | 26/05/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Early delivery received to allow for site preparation. Material quantity and quality verified; meeting required standards. |
|  | Backfill material (crusher dust, compacted fill) | Ongoing deliveries as needed | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Deliveries scheduled in batches based on progress. First batch received 27/05/2024, with subsequent deliveries aligned with work sequence. |
|  | Hydraulic pipework, fittings, valves | 27/05/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | All components delivered on time. Inspection confirmed correct sizes and specifications. No defects noted. |
|  | Bedding material (sand, aggregate) | 26/05/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Arrived a day early to facilitate preparation. Material quality checked meeting grading requirements. |
|  | Concrete cutting tools & supplies | 28/05/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | All tools and supplies received before the scheduled start date. Equipment tested and ready for use. |
|  | Reinforcement steel & formwork | 07/06/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Delivery received on time. Steel checked for correct grade and dimensions. Formwork inspected for defects, all in good condition. |
|  | Concrete for piers | As per pour sequence (First pour on 10/06/2024) | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Concrete delivery scheduled in line with construction progress. Slump test and quality checks to be performed before each pour. |
|  | Damp Proof Membrane & Reinforcement Mesh | 14/06/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Both the damp proof membrane and reinforcement mesh have been successfully delivered. The materials are on-site and ready for installation. Ensure proper storage and protection from the weather until installation. |
|  | Concrete Supply | As per pour plan (scheduled with bulk earthworks) | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | The concrete has been delivered as per the pour plan. Confirm that all preparations are complete and ready for the pour. Check the quality and quantity of the concrete to ensure it meets specifications before proceeding. |
|  | Blocks & Mortar | 28/06/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | The blocks and mortar have been delivered as scheduled. Ensure all materials are stored properly to avoid damage from weather or exposure. Ready for use in the construction of the blockwork and engaged piers. |
|  | Corefill Concrete | As per pour dates (scheduled) | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Corefill concrete is scheduled for delivery according to the pour dates. Verify the delivery timing to ensure alignment with the pour schedule and confirm material readiness for placement. |
|  | Steel Beams, Rafters, Bracing | 08/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | The steel beams, rafters, and bracing have been delivered as scheduled. Ensure they are inspected for quality and stored in a safe location to avoid damage. Ready for installation according to the project timeline. |
|  | Purlins & Outriggers | 08/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Purlins and outriggers have arrived as planned. Confirm that the materials are ready for use and stored properly until installation begins. |
|  | Roofing Sheets & Insulation | 22/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Roofing sheets and insulation have been delivered. Ensure proper handling and storage to protect from weather and physical damage. Ready for installation according to the roof framing schedule. (Alternative roofing material as per variation) |
|  | Louvers & Door Frames | 23/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Louvers and door frames have been delivered as scheduled. Inspect the materials for any damage and ensure they are stored safely and securely until installation. Ready for fitting into the external façade. |
|  | Door Hardware | 23/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Door hardware updated as per revised construction drawings. All components delivered in correct quantities and specifications. Installation to proceed as scheduled. |
|  | Hose taps and fittings | 23/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Hose taps and fittings have been delivered as scheduled. Inspect all components to ensure they are complete and undamaged. Store securely in a dry area until installation begins. |
|  | Electrical conduits and cables | 23/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Electrical conduits and cables have been delivered as scheduled. Inspect for any damage and confirm quantities match the requirements. Store in a secure and dry area until installation begins. |
|  | DB-XX, Emergency Lighting & Accessories | 22/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Distribution board (DB-XX), emergency lighting, and accessories have arrived on time. Verify all components are accounted for and in good condition. Ensure proper storage to prevent damage before fit-off. |
|  | Lockers (supplied by client) | 19/08/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Lockers are to be delivered before the specified date to allow for installation as per schedule. Coordinate with the client to confirm delivery timing and inspect upon arrival to ensure all units are complete and undamaged. Store securely until installation begins. |
|  | Base Course & Concrete for Footpaths | 29/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Base course material and concrete have been delivered as scheduled. Ensure proper storage and handling to maintain material integrity. Ready for use in footpath construction. |
|  | 750mm Rock for Protection Channel | 29/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Rock for the protection channel has arrived on time. Confirm the required quantity and proper placement for installation. |
|  | Topsoil, Turf & Landscaping Materials | 30/07/2024 | Met agreed amount. Agreed amount not met. Enough buffer | Met agreed: Dimensions Colour Weight | Landscaping materials, including topsoil and turf, have been delivered as planned. Store appropriately to prevent contamination or drying out before installation. Ensure coordination with the landscaping team for timely placement. |