Assessment Workbook 5

Assessment Workbook 5

BSB51415 Diploma

of Project Management

Integration Management

Version 1.01 Produced 18 October 2018

Copyright © 2020 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following assessment validation. | 1.0 |
| 18 October 2018 | Version 1.01 Change to Practical Assessment | 1.01 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Case Study	5

Instructions to Student	5

Introduction	6

Workbook Checklist	17

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 5 |  |  |
| --- | --- | --- | --- |
| TITLE: | Integration Management |  |  |
| FIRST AND SURNAME: | BRYDON HOGARTH |  |  |
| PHONE: | 0432738800 |  |  |
| EMAIL: | hogarthbrydon@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Brydon Hogarth |  | Signature: Brydon Hogarth | Date: 03/06/20 |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant advisor to the project team at Awesome Landscapes Pty Ltd. Specifically you are required to provide independent advice on seeing their current project through the entire life cycle. You have already provided advice to them in the previous four workbooks. The project manager has advised the project is now complete, and is about to archive all the project documentation. Your task is to evaluate the supplied project documentation and to ensure all due diligence has been completed. You will need to compare the project plan with the previous version to ensure it is ready for closure. Project Charter version 4 (.pdf) Project Plan version 4 (.pdf) Project Gantt Chart version 4 (.mpp) Project Gantt Chart version 4 (.pdf) Project Network Diagram version 4 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- Sam has asked to you check the Project Plan for anything that is missing. He has been very busy but appears to have done all the necessary finalisation of the plan ready for sign off. He has mentioned the final report or lessons learnt documentation has not been included, and the project archiving checklist have not been completed either. You will be assigned to complete these later. Examine the Project Charter (version 4) and Project Plan (version 4) and identify four (4) things that are missing. Guidance: - Assume the Project Gantt Chart and the financial figures in the summary/detailed costing tables are up to date as these have already been audited. Also remember this final project plan is in draft, and will not be signed off until the final acceptance meeting in a few days’ time. - Take note of the following: - Version control. - The updates from the project in the other workbooks you have completed in previous workbooks. - Check the project archiving checklist for everything that should be included

- Project plan is not shown as final version - Issue register not updatated - Cashflow not updated - Final audit not completed

- Sam is in the process of developing a set of Lessons Learnt Documentation for the project. - Access and review the four (4) previous workbooks you have completed and derive three (3) different lessons learnt throughout the project. - Document each lessons learnt using the Lessons Learnt Documentation Template provided. Use one template for each lessons learnt.

| Lessons Learnt Documentation Template 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Brydon Hogarth |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 14/4/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 001 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Site work group |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PMBOK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Information being poorly relayed to site team. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | inproductive work group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Understanding each team members role and specific duty |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Prestart meeting, with clear delagation of tasks and a clear line of communication to express any issues. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Without specific procedure in place site communication can break down. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensuring daily prestarts are documented and signed off by all team members to maintain site communication. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Open and clear dialouge between site team and prroject manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communication to site team can continue even after project has been finalised and prestarts implemented from the start of the next project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Brydon Hogarth |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 14/4/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 002 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Ensure employees are job ready |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Project team |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PMBOK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Poor computer knowledge and skills by site supervisor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Reporting and communication between project admin site team suffered |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Site supervisor having the nessarcary skills required for his position |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Prior identification and reticification of skills |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensuring site team is trained and prepared for required tasks. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| During interviewing the risk could be identified |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training and upskilling provided and easily unattainable |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Issues has resolved for this project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalets |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Brydon Hogarth |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 14/04/2017 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 003 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Conflict of intrest |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | Project team |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PMBOK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurrment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | A contractor was engaged that had prior bad history with a stakeholder |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Contract was terminated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Contract fufilled and with no conflict |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | A differnet contractor engaged |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Background checks during procurremnet are required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Informing all stakeholders of preferred contractors before engaging |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementing procedures to inform all parties and have them sign off |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Issue is resolved on tis project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Sam has asked you to write the final report for the project. Complete the final report using the template below, assuming the things missing from the project plan in the question above have been included. Guidance: - Access and carefully review the project documentation you were provided with along with the case study scenario and populate all the fields with the required information. - Provide a date that is later than the last date in the Project Gantt Chart version 4. - Assume that this report will be submitted to Terrence Mackay, Stephen Lyons, Kate Chan, and Kim Nguyen. - Provide a brief summary of the project in terms of the four project constraints (Scope, Cost, Time, and Quality). - Provide a detailed summary of the project covering the functions of project management listed below. Further guidance is provided for you within the template.

| Project Name: | Cascade Peak Chalets |  |  |
| --- | --- | --- | --- |
| Prepared by: | Brydon Hogarth |  |  |
| Date: | 14/04/2017 |  |  |
| Project Summary |  |  |  |
| Scope (What was included and excluded) |  |  |  |
| Inclusions: Provide project management, Vegetation removal, Contruct access road, Build retaining wall, excavte services and septic, mainatin plants, divert stream, convert roads to paths, erect signs and detailed landscaping. |  |  |  |
| Exclusions Delivery of any good related to construction of chalets, Supply of incoming services and any scope not coverd by council plans. |  |  |  |
| Cost (Budget vs. actual) |  |  |  |
| $444 253.00 vs $ 514 892.00 |  |  |  |
| Time (Estimate vs. Actual) |  |  |  |
| 03/08/2016- 08/03/2017 vs 27/07/2016 -13/04/2017 |  |  |  |
| Project Report Submitted to: |  |  |  |
| Name: Kim Nguyen |  | Title: Director - Awesome Landscapes | Date: 14.04.2017 |
| Name: Terrence Mackay |  | Title: General Manager - Cascade Peak Hotels | Date: 14.04.2017 |
| Name: Stpehen Lyons |  | Title: Planning Manager - Cascade Peak Council | Date: 14.04.2017 |
| Name: Kate Chan |  | Title: Project Manager - Timber Home Construction | Date: 14.04.2017 |
| Analysis of Project Guidance: - Process Review - Describe all of the processes used during the planning, implementation and closure stages. - Lessons Learnt - Describe what went right and or what went wrong and how effective were the management and the processes you used. If necessary, state how you overcame any problems. - Recommendations – Make recommendations as a result of the lessons learned. |  |  |  |
| Scope |  |  |  |
| Process Review Change process |  |  |  |
| Lessons Learnt Change process must be accurate and kept up to date to avoid extra works being added without knowledge of project manager. |  |  |  |
| Recommendations Regular reporting to monitor and watch for scope creep |  |  |  |
| Time |  |  |  |
| Process Review Maintain task completion on schedule |  |  |  |
| Lessons Learnt Change in project sponsor meant a large delay to completion of project |  |  |  |
| Recommendations Update project timeline to ensure all tasks are still achievable in new timeframes. |  |  |  |
| Cost |  |  |  |
| Process Review Scheduling a Payment of invoices |  |  |  |
| Lessons Learnt Cost management plan was not set out according to payment schedule leading to low cashflow for the entire project. |  |  |  |
| Recommendations Ensure invoicing is corresponding with cashflow requirements. |  |  |  |
| Quality |  |  |  |
| Process Review Auditing process on site |  |  |  |
| Lessons Learnt Not all contractors could provide the standard of work required on the project |  |  |  |
| Recommendations Backgroud checks of contracors. Maintain auditing and supervision |  |  |  |
| Human Resources |  |  |  |
| Process Review Maintain project team |  |  |  |
| Lessons Learnt Inetruptions to schedule can effect employment |  |  |  |
| Recommendations Other works e.g maintainance or service, required to fill in down time preventing the loss of employees. |  |  |  |
| Communications |  |  |  |
| Process Review Site comunication |  |  |  |
| Lessons Learnt Site team were unaware of all required process due to lack of communictaing between management, supervision and site team. |  |  |  |
| Recommendations Ensure all employees and capable of postion, provide training if required. |  |  |  |
| Procurement |  |  |  |
| Process Review Tendering Process |  |  |  |
| Lessons Learnt A contractor engaged on site having previsouly had issues with project stakeholder |  |  |  |
| Recommendations A register of conflict of intrest is required to prevent previous bad relationships with any companies on site affecting project |  |  |  |
| Risk |  |  |  |
| Process Review Risk management register |  |  |  |
| Lessons Learnt Project risk management was poor allowing complacence on site |  |  |  |
| Recommendations Devlop better stattergies for identifing risks prior to future projects. |  |  |  |
| Project Integration |  |  |  |
| Process Review Requirements of project sponsor |  |  |  |
| Lessons Learnt Original project sponsor failing finically, new sponsor engaged to finish contract |  |  |  |
| Recommendations Ensuring all new sponsors requirements are captured in change of scope and timeline. |  |  |  |

- Sam has approved the report in the above question to be distributed. He has also updated the project plan following your advice. Now he is ready for the project closure meeting. He has assigned you the task of organising this meeting. Answer the questions that follow.

- Who will attend this meeting? Guidance: List the attendees by name, job title, and organisation).

Terrence Mackay, General Manager, Cascade Peak Hotel Pty Ltd Stephen Lyons, Planning Manager, Cascade Peak shire council Kim Ngyuen, Director, Awesome Landscapes Kate Chan, Project Manager,Timber Home Construction Sam Ng , Project Manager, Awesome Landscapes

- What information will each person need before the meeting?

Project plan, charter and report will be required

- Which documents (and which version number of each document) will need to be printed off for the meeting?

Project plan and charter both version 4 Project completion report Project Archives checklist Formal Acceptance and Closure

- Which of these documents will require signatures?

Project plan and charter both version 4 Project completion report Formal Acceptance and Closure

- Who will need to sign off on these documents?

Terrence Mackay, Stephen Lyons, Kim Ngyuen, Kate Chan, Sam Ng

- Do you believe the project objectives aligned with the objectives of Awesome Landscapes throughout the entire project life cycle? Explain your answer.

Objectives didn’t align thoughout the project lifecycle due the change in sponsor and the delay in timeline that it caused. But other than this yes Awesome landscapes managed to reach the project objectives.

- What needs to be done after the meeting to complete the closure of the project?

A copy of the project completion report must be distirubted to all members of the meeting. A final invoice can then be raised by Awesome Landscapes and once payed achriving can be completed.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document