## Cover
QMP - Part B
Project Number: | 22066 |  | Project Name: | Rockpool Pelican Waters
Planning for Quality
Planning for quality is a collaborative process throughout the estimating, design and delivery of a project. Planning for quality outcomes requires us to understand the expected standards and how they will be achieved as early as possible, so we can put steps in place to ensure success.
This document is to be established by the Design Manager and Project Manager (where available) at the commencement of Design, then referred to monthly (or at key milestones thereabouts) to ensure consideration is given to quality planning.
At the time of client review and 'safety in design meeting', use this tool to check what we know and what we need to know, to ensure quality related information and concerns have been addressed and planned for.
At the time of the pre-mob meeting, bring the team together to collaboratively discuss and work through this document (as already populated to date) and identify any specific/detailed plans or actions required (Actions and Responsibilities tab). Schedule approx. 2 hours for this meeting. Include your projects Quality representative.
Review must occur monthly (or at key milestones thereabouts) to address action against plans, respond to changes, milestones, or next steps, and keep the focus and planning live.
This tool will support the discussion of high level quality issues, actions, management at your monthly project report meetings.
Our team will review:
a) Monthly | x | OR | b) at Key Milestones
Reviews Undertaken
Orange colour for the month of March Blue colour for the month of April Green for the month of May Purple For the month of June Navy blue for the month of July Yellow for the month of August Brown for the month of September
Note on A37: Ashley Lowe:

## Quality overview
QUALITY OVERVIEW
Items for discussion amongst your team to assist in identifying potential quality risks, issues, and planning requirements.
You do not need to note every little detail for each of these things, it is a prompt for you to consider and discuss, and a tool for you to keep track of key considerations.
AREA FOR CONSIDERATION | Y/N/NA | COMMENTS * if this is not enough space to capture relevant information, keep notes in a form that suits and attach.
CLIENT/CUSTOMER/ESTIMATING
Do we have a complete understanding of client and end user expectations? | Y | Repeat client. Carseldine benchmark, exceed Carseldine quality and client experience.
What standard do they expect / level of quality (e.g. class XXX) | Y | Exceed quality as previous project
Client specific requirements (audits, accreditation standards, reporting, design, product/systems etc.) | Y | Monthly PCG, Web FM (need to get in touch with WebFM to keep moving)
What have we priced vs what have we sold (client expectations)? | Y | Some items not covered against carseldine, Change register ongoing
What are the clients handover needs? (is this explicitly agreed with the client?) | Y | Operations Training and services fully commissioned (refer solar at Carseldine)
Will the client conduct 3rd party inspections? When? | N | Not expected
DESIGN
Completeness of design? (what stage is it at?) | 100% | Done
Value Engineering - has the client agreed in writing to the VE and understood responsibility for future defects relating to any VE | N/A
What is the zone classification - This will determine threshold termination height, windows /curtain walls and façade designs and certification? | N3 | Noted as B3 on Strcutural drawings
CONSULTANTS/SUBCONTRACTORS/SUPPLIERS/PRODUCTS
Consultant scopes - do they cover specific risks? | Y | 100% inspections done
Which trade scopes include high risk quality work? (complex, new systems, changing design, complex compliance requirements, common incidents scopes – waterproofing, tiling, roofing, concreting, fire etc.) - See 'Specific considerations' | Y | Vinyl, Waterproofing, External Render, Joinery, Painting, Tiling, Epoxy floor, Metalwork, Stainless steel, EMS, Curtain wall
Subcontractors, who are high risk? Why?(inexperience with system, inexperience with McNab standards and procedures, performance, capacity/availability of men etc.) | Y | Floor coverings - manpower (2nd crew this week), Electician - admin tasks, Painter (monitor quality with rushed works, Renderers (monitor timing)
Prefab off site - what products/what process/how will we ensure it's right? | Y | Metalwork
Items procured from Overseas | Y | Scozia has coordinated a final date to knock everything off the list
CONSTUCTION PROCESS
High quality finishes in a live/work area (i.e., need to store materials on high quality floor finish) | Y | Flooring Protection, Window Protection, GF access, Joinery Protection, dust free comms rooms
Temp works - fully considered / site layout and locations considered | Y | Nil
Defect management system - how will we do this during construction, how will we do this in DLP? | Y | Procore, plus realignment of roles and responsibilties discussed this morning
MCNAB PROCEDURES/SYSTEMS (as per QMP)
Requirement to step outside normal McNab procedure (Why? - Client requirement, McNab procedure/system impractical) | N | Must be approved by CM/QM and noted
Document control / ? any systems being used other than Procore | N
RFI Mgmt. | Y | Done
Collecting, recording and maintaining data sheets (Who and how?) | Y | CA team
Dilapidation report | Y | issued to council
Construction program accessibility/ communication/ stakeholder buy-in | Y | Client agreed on 60 week construction Program [300days]
Certification requirements | Y | CofC, QFES, Plumbing received
OTHER
Consideration of other stakeholders – neighbours etc. | Y | Front footpath closure and monitor traffic. Bring in bollards not in use
General working environment considerations | Y | Phased lockup through zones implemented and instructed to teams. Ground floor requires clean-up. Clean-up loading dock. Ensure keys are taken out of machines at lock-up
Services -locations and separation requirements achievable | Y | Excavations complete
May need to determine cost/requirements of plans ('Actions & Responsibilities' tab) in response to the above before proceeding
BUDGET
Are we resourced for success and to achieve our/clients quality expectations? (supervisory, compliance mgmt./site eng, equipment, etc.) | Y | Done
PROGRAM/SCHEDULE
Have we understood and planned for achieving our/clients quality expectations (quality actions) in our program?(for quality planning, monitoring, controlling, documenting, testing) | Y | GJG happy with quality and does not need to attend. McNab continue normal inspection procedures Team to fully review the defects list from Carseldine
MCNAB TEAM
Who is the QBCC Site Supervisor licence holder and is the class correct for the type of Building? | Y | Adrian Wyatt
Do we have the right skills and experience? (in methodology, technology, systems) | Y
Team members new to McNab? | N
Clarity of roles and responsibilities? | Y | Org chart completed as part of premob
Are we self-performing anything? | Y | Joinery install, ground floor trusses
Adequate process/system to track and manage change? (re-establish plans) | Y
Do we have an apprentice? How will we train them? | N

## Specific considerations
QUALITY - SPECIFIC CONSIDERATIONS
You do not need to note every little detail for each item. It is a prompt for you to consider and discuss, and a tool for you to keep track of key considerations.
ITEM | Y/N/NA | COMMENTS/CONSIDERATIONS * if this is not enough space to capture relevant information, keep notes in a form that suits and attach.
CIVIL
Does the geotechnical report mention any of the following:
Acidic Soils – What is the treatment requirement for soil / water and tipping locations? | Y
Water table height- Will a dewatering system be required? | Y
Fill materials – Is the fill Contaminated? | N
Classification of rock | N
Black soil or Clay – Expansion and contraction requirements | N
Sand – shoring requirements | Y
Other:
Services, In Ground and Overhead:
Has a current set of dial before digs been obtained? | Y | Done
Do services require vacuum excavation? | Y | Done
Backfilling requirements- Fill types / Level of supervision required | Y
Services as constructed picked up by Surveyor prior to backfill. | Y | Ongoing updated as required by surveyor
Any overhead services impacting site or operations | N
Any In ground water retention tanks / Filtration systems required | Y | SPEL to be commissioned
Compaction testing undertaken by Geo-tech | Y | Done
Other:
STRUCTURE/CONCRETE *minimum mandatory actions exist - see 'Actions and Responsibilities' tab
Have we reviewed the structural engineers safety in design? | Y
Has a 3rd party structural review being undertake and what was the outcome | Y
What does the structure consist of and what are the risks of each entity including fire rating? | Y | concrete/ blockwork / Structural steel
Do we have stressed slabs? | N
Do we have deflection mapping? Have we consulted the Engineer regarding this if topping slabs? | Y | design manager reviewing with windows ( Closed)
Conventional slabs | Y
Slab finish – exposed, polished, burnished? | Y | Broom finish external, spraycrete linemarking
Blockwork – Structural – Non-Structural | Y | Done
Structural steel | Y | Warranty for paint finish sorted by Reeve
Structural metal framing Façade. Does this meet the Earthquake requirements of AS 1170.4? | N/A
Retention walls (Note types) | N
Other:
PASSIVE FIRE *minimum mandatory actions exist - see 'Actions and Responsibilities' tab
Technical data/certificates required for all passive fire systems and Prototype wall / ceiling sections | Y | All up to date
Covering on external façade, atrium, void or an ancillary member to a façade, atrium or void confirmed as ‘non-combustible’? (product tested in accordance with AS 1530.1 or an exempt building element or ancillary building element under NCC Vol 1, C1.9 or C1.14.) | Y | All products confirmed. Lift to be complete
Have we cast any elements into the pre-cast that need specific fire protection? | N
Other:
WATERPROOFING *minimum mandatory actions exist - see 'Actions and Responsibilities' tab
Are there any nonstandard Façade waterproofing requirement? | Y | closed
Have we detailed all construction joints properly? | TBA | Done
Compatibility testing? | Y
Note all Areas requiring waterproofing | Y | Planter boxes, Roof plant deck , Ensuites, Kitchens (GF no waterproofing), Laundry, Lift lid, Kitchen roof slab, wanderers deck under pavers, water feature
Is a Blinding layer required to take membrane , if so state thickness | Y | blinding required. But not to take membrane ( Not Required)
Other: |  | Done
ROOFING *minimum mandatory actions exit - see 'Actions and Responsibilities' tab
Any special considerations | N | Josh to upload video to ITP - done, balance of works to be closed
Consider solar - no issues after water tests and rain
TILING *minimum mandatory actions exit - see 'Actions and Responsibilities' tab
Any special considerations | Y | Percentage of spares required - start loading tiles, carpet, paint spares, in store room on GF next to MSB room
| Y | No EWP on GF tiles
| Y | working through stone cladding inc expansion joints. Compatibility of glue and membrane
Please feel free to add any other items you feel require consideration based on your teams learnings/understanding of risks on the project
COASTAL NON-NEGOTIABLES
Coastal |  | Outside of breaking surf.
| Y | Warranties and maintenance during construction
| Y | Check rust on door hinges to external areas. Clean and treat prior to handover
LESSONS LEARNT
Callum also creating spreadsheet |  | This document is also a live document driven by Callum Bell (PM)
FAÇADE
Metalwork screens |  | Weld detail resolved - underway Lesson learnt tilt horizontal metalwork members Ensure cleaning regime is included in maintenance manuals

## Actions and Responsibilities
ACTIONS AND RESPONSIBILITIES
Recording and reviewing your key actions/plans is mandatory and you can do so below, however, you may wish to use Procore or some other method to keep record of actions/plans and reviews. Please note where you will document, review and maintain actions/plans.
We will keep record of our actions on:
TIPS/IDEAS to respond to identified unknowns/risk areas
* Asking the client to show you previous projects and point out what they were happy and unhappy with/what met their standard, what didn’t and what exceeded their standard
* A prototype or trial - think both structures and finishes (e.g. small concrete/column pours, prototype board etc.)
* Agree specific hold points where the client would like to attend and see for themselves
* Having client review prototype or first instance and confirming it is to their standard
* Creative and additional ITPs outside of mandatory requirements
* Get training early for the team from an expert/3rd party/trusted subcontractor
* Get training early from the Quality team
* Getting a peer review from someone you know has used the system or product before
* Give client a list of defects 30 days out from PC, so we can understand expectations and manage close out from the front foot.
ACTION/PLAN REGISTER
ITEM/RISK | CONTROL/ACTION | WHO IS RESPONSIBLE | WHEN | Tips/requirements
MANDATORY ITEMS
Waterproofing/tiling Above Ground | McNab AS Compliance Guides and ITPs:
| - Bathroom (03-DOC-004) | Team | Completed
| - Balcony (03-DOC-005) | Team | Completed
| - Planter Box (03-DOC-006) | Deleted from design | Not required
3rd Party Inspection
Waterproofing Below Ground | McNab Guide and ITP (03-DOC-008) | Complete
Waterproofing - Ensuites | Membrane/Fixing requirements/ITPs | Adrian Wyatt | Completed
Waterproofing - Planter Boxes | ITPs | Deleted from design | Not required
Waterproofing - other | ITPs:
Tiling - other | ITPs: | Adrian Wyatt | Completed
Roofing | ITPs: | Adrian Wyatt | Completed | Video of completed roof to be attached to ITP
-
-
Concreting | ITPs: | Josh MacPherson | Complete
-
-
-
Passive Fire | McNab Guide (03-DOC-007) and ITPs: | Adrian Wyatt | Completed
-
-
-
| Technical representative of tested system training (McNab & subbie) | Bayset, Passive fire
| 3rd Party Inspection | QSM | 2023-02-07 | Initial report undertaken and received
OTHER (Actions/ITPs)
Auto Doors Condensation |  | No air curtain at front door | TBA | air curtain required at café doors. Discuss with STP
Paint/repair/render to stairs | Sample on AFS. | Josh MacPherson | 2023-05-01 | Apex confirmed AFS have spoken to engage
UFD inspection kitchen and laundry |  | Mick B | 2023-06-01 | two inspections allowed for (PC and DLP), 80% inspection done
Permanent power | boards by 22/6, lights and power for AC by 3/7 | Ado/Levi | 2023-06-01 | Complete
Review Carseldine defect list as lessons learnt | OmTrak list emailed to team 19 June | All | 2023-06-01 | part done
Bidet to be tested |  | Levi | 2023-08-01 | Done
Check trellis requirements in DA and landscape expectations |  | Reeve | 2023-08-01 | No requirment in DA. Perg 1-4 will be done
Check any area which might be impacted by vehicle - bollards |  | Adrian/Levi | 2023-08-01 | Bollards to hydrants, loading dock
Camera inspections of in-ground services |  | Mick B | 2023-09-01
Currybowl extravanagze bonanza mst be locked in |  | Levi | 2023-08-01 | Done
Final ID survey needs to be coordinated |  | Mick B | 2023-09-01
EMS to be up and running prior to PC |  | Levi | 2023-09-01
Power on and dust free comms rooms |  | Alex | 2023-08-01 | Done
Bedside leg changover |  | Alex | 2023-09-01 | Done
Wall paper procurement |  | Levi | 2023-08-01 | Out of our scope now
Coordinate glass splashbacks to correct locations |  | Alex | 2023-08-01 | Done
Spare materials to be loaded into GF store rooms |  | Alex/Mick | 2023-09-01
Maintenance and warranties during construction for coastal requirements |  | Reeve | 2023-08-01
Review observations and action/close out |  | All | 2023-09-01
Close out Procore |  | All | 2023-09-01
Close out Hammertech |  | All | 2023-09-01