CPCCBC4007A

Plan building or construction work

ASSESSMENT SUMMARY

The assessment activities for CPCCBC4007A Plan building or construction work cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Corey Passey |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4007A

Plan building or construction work

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Corey Passey |
| --- | --- |
| Participant signature |  |
| Date | 20/06/2022 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 45 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

- Name one (1) document you might read alongside the contract to identify the following aspects:

- Material requirements

- Plant requirements

- On-site labour requirements

- Any unusual aspects of construction

| Answer | The specifications You should always refer to project plans specifications to ensure that you understand any particular requirements for the use of materials. - In some cases the NCC details the way in which the material is able to be used (e.g. through the Australian Standard). - In other cases you are expected to go to the websites of particular manufacturers and access the fixing and safety details for yourself. |  |
| --- | --- | --- |

- Name the Act and identify the section that outlines the maximum deposit amounts that may be accepted by a builder before services are provided. Identify the maximum deposit amounts and the penalties for breaching such requirements.

| Answer | Section of Act | Requirements and penalties |  |
| --- | --- | --- | --- |
|  | Queensland Building and Construction Commission Act 1991 (Qld): | Deposits. Generally, if the cost of your building work is $20,000 or more, the maximum deposit allowed is 5% of the total contract price (including labour, materials and GST) Possible Fines—penalty infringement notices—are issued where we discover non-compliant |  |

- Identify three (3) subcontractors you may engage for a job and the type of work they may undertake.

| Answer | Subcontractor | Work |  |
| --- | --- | --- | --- |
|  | Tiler | Laying of floor and wall tiles |  |
|  | Painter | Painting of internal walls and exterior claddings |  |
|  | Plumber | All plumbing and drainage work Organises water supply; installs pipes and drains; installs roof and guttering; fits taps, hot water systems and toilets; ensures that downpipes are fitted and the sewer is connected. N |  |

- Which of the following methods may be used to find subcontractors for a project? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Advertising |  |
|  |  | Networking |  |
|  |  | Online searches |  |
|  |  | Tenders |  |
|  |  | Word of mouth |  |

- Explain the importance of determining subcontractor or plant availability for a job.

| Answer | To avoid delays |  |
| --- | --- | --- |

- Identify two (2) methods you might use to find a supplier for materials.

| Answer | Internet Word of mouth referal |  |
| --- | --- | --- |

- Name two (2) factors that may impact on the availability of materials.

| Answer | Covid / Pandemic, supply chain issues, shipping etc Weather Material shortages |  |
| --- | --- | --- |

- Australian Standards must be considered when selecting materials. Identify the Australian Standard (referenced in the National Construction Code) which relates to the requirements for interior lighting.

| Answer | NCC Volume 1 Part J6 |  |
| --- | --- | --- |

- Identify two (2) types of plant that may be used for a building project and identify the type of work they may be used for.

| Answer | Plant | Work |  |
| --- | --- | --- | --- |
|  | Bobcat | Site scrapes, site cleans, prep work |  |
|  | Crane | Lifting frames and trusses and big items |  |

- Identify two (2) types of equipment that may be used for a building project and identify the type of work they may be used for.

| Answer | Equipment | Work |  |
| --- | --- | --- | --- |
|  | Extension Ladder | To reach heights, eg, climb onto a roof |  |
|  | Wheelbarrow | To move dirt and debris and things too heavy to lift by hand |  |

- Identify two (2) of the records you should keep when hiring plant and/or equipment.

| Answer | - Keep records of the invoices and receipts associated with the hire of plant to ensure you receive deposits back |  |
| --- | --- | --- |

- Name five (5) temporary services that need to be organised for a building site.

| Answer | The following temporary services should be supplied from the start of the building process: - Temporary electrical pole or power box built into its permanent position. If a slab is being poured on the ground, the power is brought on-site and the power board is put into its permanent place. Sometimes the location of the existing service will determine this. The set back distance and overhead or underground supply need to be considered - Water tapping to supply water to the site. This may be a short tapping (on the same side of the street) or a long tapping which requires piping under the road (if supply is on the other side of the street) - Temporary fencing around the site so that the public does not have access - Barricades to meet the local municipal by-laws. If the site cut is over one metre, a barricade is erected to prevent public access. If the site cut is less than one metre, a temporary fence is erected. - Waste bin |  |
| --- | --- | --- |

- True or False (Tick your response): Site accommodation should be provided where construction work occurs in a remote area.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What is required of a builder before any person is allowed on a building site? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | To check the person has a Construction Induction Card |  |
|  |  | To check the person has the approval of the local council |  |
|  |  | To check the person is wearing appropriate signage |  |
|  |  | To keep a record of all inductions and all personnel on the site |  |

- Who issues a construction induction card? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Australian Parliament upon fee payment |  |
|  |  | Each site at the conclusion of a site induction |  |
|  |  | Registered Training Organisations at the conclusion of training |  |

- Identify one (1) action you might take to facilitate site access for machinery.

| Answer | - Check if excavation works need to be undertaken to enable access for machinery. If this is the case, barriers may be required for additional protection of footpaths against water, mud and soil |  |
| --- | --- | --- |

- Identify the Volume and Sections of the NCC that relate to access to buildings for Classes 1 and 10, and Classes 2 to 9.

| Answer | Classes 1 and 10 | Classes 2 to 9 |  |
| --- | --- | --- | --- |
|  | NCC Volume 1, Part 2.5 | NCC Volume 1, Section D |  |

- You should contact your local council to be approved for out of hours construction. Identify the required documentation for an application and the timeframe for approval.

| Answer | You must fill out and application and approval form 10 working days prior to doing the works. Operational Works/Compliance Assessment SmartForm. |  |
| --- | --- | --- |

- In addition to the permit from Q18. identify two (2) other permits you may need to obtain to undertake a building project. 

Briefly describe the documents required for approval and who these should be submitted to for approval.

| Answer | Permit | Documentation and approval body |  |
| --- | --- | --- | --- |
|  | - Traffic Management Plan for temporary lane/road closure | City council to approve and must be lodged 20 days prior to works |  |
|  | Footpath closure permit | City council to approve and must be lodged 20 working days prior to works |  |

- True or False (Tick your response): Project commencement date is always at the date the contract is signed.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What document should be developed when purchasing supplies or construction materials?

| Answer | Purchase orders with all the relevant details |  |
| --- | --- | --- |

- True or False (Tick your response): Every delivery should be physically checked against the delivery sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Who should be contacted if items are missing from a delivery?

| Answer | Supplier/office staff/ admin/supervisor |  |
| --- | --- | --- |

- Name the Act and identify the section that outlines the requirement to implement hazard and risk management on site. Briefly describe the requirements.

| Answer | Section of Act | Requirements |  |
| --- | --- | --- | --- |
|  | Safe Work Australia | - ensure that a safe work method statement (SWMS) is prepared before the proposed work starts - make arrangements to ensure that the high risk construction work is carried out in accordance with the SWMS - ensure that a copy of the SWMS is given to the principal contractor before the work starts - ensure that a SWMS is reviewed and revised if necessary - keep a copy of the SWMS until the high risk construction work is completed. |  |

- Identify one (1) regulation that an organisation’s WHS policies and procedures must comply with.

| Answer | - the Work Health and Safety Act 2011 |  |
| --- | --- | --- |

- What document should be followed when disposing of hazardous materials?

| Answer | under the Environmental Protection Regulation 2019 (Qld) waste handlers must submit waste tracking information when transporting regulated waste or waste residues. A complete list of trackable regulated wastes can be found in Schedule 11 of the Environmental Protection Regulation 2019 (Qld). |  |
| --- | --- | --- |

- An asbestos removal control plan is required when more than ____m2 of asbestos containing material is to be removed.

| Answer | 10m2 |  |
| --- | --- | --- |

- True or False (Tick your response): A site assessment should be undertaken if contamination is known or likely to be present from the removal of existing services.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- True or False (Tick your response): Multiple projects can be planned using a single Gantt Chart.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- What are the advantages of hiring subcontractors to work across multiple nearby projects? Explain with an example.

| Answer | Consistency Less traveling Easier to organise One point of contact Save time and money |  |
| --- | --- | --- |

- Provide one (1) example to explain why construction operations must be sequenced.

| Answer | To provide a good work flow, one task must be completed before the next in order to save time and money and mistakes and unhappy trades. EG you can’t paint walls before they have been plastered and before the carpenters have fixed out. |  |
| --- | --- | --- |

- Which of the following should be considered as part of task sequencing? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Holidays |  |
|  |  | Labour availability |  |
|  |  | Plant availability |  |

- Order the following construction operations from 1 to 6 to form the most efficient sequence.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 2 | Excavation of footings |  |
|  | 4 | Floor frame |  |
|  | 3 | Installing brick base |  |
|  | 6T | Roof trusses |  |
|  | 1 | Set out |  |
|  | 5 | Wall frames |  |

- Refer to the table below to complete the chart shown. Label the blank boxes with the appropriate Task ID letters.

| Task ID | Task | Preceding event | Nodes |
| --- | --- | --- | --- |
| A | Make enquiries and order all materials required | Start | 1 |
| B | Wait for bricks, sand and cement to arrive | A | 2 |
| C | Clear vegetation from the site | A | 2 |
| D | Order concrete to be delivered | A | 2 |
| E | Dig the trench | C | 4 |
| F | Pour the footings | E | 5 |
| G | Footings curing time | F | 6 |
| H | Load the bricks on the site | B | 3 |
| I | Mix the mortar and lay the bricks | H | 7 |
| J | Clean rubbish from the area | I | 8 |
|  | Finish | J | 9 |

GONe Pager Expre

F

H

EDif E

I

J

D

C

B

A

| Answer |  |  |
| --- | --- | --- |

- Name one (1) computer-based software package that may be used to prepare a project schedule.

| Answer | One Pager Express |  |
| --- | --- | --- |

Refer to the chart below to respond to Q36. to Q40. This chart shows the task sequence for building a brick fence.

- What is the total time for the process if the top path is taken? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- What is the total time for the process if the path through nodes 2, 4 and 5 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- What is the total time for the process if the path through nodes 2, 5 and 6 is taken? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | 8 days |  |
|  |  | 9 days |  |
|  |  | 11 days |  |

- Describe the critical path.

| Answer | - The ‘critical path’ – the longest sequence of activities in a project (which determines the shortest possible completion time if all events are to be completed) - Depending on the path you take will depend on how much float is in the job Delays in your critical path can cause an increase in time and money |  |
| --- | --- | --- |

- True or False (Tick your response): Even if the brick delivery in the top path was late by two (2) days, it is possible that the job will still run on schedule.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify three (3) factors that may impact on the critical path of a project and cause it to need revision.

| Answer | Wet weather Client Variations Material delays |  |
| --- | --- | --- |

- Which major point(s) should you note when carrying out an inspection of neighbouring properties? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | If the neighbours drive the right kind of car for that neighbourhood |  |
|  |  | Structure and condition of any boundary fences |  |
|  |  | Type and condition of all structures on the boundary |  |
|  |  | Whether the houses are of Victorian heritage |  |

- Why should you take photographs of site boundaries with neighbouring properties?

| Answer | For proof To avoid any arguments over damaged property |  |
| --- | --- | --- |

- When should a condition report be given to owners of adjacent buildings? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Before construction commences |  |
|  |  | During construction |  |
|  |  | After construction completes |  |

- When might a neighbouring property owner be required to refer to a condition report?

| Answer | When there is a dispute. |  |
| --- | --- | --- |

CPCCBC4007A

Plan building or construction work

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | Corey Passey |
| --- | --- |
| Participant signature |  |
| Date | 20/06/2022 |

| Assessor name | Mark Harris |
| --- | --- |
| Assessor signature |  |
| Date | 20/06/2022 |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4007A

Plan building or construction work

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to plan on-site activities, including the employment of physical and human resources and the development of documentation and advice for relevant authorities: - Occasion 1: Residential projects - Occasion 2: Commercial projects The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - A construction program/schedule for a project showing: - The sequencing of the trades, etc. - Working and non-working days, etc. - Local authority construction commencement notices - Pre-construction site inspection reports or dilapidation reports - WHS policy The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document. |  |  |  |
| Resources required: Computer (ideally with project scheduling software), Building Contract, Organisational policies, Telephone, Facsimile. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: | Corey Passey |  |  |
| Name of observer: | Mark Harris |  |  |
| Role of observer (Confirm suitability to sign) | GM Stroud Homes |  |  |
| Email address of observer | Mark.harris@stroudhomes.com.au |  |  |
| Signature of observer: |  |  |  |
| Date: | 10/06/2022 |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| 1 Appraise contract documentation |  |  |  |
| - Review contract documentation, codes, standards and regulations to identify any unusual aspects of construction, use of materials or penalties. |  |  |  |
| - Determine availability of selected subcontractors to suit the job requirements. |  |  |  |
| - Assess availability of materials and confirm with suppliers. |  |  |  |
| - Identify site access requirements and limitations, taking action to facilitate entry. |  |  |  |
| - Prepare documentation for authorities controlling construction work and determine project commencement date. |  |  |  |
| - Implement procedures for controlling and recording site deliveries. |  |  |  |
| 2 Construction operation strategies |  |  |  |
| - Identify organisational strategies for implementing construction. |  |  |  |
| - Implement procedures for recording the hire of plant and equipment. |  |  |  |
| - Implement organisational WHS policies and procedures, including hazard and risk management. |  |  |  |
| - Implement procedures for the removal of existing services and hazardous materials, in accordance with Environmental Protection Agency requirements. |  |  |  |
| - Follow procedures for the control of multiple projects. |  |  |  |
| 3 Project schedule |  |  |  |
| - Sequence construction operations. |  |  |  |
| - Enter operation details into a manually prepared project schedule or computer-based software package. |  |  |  |
| - Define critical path of the project, revising as required. |  |  |  |
| - Adjust project timeframes to account for anticipated delays. |  |  |  |
| 4 Required resources |  |  |  |
| - Determine and document temporary services and site accommodation requirements. |  |  |  |
| - Determine and document plant requirements and availability, with reference to contract documentation. |  |  |  |
| - Determine and document on-site labour requirements, with reference to contract documentation. |  |  |  |
| 5 Condition reports |  |  |  |
| - Complete reports on the condition of existing buildings and structures on adjacent site boundaries. |  |  |  |
| - Forward copies of condition reports to the owners of adjacent buildings prior to commencing construction. |  |  |  |
| - Effectively communicate using the following methods: - Telephone, facsimile, email and in writing - Language/concepts appropriate to cultural differences - Non-verbal communication |  |  |  |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments

I have observed Corey satisfactorily complete each of these tasks mentioned above on the projects attached to this module. I have no hesitation in recommending him to pass this subject. He has a clear understanding of the importance of scheduling trades and uses our management system Onsite Companion. He has a clear understanding of this module. He understands how to appraise contract docs, I have witnessed him follow our company procedures on multiple contracts/projects and have heard him on the phone to trades and suppliers and clients. I recently saw him organise temporary services on site for one of our jobs he is currently help supervise in Brisbane south. Prior to joining Stroud homes Corey built a restaurant/cocktail Bar on the sunshine coast at the <Mooloolaba Wharf for Livi Robins, feel free to call her for a reference (0423052162), So as I did not observe him for the commercial project I know he has done this for that particular project. He has also worked along side our new franchisee Liz and Dave Bird at Lunic Developments who did similar commercial fit outs. (0413244546) Corey was also a director of “Total Fitouts” for 5 years, so has a good knowledge of this sector. Kind Regards Mark Harris GM Stroud Homes