## Sheet1
CPCCBC4004A - Task 1 - Scope of works - Bricklaying
External wall areas
Ground Floor | Totals
Main wall | 161.67
Alfresco head | 3.27
Alfresco piers | 9.8
Patio pier | 5.74
Total area - m2 | 180.48
First floor
Main wall | 164.6
B wall for thickness of slab | 0.96
Balcony walls - 1500 H | 4.95
Raked walls | 12.17
Total area - m2 | 182.68
Total areas of walls - m2 | 363.16
Total walls m2 | 363.16
Total windows m2 | 78.79
Total walls m2 - less openings | 284.37
284.37 x 0.0336 = | 8469.39 | Bricks required
add 5% wastage = | 8886.56 | Rounded to 8887 Bricks
Total Bricks | 8887
Brick workings = 0.12 x0.28 = 0.0336 m2 per brick
Total Labour rates
Labour = 8887 x $1.80 per brick = | $15 966.60
Day labour rate - $15 966.6 - 10 working days | $1 597 | per day
Scaffold
Scaffold hire - approx 20 m | 110 | per day
Total scaffold hire | 1100 | 10 days hire
Lintels
1200 lintel | 37 | $30.83 per m
1500 lintel | 47.38 | $31.60 per m
1800 lintel | 58.71 | $32.61 per m
2400 lintel | 78.28 | $32.63 per m
2100 lintel | 67.98 | $32.40 per m
Average = $32.10 per m
Other materials required to complete scope of works
Mixer hire | 1100 | for 10 days
Cement allowance | 8000
Hose | 25
Square mouth shovel x 1 | 11.95
Long handle shovel x 1 | 48
Line pins x2 | 8
Wheel barrow x 1 | 165
Brickies trowel x 3 | 97.9
Brickies ties x 2 | 130
Pointing trowel x 3 | 180
Total cost of works ex GST | 27121.8
GST amount | 2172.19
Total cost of works including GST | 29293.99