CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

The assessment activities for CPCCBC4003A Select and prepare a construction contract, CPCCBC4016A Administer a construction contract & CPCCBC4032A Apply contract law to sales processescover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Zac Markwell |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for CPCCBC4003A | Competent | Not Yet Competent |
| Outcome for CPCCBC4016A | Competent | Not Yet Competent |
| Outcome for CPCCBC4032A | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Zac Markwell |
| --- | --- |
| Participant signature |  |
| Date | 27/01/2022 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 51 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

Order the following elements of an agreement from 1 to 4.

| Answer | Element Number | Element |  |
| --- | --- | --- | --- |
|  | 2 | Acceptance |  |
|  | 4 | Consideration |  |
|  | 3 | Intention of legal consequences |  |
|  | 1 | Offer |  |

When would an offer be considered to have lapsed?

| Answer | When the -acceptance period has expired -Offer has be withdrawn before acceptance -After reason period of tie dependent on the size of a contract |  |
| --- | --- | --- |

What happens to the offer if new terms are suggested?

| Answer | New terns are classed as a counter offer and can be accepted or rejected |  |
| --- | --- | --- |

What does it mean when a contract is supported by ‘valuable consideration’?

| Answer | A promise made from one party to another for a agreed promise un return, mostly in the form of money |  |
| --- | --- | --- |

Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

| Answer | Persons suffering from a mental disability, intoxicated and senile person |  |
| --- | --- | --- |

- Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

| Answer | Consent is a motion put forward from a individual that is in a clear state of mind with no influence or pressure from other individuals or groups |  |
| --- | --- | --- |

Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

| Answer | QBCC helps with developing contracts by delivery pre-establish contract that help and guide traders in the right direction in terms of legislation and sets a general base line and standard to what contract should represent. -Licensing contractors -Educating contractors about their legal rights and responsibilities -Educating consumers about their rights and obligations -Handling disputes fairly and equitably -Protecting homeowners against loss through the Queensland Home Warranty Scheme -Implementing and enforcing legislative reforms and, where necessary, -prosecuting people not complying with the law |  |
| --- | --- | --- |

Under what laws are domestic building contracts regulated?

| Answer | QBCC |  |
| --- | --- | --- |

Domestic building contracts must be put in writing once the work exceeds what value?

| Answer | $3300 |  |
| --- | --- | --- |

A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

| Answer | $100,000 Competition and consumer regualtions 2010 |  |
| --- | --- | --- |

Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

| Answer | With in 5 business days The QBCC Act (Schedule 1B, Section 15 |  |
| --- | --- | --- |

What are the benefits of having a written contract in place between parties?

| Answer | Allows for a clear and concise communication between parties in what the responsibilities and liabilities of each party as with in the contact. Makes the process of Payment, Variation, Time frames easier to manage. |  |
| --- | --- | --- |

Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Clauses |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Acceptances | 1 - F | A | Provide specific reasons that allow the contract period to be adjusted |  |
|  | 2 | Cost adjustments | 2 - E | B | A provision for which remedies can be sought if breached |  |
|  | 3 | Extensions of time | 3 - A | C | Specifically outlines the tasks to be completed as part of the construction work |  |
|  | 4 | Payments | 4 - D | D | Outlines the requirements for deposits |  |
|  | 5 | Scope of work | 5 - C | E | Address the risk of rise/fall of expenses |  |
|  | 6 | Term | 6 - B | F | Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding |  |

Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  | þ | Contract estimate |  |
|  | þ | Contract request |  |
|  | þ | Preliminary agreement |  |

True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

| Answer | þ | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

| Answer | Contract name | Description |  |
| --- | --- | --- | --- |
|  | Kitchen Bathroom & Laundry Supply Install | A supply and install contract specifically suited for bathrooms and laundry |  |
|  | Small Works Contract | Domestic building works that don’t incorporste footing or foundations |  |
|  | Commercial Minor Works Contract | Minor commercial work to the value of $100,000 |  |
|  | Commercial building contracts | Construction only of commercial building works |  |

Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

| Answer | Commercial Minor contract |  |
| --- | --- | --- |

Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

| Answer | Basic works contracts with a maximum value 0f $80,000 |  |
| --- | --- | --- |

Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

| Answer | Topics | Definition |  |
| --- | --- | --- | --- |
|  | Builder’s Licence | Use QBCC licenced contractors, if unlicenced check builder history via QBCC online search. |  |
|  | Contract price | Contract price if fixed should be shown on first page, if not fixed all allowances shall be stated in the contact schedule, contract must contain warning about possible price adjustment |  |
|  | Building approvals and inspections | Building approvals and inspections are the responsibility of a building certifier who may be engaged by you or, more commonly, your builder If a certifies has been engaged any additional certifying function will be at your expense. Any certificate of inspection must be presented to all party as soon as possible. |  |
|  | Practical completion and handover | Final payment isn’t due until all contract obligation have be completed, all legal requirements met, defects rectified. Document should be compiled during a handover inspection. |  |
|  | Implied warranties | Schedule IB of the Act sets out statutory warranties Warranty period of 6 years from completion, or termination or cessation of the work for breaches resulting in structural defects 1 year for all other breaches Any legal proceeding must begin with-in warrant period or a further 6 months if the breach becomes apparent within the last 6 months of the warranty period |  |

- Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  | þ | Engineer specifications |  |
|  | þ | Plans, drawings and specifications |  |
|  | þ | Prime Cost Items Schedule |  |
|  | þ | Processes for applying for extensions of time |  |
|  | þ | Product catalogues |  |
|  | þ | Project timelines and schedules |  |
|  | þ | Provisional Sums Schedule |  |
|  | þ | Rise and fall calculations |  |
|  | þ | Site conditions report |  |
|  | þ | Soil and sedimentation report |  |

What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

| Answer | Provisional Sum is an amount of money to cover unexpected costs once initial works commence (Berried tree stump or large rocks) Prime cost is amount allocated for the purchase of toilets, tiles basin and tap fittings. |  |
| --- | --- | --- |

Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

| Answer | General building material costs such as Timber, steel, copper, pvc, roof iron |  |
| --- | --- | --- |

True or False (Tick your response): Variations can be requested by both the client and the builder.

| Answer | þ | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

| Answer | All variation must be put in writing, The contractor should submit a extension of time and payment linked to the variation document if required via writing. |  |
| --- | --- | --- |

Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

| Answer | ACCC (Australian competition consumer commission) Competition and Consumer Act 2010 (Cth) Fair Trading Act 1989 |  |
| --- | --- | --- |

Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

| Answer | Make enquire about – why you want to borrow money -about your financial situation - steps to verify your financial situation Determine if you can meet your financial obligation of the contract Determine if the contract is suitable for you |  |
| --- | --- | --- |

What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

| Answer | 5 business days to withraw from the contract, but there are implementing cost to the homeowner. The submission must in writing under the cooling- off provision in section 35 of Shedule 1B of the QBCC |  |
| --- | --- | --- |

What are the maximum deposits recommended for a residential building project?

| Answer | If priced over $20,000 a max deposit of 5% If priced more than $3,300 but less than $20,000, deposit not to exceed 10% 20% if 50% of the work is to be performed off site |  |
| --- | --- | --- |

Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

| Answer | At the end of each construction stage Deposit 5% Base 15% Frame 20% Enclosed 25% Fixing 20% Practical 15% |  |
| --- | --- | --- |

- You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

| Answer | 12.73% |  |
| --- | --- | --- |

- Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

| Answer | Breach | Explanation |  |
| --- | --- | --- | --- |
|  | Breach of condition under contract | These are essential terms. If a condition is not fulfilled, the nature of the contract is drastically changed. If a condition is breached, the aggrieved party can elect to discharge the contract and sue for damages |  |
|  | Breach of warranty under contract | If a warranty is not fulfilled, the nature of the contract is not drastically changed. If a warranty is breached, the aggrieved party cannot elect to terminate or discharge the contract – they may only seek damages. |  |

What does repudiation of a contract mean?

| Answer | Repudiation is a term used to describe the rejection of a proposal or idea |  |
| --- | --- | --- |

True or False (Tick your response): In the event of repudiation, the injured party has two options:

- Continue with the contract

- Accept the repudiation and move to terminate the contract

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  | þ | False |  |  |

Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

| Answer | Caution should be given due to some of the repercussion, the other party may be able to sue for defaulting or innocent party chooses to insist on performance, then the contract will still be on foot and all of the obligations and liabilities will still be applicable. |  |
| --- | --- | --- |

What does ‘abandonment of contract’ mean?

| Answer | Where both parties have ventured outside of the original contract terms and requirements making the contract no longer valid Another is when a contractor fails to perform the work on a project by not commencing work or not completing works |  |
| --- | --- | --- |

A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

| Answer | Cause, is when one party stops due to a lack in performance by the other party, the law provides limited resources to the terminated party. Termination, when the owner stops work from other than performance related reasons, the law may provide assistance to the aggrigated contractor against the owner. |  |
| --- | --- | --- |

Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

| Answer |  | Yes |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | þ | No |  |  |

If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

| Answer | - What has to happen to meet contract requirements - A reasonable timeframe given in which the contract must be completed - A statement of consequences reflecting the non performance in accordance with the notice |  |
| --- | --- | --- |

True or False (Tick your response): Where the notice given (as per Q38. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

| Answer | þ | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

| Answer | Final payment can’t be with-held to wait the completion of defects. The builder has a contractual obligation to repair all defect, however this doesn’t all ways happen before handover. |  |
| --- | --- | --- |

Explain the concept ‘conditions for completion at the cost of the contractor’.

| Answer | Is the rectification of defects or omissions of a contract works that have become apparent with in a 6mnth period of practical completion. The defect must be presented in writing within 6mnth of the contract completion and rectification must completed with-in a 28day period of the notice, dependent on agreed access. |  |
| --- | --- | --- |

Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

| Answer | the person’s name; the person’s business address; the person’s telephone number; the person’s email address |  |
| --- | --- | --- |

Name one (1) person you should consult if you are considering ousting a contractor from a building site.

| Answer | Lawyer |  |
| --- | --- | --- |

What document should you refer to if you are considering ousting a contractor from a building site?

| Answer | Contract Documentation |  |
| --- | --- | --- |

How should you handle a customer complaint?

| Answer | Deal with immediately Remain calm Identify the issue Decided a resolution Arrange second opinion Keep records Repair issue |  |
| --- | --- | --- |

How do you reduce the risk of dispute?

| Answer | Record all complaints Act promptly to all concerns Do what was agreed Cot be unrealistic |  |
| --- | --- | --- |

What is the process for dispute resolution?

| Answer | avoiding, accommodating, compromising, competing and collaborating |  |
| --- | --- | --- |

- During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

| Answer | Hi Damien, Thank you for your email regarding you concerns with the bathroom. On review I have taken down information regarding the suite and the specification reflected in the original contract, in comparison what is installed is what is presented in the original contract I have attached the snip-it of the contract for your perusal. However, if you would like to swamp the bath for a different style Im sure we accommodate your request. Kind regards |  |
| --- | --- | --- |

Where would you find any possible penalties associated with a build?

| Answer | In the initial contract terms |  |
| --- | --- | --- |

Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

| Answer | The local authority will hold the certificate and its up to a accredited building certifier to loge the document. The certificate can be obtained once the contract is fully completed and is issued at the end of the defects and liabilities period thus releasing the remain money Q51. Answer: New Homes Construction contract |  |
| --- | --- | --- |

- Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:

  - The land has been secured and paid for by the Clients.

  - Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.

  - Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured.

  - Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list.

  - The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.

  - The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.

  - Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build.

  - The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.

  - The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.

  - The construction period excluding inclement weather and possible delays is 23 weeks

  - Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).

  - Prime costs are required for the solar hot water system and ducted air conditioning

  - Provide fictitious details for all other sections of the contract.

  - 18 solar panels are to be installed on the roof

| Answer |  | ¨ |
| --- | --- | --- |

CPCCBC4003A Select and prepare a construction contract

CPCCBC4016A Administer a construction contract

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | Zac Markwell |
| --- | --- |
| Participant signature |  |
| Date | 26/01/2022 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to apply contract law to residential and/or commercial construction sales processes. The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - Copy of a contract issued to sub-contractor for your project with relevant AS code on the front - Proof of consultation with sub-contractor regarding contract and contract terms, inclusions and omissions (emails) - Copy of HSE minimum requirements sent as contract condition - Construction contracts that have been developed, signed off, or contributed to by the candidate - Proof of correspondence with client regarding construction contract. Redact sensitive information as required. The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment. |  |  |  |
| Resources required: Two (2) pre-contract agreements; two (2) sales contracts (e.g. QBCC contracts), telephone, facsimile machine, computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: |  |  |  |
| Name of observer: |  |  |  |
| Role of observer (Confirm suitability to sign) |  |  |  |
| Email address of observer |  |  |  |
| Signature of observer: |  |  |  |
| Date: | Click here to enter a date. |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Explain to the client: - Essential terms and elements of a valid contract - Types and purposes of agreements employed with the industry (including sales contracts and pre-contract agreements) - The range of documents that collectively make up a contract (including construction schedules, reports, specifications) - The importance of the contract to sales process - Implications of legislation, regulations and codes of practice (including Australian Consumer Law) |  |  |  |
| - Discuss and agree upon clauses of a pre-contract agreement, including payment or deposit. |  |  |  |
| - Ensure the pre-contract agreement is signed and processed according to organisational requirements. |  |  |  |
| - Select appropriate contract and seek expert advice in the preparation of the contract, considering: - Contract rise and fall amounts - Schedule of progress payments - Processes for applying of extensions of time |  |  |  |
| - Break down contract clauses/terms/conditions with the client, including: - Rights, liabilities and potential penalties of parties under the contract - Definitions of building work, common contract terms and procedures, considering – - Practical completion and issuing a final certificate - Defects liability and completion at the cost of the contractor - Effect of ousting the contractor from the building or site - Cooling off periods - Provisional sum and prime cost allowances - Measures to be taken in the event of an anomaly in the rendering of the contract, considering – - Variations - Circumstances that bring about a breach and termination of contract, considering – - Unreasonable/vexatious notice - Abandonment of a contract - Methods for resolving contractual disputes |  |  |  |
| - Effectively communicated with clients, subcontractors, colleagues and external parties using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication - Using technology (including telephone, facsimile, email) - In writing (including drafting responses to queries about contracts) |  |  |  |
| The participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments