🛠 Project: 6x6 Colorbond Shed Installation

📍 Location: 16 Sheehan Street, Rockhampton
📅 Estimated Duration: 7–10 days
💲 Labour Rate: $33.50/hour
🔨 Total Labour Hours: 50 hrs
💲 Material Cost: $32,360

🗓 Detailed Project Schedule

| Day | Task | Duration (hrs) | Labour Cost | Notes |
| --- | --- | --- | --- | --- |
| Day 1 | Site preparation (clearing, levelling) | 5 hrs | $167.50 | Remove debris, level ground, mark corners |
| Day 2 | Excavation & formwork | 6 hrs | $201.00 | Dig foundations, install formwork for slab |
| Day 3 | Concrete slab pour | 6 hrs | $201.00 | Pour and finish reinforced concrete |
| Day 4 | Slab curing, delivery check, framing prep | 3 hrs | $100.50 | Light work while slab cures; inspect material delivery |
| Day 5 | Wall frame assembly | 7 hrs | $234.50 | Erect side and rear walls, secure to slab |
| Day 6 | Roof trusses and sheeting | 7 hrs | $234.50 | Install rafters and Colorbond roof sheeting |
| Day 7 | Cladding, guttering, flashings | 6 hrs | $201.00 | Wall cladding, waterproofing elements |
| Day 8 | Doors, windows, internal finishing (if any) | 5 hrs | $167.50 | Install roller/sliding doors, add optional internals |
| Day 9 | Electrical/lighting prep (optional) | 3 hrs | $100.50 | Placeholder if power included—licensed sparky needed |
| Day 10 | Final inspection & site clean-up | 2 hrs | $67.00 | Quality check, cleanup, removal of debris |

💰 Cost Summary

| Item | Cost |
| --- | --- |
| Labour (50 hrs @ $33.50/hr) | $1,675.00 |
| Materials (Colorbond, slab, fittings) | $32,360.00 |
| Total Estimated Cost | $34,035.00 |