# Operational Plan Monitoring

## Performance systems

Assessment of progress towards achieving profit and productivity plans and targets.

## Analysis

Complete the table below, fill out the budget and actual data to determine variances in performance

| Finances | April (Budget) | April (Actual) | May (Budget) | May (Actual) | June (Budget) | June (actual | Budget total | Actual total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CA City Payroll | $83333 | $83333 | $83333 | $89166 | $83333 | $90833 | $249999 | $263332 |
| Advertisement filming/ editing | $5000 | $3000 | $5000 | $6000 | $5000 | $6350 | $15000 | $15350 |
| Advertisement space on networks | $5000 | 0 | $5000 | $3500 | $5000 | $5000 | $15000 | $8500 |
| DM Printing | $746 | $723 | $746 | $858 | $746 | $836 | $2238 | $2417 |
| DM Distribution | $500 | $510 | $500 | $510 | $500 | $495 | $1500 | $1515 |
| Miscellaneous | $1667 | $1334 | $1667 | $667 | $1667 | $2000 | $5001 | $4001 |
| Total | $96246 | $88900 | $96246 | $100701 | $96246 | $105514 | $288738 | $295115 |

Complete the table below, fill compare the progress of productivity to the timelines established

| Productivity | April (Projected) | April (Actual) | May (Projected) | May (Actual) | June (Projected) | June (actual | Projected total | Actual total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Management | 100% | 95% | 100% | 80% | 100% | 110% | 100% | 95% |
| Advertising team | 100% | 80% | 100% | 80% | 100% | 73% | 100% | 78% |
| Media liaisons | 100% | 100% | 100% | 94% | 100% | 100% | 100% | 98% |
| Printing | 100% | 100% | 100% | 80% | 100% | 81% | 100% | 87% |
| Distributions | 100% | 98% | 100% | 95% | 100% | 90% | 100% | 94% |
| Analysts | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |
| Total | 100% | 96% | 100% | 86% | 100% | 92% | 100% | 91% |

## Unsatisfactory performance

Record any performance deemed unsatisfactory and the steps taken to rectify the situation to bring it in line with the operational plan or implement appropriate contingencies while consulting with relevant personnel.

## Recommendations

Based on the last three months, prepare recommendations to variation of the operation plan, identify who the designated persons are to gain approval to implement variation.

## Implementation systems

Outline the how you would implement systems, procedures and records associated with performance in accordance with organisation’s requirements used in this operational plan