## REO SUPPLY SUMMARY
REO SUPPLY: MCU Sheet
|  | PO/ ESTIMATE | [5 empty] | ACTUALS
AREA | TYPE | QTY | UNIT | COST $ | TOTAL |  |  | QTY's | $ | Var Qty | Var $ | Forecast Qty's to GO | Forcast $ TO GO | SITE Percentage Completed | Percentage of Area Completed
Admin building Reo Supply
Pad Footings | N12 Bar | 0.15 | tonne | 1215 | 182.25 |  |  | 0 | 0 | -0.15 | -182.25 | 0.15 | 182.25 |  | 0%
Ground Beams | R10 ligs | 1.1892 | tonne | 1315 | 1563.798 |  |  | 0 | 0 | -1.1892 | -1563.798 | 1.1892 | 1563.798 |  | 0%
Ground Beams | Bar | 3.7631 | tonne | 1215 | 4572.1665 |  |  | 0 | 0 | -3.7631 | -4572.1665 | 3.7631 | 4572.1665 |  | 0%
Retaining Wall | Bar | 1.1047 | tonne | 1215 | 1342.2105 |  |  | 0 | 0 | -1.1047 | -1342.2105 | 1.1047 | 1342.2105 |  | 0%
SOG | N16 Bar | 1.8743 | tonne | 1215 | 2277.2745 |  |  | 0 | 0 | -1.8743 | -2277.2745 | 1.8743 | 2277.2745 |  | 0%
SOG Waffle Pod | 375mm | 361.0712 | each | 14 | 5054.9975 |  |  |  | 0 | -361.0712 | -5054.9975 | 361.0712 | 5054.9975 |  | 0%
SOG Waffle Pod | 300mm | 26.7878 | each | 9.2 | 246.4479 |  |  |  | 0 | -26.7878 | -246.4479 | 26.7878 | 246.4479 |  | 0%
SOG Waffle Pod | 4 way spacer | 388 | each | 0.9 | 349.2 |  |  |  | 0 | -388 | -349.2 | 388 | 349.2 |  | 0%
SOG Waffle Pod | 2 way spacer | 194 | each | 0.75 | 145.5 |  |  |  | 0 | -194 | -145.5 | 194 | 145.5 |  | 0%
Stairs | N32 | 0.24 | tonne | 1215 | 291.6 |  |  |  | 0 | -0.24 | -291.6 | 0.24 | 291.6 |  | 0%
Driveway | R10 ligs | 0.0525 | tonne | 1315 | 69.0375 |  |  |  | 0 | -0.0525 | -69.0375 | 0.0525 | 69.0375 |  | 0%
Driveway | N12 Bar | 0.24738 | tonne | 1215 | 300.5667 |  |  |  | 0 | -0.24738 | -300.5667 | 0.24738 | 300.5667 |  | 0%
Admin Walkway Reo Supply
Ground Beam | Bar | 1.0101 | tonne | 1215 | 1227.2715 |  |  |  | 0 | -1.0101 | -1227.2715 | 1.0101 | 1227.2715 |  | 0%
SOG Waffle Pod | 225mm | 133.8169 | each | 7.7 | 1030.3899 |  |  |  | 0 | -133.8169 | -1030.3899 | 133.8169 | 1030.3899 |  | 0%
SOG Waffle Pod | 395mm | 17.0056 | each | 17.5 | 297.5984 |  |  |  | 0 | -17.0056 | -297.5984 | 17.0056 | 297.5984 |  | 0%
SOG Waffle Pod | 4 way spacer | 134 | each | 0.9 | 120.6 |  |  |  | 0 | -134 | -120.6 | 134 | 120.6 |  | 0%
SOG Waffle Pod | 2 way spacer | 67 | each | 0.75 | 50.25 |  |  |  | 0 | -67 | -50.25 | 67 | 50.25 |  | 0%
Hall Reo Supply
Pad Footings | N12 Bar | 2.33 | tonne | 1215 | 2830.95 |  |  | 1.768 | 2148.12 | -0.562 | -682.83 | 0.562 | 682.83 |  | 75.88%
Ground Beams | R10 ligs | 2.16 | tonne | 1315 | 2840.4 |  |  |  | 0 | -2.16 | -2840.4 | 2.16 | 2840.4 |  | 0%
Ground Beams | Bar | 7.5476 | tonne | 1215 | 9170.334 |  |  |  | 0 | -7.5476 | -9170.334 | 7.5476 | 9170.334 |  | 0%
SOG | N16 Bar | 0.23 | tonne | 1215 | 279.45 |  |  |  | 0 | -0.23 | -279.45 | 0.23 | 279.45 |  | 0%
SOG Waffle Pods | 300mm | 43 | each | 9.2 | 395.6 |  |  |  | 0 | -43 | -395.6 | 43 | 395.6 |  | 0%
SOG Waffle Pods | 375mm | 1115.4885 | each | 14 | 15616.839 |  |  |  | 0 | -1115.4885 | -15616.839 | 1115.4885 | 15616.839 |  | 0%
SOG Waffle Pod | 4 way spacer | 1116 | each | 0.9 | 1004.4 |  |  |  | 0 | -1116 | -1004.4 | 1116 | 1004.4 |  | 0%
SOG Waffle Pod | 2 way spacer | 558 | each | 0.75 | 418.5 |  |  |  | 0 | -558 | -418.5 | 558 | 418.5 |  | 0%
Driveway | R10 ligs | 0.06 | tonne | 1315 | 78.9 |  |  |  | 0 | -0.06 | -78.9 | 0.06 | 78.9 |  | 0%
Driveway | N12 Bar | 0.27 | tonne | 1215 | 328.05 |  |  |  | 0 | -0.27 | -328.05 | 0.27 | 328.05 |  | 0%
Hall Walkway Reo Supply
Ground Beams | Bar | 0.145 | tonne | 1215 | 176.175 |  |  |  | 0 | -0.145 | -176.175 | 0.145 | 176.175 |  | 0%
SOG | Bar | 0.01 | tonne | 1215 | 12.15 |  |  |  | 0 | -0.01 | -12.15 | 0.01 | 12.15 |  | 0%
SOG Waffle Pod | 225mm | 1270.0312 | each | 7.7 | 9779.2406 |  |  |  | 0 | -1270.0312 | -9779.2406 | 1270.0312 | 9779.2406 |  | 0%
SOG Waffle Pod | 4 way spacer | 1270 | each | 0.9 | 1143 |  |  |  | 0 | -1270 | -1143 | 1270 | 1143 |  | 0%
SOG Waffle Pod | 2 way spacer | 635 | each | 0.75 | 476.25 |  |  |  | 0 | -635 | -476.25 | 635 | 476.25 |  | 0%
Courts Reo Supply
Ground Beams | Bar | 6.66 | tonne | 1215 | 8091.9 |  |  |  | 0 | -6.66 | -8091.9 | 6.66 | 8091.9 |  | 0%
SOG | Bar | 0.25 | tonne | 1215 | 303.75 |  |  |  | 0 | -0.25 | -303.75 | 0.25 | 303.75 |  | 0%
SOG Waffle Pod | 225mm | 34 | each | 7.7 | 261.8 |  |  |  | 0 | -34 | -261.8 | 34 | 261.8 |  | 0%
SOG Waffle Pod | 4 way spacer | 77 | each | 0.9 | 69.3 |  |  |  | 0 | -77 | -69.3 | 77 | 69.3 |  | 0%
SOG Waffle Pod | 2 way spacer | 38.5 | each | 0.75 | 28.875 |  |  |  | 0 | -38.5 | -28.875 | 38.5 | 28.875 |  | 0%
Sundries
Ancillaries 5% |  |  |  |  | 5330.66 |  |  |  | 0 | 0 | 0 | 0 | 5330.66 |  | 0%
Diamond Danely Dowel | 6mm | 480 | each | 7.44 | 3571.2 |  |  |  | 0 | -480 | -3571.2 | 480 | 3571.2 |  | 0%
Mesh | SL102 | 464 | Sheet | 93.6 | 43430.4 |  |  |  | 0 | -464 | -43430.4 | 464 | 43430.4 |  | 0%
Mesh | SL82 | 120 | Sheet | 59.8 | 7176 |  |  |  | 0 | -120 | -7176 | 120 | 7176 |  | 0%
Mesh | SL72 | 2 | Sheet | 46.8 | 93.6 |  |  |  | 0 | -2 | -93.6 | 2 | 93.6 |  | 0%
Trench Mesh | 3L11TM | 728 | Sheet | 16.9 | 12303.2 |  |  |  | 0 | -728 | -12303.2 | 728
Pod Freight |  | 13 | each | 1100 | 14300 |  |  |  | 0 | -13 | -14300 | 13 | 14300 |  | 0%
Pod Rails |  | 294 | Bag | 12.5 | 3675 |  |  |  | 0 | -294 | -3675 | 294 | 3675 |  | 0%
Reo Delivery |  | 6 | each | 750 | 4500 |  |  |  | 0 | -6 | -4500 | 6 | 4500 |  | 0%
Pod Scrap Collection |  | 11 | times | 65 | 715 |  |  |  | 0 | -11 | -715 | 11 | 715 |  | 0%
[8 empty] | 3 | 0 | 3 | 0 | -3 | 0 |  | 0%
[8 empty] | 1 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
|  | 9625.9952 |  |  | 167522.0826 | 0 | 0 |  | 2148.12 | -9621.2272 | -160043.3026 | 9621.2272 | 153070.7626 |  | 0%
TOTAL DELIVERIES $ COST | [8 empty] | 0
TOTAL INVOICES PROCESSED:
Other Invoices Processed on Code
Pending Invoices in Jobpac
FORECAST TO GO
Left on Purchase Order
FORECAST FINAL COST

## REO SUPPLY SUMMARY (2)
REO SUPPLY: MCU Sheet
|  |  | PO/ ESTIMATE | ACTUALS
AREA |  | Status | Budget | QTY's | Var $ | Forcast $ TO GO | SITE Percentage Completed | Percentage of Area Completed
Admin building Reo Supply
Admin building Reo Supply |  |  | 23700.7837 | 0 | 23700.7837 | -23700.7837 |  | #REF!
Admin Walkway Reo Supply |  |  | 5696.6715 | 0 | 5696.6715 | -5696.6715 |  | #REF!
Hall Reo Supply |  |  | 46322.7893 | 3243.31 | 43079.4793 | -43079.4793 |  | #REF!
Hall Walkway Reo Supply |  |  | 1678.125 | 0 | 1678.125 | -1678.125 |  | #REF!
Courts Reo Supply |  |  | 26899.85 | 0 | 26899.85 | -26899.85 |  | #REF!
SUBTOTAL TO DATE |  |  | 104298.2195 | 3243.31 | 101054.9095
Percentage Complete | 3.11%
Percentage +/- | -96.89%
Forecast | 104298.2195
Adjusted FFC | 3243.31
FFC Variance to Forecast | 101054.9095

## REO SUPPLY ENTRY
REO SUPPLY: MCU Sheet
|  | PO/ ESTIMATE | [5 empty] | ACTUALS
AREA | TYPE | QTY | UNIT | COST $ | TOTAL |  |  | Delivery 1 |  | Delivery 2 |  | Delivery 3 |  | Total | Qty Var | $ Var | Invoice No. | Date
[8 empty] | QTY's | $ Rate | QTY's | $ Rate | QTY's | $ Rate
Admin building Reo Supply
Pad Footings | N12 Bar | 0.15 | tonne | 1215 | 182.25 | [8 empty] | 0
Ground Beams | R10 ligs | 1.1892 | tonne | 1315 | 1563.798 | [8 empty] | 0
Ground Beams | N12 Bar | 2.0731 | tonne | 1215 | 2518.8165 | [8 empty] | 0
Ground Beams | N16 Bar | 1.69 | tonne | 1215 | 2053.35 | [8 empty] | 0
200mm Slab Reo | N12 Bar | 0.1542 | tonne | 1215 | 187.353 | [8 empty] | 0
Retaining Wall | N16 Bar | 0.7538 | tonne | 1215 | 915.867 | [8 empty] | 0
Retaining Wall | N12 Bar | 0.3509 | tonne | 1215 | 426.3435 | [8 empty] | 0
SOG | N16 Bar | 1.7201 | tonne | 1215 | 2089.9215 | [8 empty] | 0
SOG | SL102 | 67 | Sheet | 93.6 | 6271.2 | [8 empty] | 0
SOG | SL72 | 2 | Sheet | 46.8 | 93.6 | [8 empty] | 0
SOG | 3L11TM | 192 | Sheet | 16.9 | 3244.8 | [8 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
Stairs | N32 | 0.24 | tonne | 1215 | 291.6 | [8 empty] | 0
Driveway | SL82 | 37 | Sheet | 59.8 | 2212.6 | [8 empty] | 0
Driveway | R10 ligs | 0.0525 | tonne | 1315 | 69.0375 | [8 empty] | 0
Driveway | N12 Bar | 0.24738 | tonne | 1215 | 300.5667 | [8 empty] | 0
Driveway | DDD 6mm | 172 | each | 7.44 | 1279.68 | [8 empty] | 0
Area Total |  |  |  |  | 23700.7837 | [8 empty] | 0
Admin Walkway Reo Supply
Ground Beam | N12 Bar | 0.098 | tonne | 1215 | 119.07 | [8 empty] | 0
Ground Beam | N16 Bar | 0.0162 | tonne | 1215 | 19.683 | [8 empty] | 0
Ground Beam | N16 Bar | 0.8959 | tonne | 1215 | 1088.5185 | [8 empty] | 0
Ground Beam | 3L11TM | 82 | Sheet | 16.9 | 1385.8 | [8 empty] | 0
SOG | SL102 | 24 | sheet | 93.6 | 2246.4 | [8 empty] | 0
SOG | SL82 | 14 | sheet | 59.8 | 837.2 | [8 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
Area Total |  |  |  |  | 5696.6715 | [8 empty] | 0
Hall Reo Supply
Pad Footings | N12 Bar | 2.33 | tonne | 1215 | 2830.95 |  |  | 1.768 | 1215 |  |  |  |  | 2148.12 | 0.562 | 682.83
Pad Footings | SL82 | 8 | sheet | 59.8 | 478.4 |  |  | 7 | 59.8 |  |  |  |  | 418.6 | 1 | 59.8
Pad Footings | 3L11TM |  |  | 16.9 |  |  |  | 6 | 16.9 |  |  |  |  | 101.4 | -6 | -101.4
Ground Beams | R10 ligs | 2.16 | tonne | 1315 | 2840.4 | [8 empty] | 0 | 2.16 | 2840.4
Ground Beams | N12 Bar | 0.4095 | tonne | 1215 | 497.5425 | [8 empty] | 0 | 0.4095 | 497.5425
Ground Beams | N16 Bar | 5.5 | tonne | 1215 | 6682.5 | [8 empty] | 0 | 5.5 | 6682.5
Ground Beams | N16 Bar | 1.6381 | tonne | 1215 | 1990.2915 | [8 empty] | 0 | 1.6381 | 1990.2915
Ground Beams | 3L11TM | 340 | Sheet | 16.9 | 5746 | [8 empty] | 0 | 340 | 5746
SOG | SL102 | 187 | Sheet | 93.6 | 17503.2 | [8 empty] | 0 | 187 | 17503.2
SOG | N16 Bar | 0.23 | tonne | 1215 | 279.45 | [8 empty] | 0 | 0.23 | 279.45
Driveway | SL82 | 50 | Sheet | 59.8 | 2990 | [8 empty] | 0 | 50 | 2990
Driveway | DDD 6mm | 308 | each | 7.44 | 2291.52 | [8 empty] | 0 | 308 | 2291.52
Driveway | R10 ligs | 0.06 | tonne | 1315 | 78.9 | [8 empty] | 0 | 0.06 | 78.9
Driveway | N12 Bar | 0.27 | tonne | 1215 | 328.05 | [8 empty] | 0 | 0.27 | 328.05
Bar Chairs for trenchmesh |  | 3.4 | Bags | 14.47 | 49.198 | [8 empty] | 0 | 3.4 | 49.198
Bar Chairs for Mesh |  | 52.1849 | Bags | 14.47 | 755.1162 |  |  | 12 | 14.47 |  |  |  |  | 173.64 | 40.1849 | 581.4762
Plastic Membrane |  | 12.4317 | Rolls | 74.57 | 927.0281 |  |  | 5 | 74.57 |  |  |  |  | 372.85 | 7.4317 | 554.1781
Tie Wire |  | 18.9 | rolls | 2.87 | 54.243 |  |  | 10 | 2.87 |  |  |  |  | 28.7 | 8.9 | 25.543
Reo Delivery | [13 empty] | 0 | 0 | 0
Grey Tape | [7 empty] | 10 | [5 empty] | 0 | -10 | 0
Area Total |  |  |  |  | 46322.7893 | [8 empty] | 3243.31
Hall Walkway Reo Supply
Ground Beams | N16 Bar | 0.1109 | tonne | 1215 | 134.7435 | [8 empty] | 0
Ground Beams | N16 Bar | 0.0341 | tonne | 1215 | 41.4315 | [8 empty] | 0
Ground Beams | 3L11TM | 16 | sheet | 16.9 | 270.4 | [8 empty] | 0
SOG | SL102 | 6 | sheet | 93.6 | 561.6 | [8 empty] | 0
SOG | SL82 | 11 | sheet | 59.8 | 657.8 | [8 empty] | 0
SOG | N16 Bar | 0.01 | tonne | 1215 | 12.15 | [8 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
Area Total |  |  |  |  | 1678.125 | [8 empty] | 0
Courts Reo Supply
Ground Beams | N16 Bar | 6.52 | tonne | 1215 | 7921.8 | [8 empty] | 0
Ground Beams | N16 Bar | 0.14 | tonne | 1215 | 170.1 | [8 empty] | 0
Ground Beams | 3L11TM | 98 | Sheet | 16.9 | 1656.2 | [8 empty] | 0
SOG | SL102 | 180 | Sheet | 93.6 | 16848 | [8 empty] | 0
SOG | N16 Bar | 0.25 | tonne | 1215 | 303.75 | [8 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
SOG | [13 empty] | 0
Area Total |  |  |  |  | 26899.85 | [8 empty] | 0
Sundries
Bar Chairs for trenchmesh |  | 46 | Bags | 14.47 | 665.62 | [8 empty] | 0
Bar Chairs for Mesh |  | 95 | Bags | 14.47 | 1374.65 | [8 empty] | 0
Plastic Membrane |  | 34 | rolls | 74.57 | 2535.38 | [8 empty] | 0
Tie Wire |  | 45 | rolls | 2.87 | 129.15 | [8 empty] | 0
Pod Freight |  | 13 | each | 1100 | 14300 | [8 empty] | 0
Pod Rails |  | 294 | Bag | 12.5 | 3675 | [8 empty] | 0
Reo Delivery |  | 6 | each | 750 | 4500 | [8 empty] | 0
Pod Scrap Collection |  | 11 | times | 65 | 715 | [8 empty] | 0
Area Total |  |  |  |  | 27894.8 | [8 empty] | 0
|  | 2454.2105 |  |  | 132193.0195 | 0 | 0 |  | 1383.61 |  |  |  |  | 6486.62
Check
TOTAL DELIVERIES $ COST | [8 empty] | 0 | [8 empty] | -1383.61
TOTAL INVOICES PROCESSED:
[8 empty] | Other Invoices Processed on Code | [5 empty] | see below ancon waffles
Pending Invoices in Jobpac
FORECAST TO GO | [13 empty] | 55 sheets @ $79.3/ sheet see costx
Left on Purchase Order
FORECAST FINAL COST

## STEEL DOCKET ENTRY
[5 empty] | REO DEL DOCKET ENTRY | [18 empty] | INVOICE ENTRY | [7 empty] | Reo Fix MCU
[5 empty] | 1215 | 1315 |  |  | 16.9 | 93.6 | 59.8 | 46.8 | [7 empty] | 74.57 |  |  |  | $ |  | 115 | [5 empty] | 640 | 3 | 1000 | 15
ENTER↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ | ↓ |  | ↓ | ↓ | ↓ |  | ↓ | ↓
Delivery Date | Doc No | Schedule No | Zone | I.D No. | Qty (t) | Special (t) | L12TM4 | L12TM3 | L11TM3 | Mesh 102 | Mesh 82 | Mesh 72 | 40/50 Deck Chairs/100bg | 50/65 Bar Chairs/100bg | Tie Wire each | Grey Tape | 180/230 Metal Bases | 150mm Top Deck Chairs | 180mm Top Deck Chairs | Black Plastic | Gal Dowels Round | Gal Dowels Diamond | Cradles | Reo Soks | Extras $ | Dels | Total Cost | Inv. Number | INV Date | INV Cost. | var | tonne | mesh | columns | stairs/each landing | Total | INV | INV Date | Inv total | var
[27 empty] | 0 |  |  | 973.9
[27 empty] | 0 |  |  | 10905.97 | [9 empty] | #REF!
[27 empty] | 0 |  |  | 1677.41 | [9 empty] | 0
[27 empty] | 0 | [12 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12583.38 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | TOTAL JAN | FFC | #REF!
Note on T3: Levi Carsburg: 2 types this height is $71.30
Note on U3: Levi Carsburg: 2 types $78.53 this height
Note on Z5: Levi Carsburg: SAFETY CAPS
Note on AA48: Tania Keenan: Key joint
Note on W49: Levi Carsburg: diamond dowell 12.47 each
Note on AA49: Levi Carsburg: 65.05 grey tape 345.56 black plastic