## Sheet1
[6 empty] | Phase One |  |  | Phase Two |  |  | Phase Three
Task | Task Description | Start Date | Finish Date | Duration | % complete | Week One | Week Two | Week Three | Week Four | Week Five | Week Six | Week Seven | Week Eight | Week Nine
1 | Perimeter Scaffold
D | Delivery | 2023-08-27 | 2023-08-27 | 1 | 100%
1.1 | Level 1 | 2023-08-01 | 2023-08-14 | 10 | 50% | [9 empty] | Wet weather,shifted perimeter completion date
1.2 | Level 2 | 2023-08-28 | 2023-09-19 | 15
1.3 | Level 3 | 2023-09-25 | 2023-10-03 | 7
2 | Stretcher Stairs
2.1 | Level 1 - Level 3 East | 2023-08-01 | 2023-09-03 | 9
2.2 | Level 1 - Level 2 North | 2023-08-03 | 2023-09-06 | 9
3 | Construction Stair
3.1 | Level 1 - Level 2 East | 2023-08-15 | 2023-08-18 | 3
3.2 | Level 1 - Level 3 North | 2023-08-16 | 2023-10-01 | 32
3.3 | Level 2 - Level 4 South | 2023-08-27 | 2023-10-05
4 | Handrail
4.1 | Sheet Pile Ground | 2023-08-01 | 2023-08-01 | 1 | 100%
4.2 | 2m high Level 1
4.3 | Loading Bay