## Project Information - Close Out
Linked through from previous pages
Project Close Out Sheet for: |  | Rockpool Pelican Waters | Please PDF and email this close out form along with a copy of the Practical Completion Certificate to: Group - Project Startup Form 5.55
About the Project:
| Project Number: | 21033 | Original Tender Sum: | 0
| Project Name: | Rockpool Pelican Waters | Estimated Margin: | 0
| Entity: | McNab Developments (Qld) Pty Ltd | Final Margin:
Date of Practical Completion:
Date of End of Defect Liability Period:
Project Team - include all who worked on project throughout
| Construction Manager: |  | Estimator:
| Project Manager/s: |  | Design Manager / Coorindator:
CA/s:
| Cadets: |  | HSE Advisor/s:
| Site Manager/s: |  | HSE Business Partner/s:
| Foreman: |  | Quality Representatives:
McNab Team Action List
| Project Manager - all items mandatory |  |  |  | Action lead
| R | Ensure archiving of site files is completed |  |  | Ado
| R | Ensure all ITPs are closed |  |  | Ado
| R | Ensure a copy of PC certificate is saved in the J drive project file |  |  | Reeve
| R | Set up Lessons Learnt meeting with all departments |  |  | Ash
| R | Ensure there is enough leftover materials to rectify defects (i.e. 10% stock) and where it is stored |  |  | Ado
| R | Ensure Procore Defects area has been populated with who will be looking after the defects |  |  | Ado
| R | Temporary Electricity Accounts closed out |  |  | Reeve
| R | Organise a Handover & Commissioning Meeting with Building Manager, invite Customer Care |  |  | Ado
| R | Supply Chain App (SCA) to be updated with ratings and comments on performance of contractors |  |  | Levi
| R | Customer Satisfaction Survey to be completed and forwarded to Marketing |  |  | Ash
HSE Team - all items mandatory
| R | Ensure all CAR entries are closed out |  |  | Clint
| R | All Procore Inspections and Observations are closed |  |  | Clint
Quality - all items mandatory
| R | Reminders in calendar to follow up on defects at 3/6/9 month intervals |  |  | Ash
| R | Reminder in calendar to follow team up at 11 months with client on Third-Party Inspection |  |  | Ash
Accounts
| R | Jobpac changes - set up defect codes for the project |  |  | Reeve
IT
| R | Decommission site |  |  | Reeve
| R | Archive J: drive project file to J:Jobs Post PC |  |  | Reeve
| R | Update status on Procore to DLP |  |  | Reeve
| R | Create an outlook reminder based on end of DLP date to update Procore status to Warranty |  |  | Ash
| R | Time lapse creation if camera has been supplied |  |  | Reeve
Marketing
| R | Phone interview |  |  | Ash
| R | Generate Project Sheet |  |  | Ash
| R | Arrange for professional photography |  |  | Ash
Admin Team
| R | Update 'Projects at McNab' |  |  | Ash
| R | Organise Grace archiving when files are returned to the office |  |  | Reeve
Equipment Hire
| R | Off hire all Plant and Equipment |  |  | Ado
| R | Negotiation of any lost equipment |  |  | Ado