CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

The assessment activities for CPCCBC4003A Select and prepare a construction contract, CPCCBC4016A Administer a construction contract & CPCCBC4032A Apply contract law to sales processescover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Adam Copland |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for CPCCBC4003A | Competent | Not Yet Competent |
| Outcome for CPCCBC4016A | Competent | Not Yet Competent |
| Outcome for CPCCBC4032A | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Adam Copland |
| --- | --- |
| Participant signature | Adam Copland |
| Date | 13/06/2020 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 51 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

Order the following elements of an agreement from 1 to 4.

| Answer | Element Number | Element |  |
| --- | --- | --- | --- |
|  | 2 | Acceptance |  |
|  | 4 | Consideration |  |
|  | 3 | Intention of legal consequences |  |
|  | 1 | Offer |  |

When would an offer be considered to have lapsed?

| Answer | When the time for acceptance expires If the offer is withdrawn before it is accepted After a reasonable time in the circumstances |  |
| --- | --- | --- |

What happens to the offer if new terms are suggested?

| Answer | New terms suggested can be either accepted or rejected. The offer does not change unless the new terms are accepted, otherwise the contract will not be binding. New terms must be written in the contract. |  |
| --- | --- | --- |

What does it mean when a contract is supported by ‘valuable consideration’?

| Answer | Consideration is what each party gives to the other as the agreed price for the other’s promises. One party promises to do something in return for a promise from another party Usually the consideration is the payment of money |  |
| --- | --- | --- |

Identify two (2) parties who may be deemed to not have the capacity to enter into a contract.

| Answer | persons suffering from a mental disability or intoxicated individuals |  |
| --- | --- | --- |

- Outline your understanding of ‘consent’ as it applies to contractual agreements. Identify when ‘apparent consent’ might not actually exist.

| Answer | Consent means that both parties agree to the proposed objectives and terms of a contract, while in sound mind and of their own free will, in order for it to be enforceable. Apparent consent might not exist if one party is being forced to agree to terms of the contract under duress. |  |
| --- | --- | --- |

Identify the building industry regulator in your state and describe its role, particularly with regards to providing advice about contracts.

| Answer | QBCC is the building industry regulator in QLD. It's roll is to ensure the maintenance of proper building standards and remedies for construction in QLD. In regard to providing advice about contracts, the QBCC has templates of contracts to be used for many different types of builds. It educates contractors about their legal rights and responsibilities. |  |
| --- | --- | --- |

Under what laws are domestic building contracts regulated?

| Answer | Queensland Building and Construction Commission Act 1991 |  |
| --- | --- | --- |

Domestic building contracts must be put in writing once the work exceeds what value?

| Answer | $3,300 |  |
| --- | --- | --- |

A commercial building contract must be put in writing before the building work is started if the reasonable cost of the work is more than what amount? Identify the relevant law that imposes this requirement.

| Answer | Stated by the Queensland Building and Construction Commission Act 1991 If commercial work is over $10,000. A contract must be put in place before work is started. |  |
| --- | --- | --- |

Contractors must give the owner a signed copy of the entire contract (including any plans and specifications) within how many days after entering the contract?

| Answer | within 5 business days after entering the contract |  |
| --- | --- | --- |

What are the benefits of having a written contract in place between parties?

| Answer | A signed contract gives both parties a clear and precise understanding of what each party is obliged to do. It makes the agreement clear from the outset. |  |
| --- | --- | --- |

Match the common building contract clauses and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Clauses |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Acceptances | 1 - F | A | Provide specific reasons that allow the contract period to be adjusted |  |
|  | 2 | Cost adjustments | 2 - E | B | A provision for which remedies can be sought if breached |  |
|  | 3 | Extensions of time | 3 - A | C | Specifically outlines the tasks to be completed as part of the construction work |  |
|  | 4 | Payments | 4 - D | D | Outlines the requirements for deposits |  |
|  | 5 | Scope of work | 5 - C | E | Address the risk of rise/fall of expenses |  |
|  | 6 | Term | 6 - B | F | Require that the contract be accepted or rejected by a certain date, otherwise the contract will not be binding |  |

Which of the following are preliminary contracts that a builder could ask a client to sign prior to signing the main contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Contract estimate |  |
|  |  | Contract request |  |
|  |  | Preliminary agreement |  |

True or False (Tick your response): Clauses within pre-contract agreements may carry over into the contract, so it is important to discuss these with the client and come to an agreement.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Identify and explain the purpose of four (4) standardised building construction contracts – two (2) residential and two (2) commercial.

| Answer | Contract name | Description |  |
| --- | --- | --- | --- |
|  | New home constructions contract | For the construction of an entire home |  |
|  | Small building projects (domestic) | Designed to help you organise repairs to a home, duplex or home unit after a natural disaster |  |
|  | Commercial building contracts | A lump sum contract to be used for the construction only of commercial building work with or without a Principal’s agent. |  |
|  | Commercial Cost-Plus contract | A cost-plus contract for use on commercial building projects, where a lump sum price cannot be established, however a fair and reasonable estimate is given. |  |

Identify an appropriate standardised contract that would be suitable for a commercial works job up to $100,000.

| Answer | Commercial Minor Works Contract from Master Builders |  |
| --- | --- | --- |

Identify one (1) standardised residential building contract and explain the maximum value of the work it may be used for.

| Answer | Basic works contracts- This contract can be used as either a Level 1 or 2 contract. This contract is a lump sum contract to be used for work performed on a detached dwelling, including a single duplex, or the renovation, alteration, extension or repair of a home, or removal or re-siting work for detached dwelling where the contract price is up to $80,000 (GST inclusive) |  |
| --- | --- | --- |

Describe the requirements for each of the topics listed below, with regards to residential contracts priced at $20,000. 

In Queensland, these are outlined in the QBCC Consumer Building Guide, which the consumer must sign before work is undertaken.

| Answer | Topics | Definition |  |
| --- | --- | --- | --- |
|  | Builder’s Licence | Builder's license must be held by the contractor completing the works at this price of contract. As it is over $3,300 |  |
|  | Contract price | Must be outlined in contract. |  |
|  | Building approvals and inspections | Approvals for building work must be obtained from a building certifier, who can be either a local government building certifier or a private certifier. Arrangements for inspection should be discussed and agreed with the builder and recorded in the contract |  |
|  | Practical completion and handover | The contract is to define when the build is considered completed and ready for handover. This usually does not include defects if the building can be safely occupied. A building inspection is required before handover. |  |
|  | Implied warranties | Warranties are set out in the contract as to what is actually considered a defect. |  |

- Which of the following documents can be referred to as collectively making up a contract? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Engineer specifications |  |
|  |  | Plans, drawings and specifications |  |
|  |  | Prime Cost Items Schedule |  |
|  |  | Processes for applying for extensions of time |  |
|  |  | Product catalogues |  |
|  |  | Project timelines and schedules |  |
|  |  | Provisional Sums Schedule |  |
|  |  | Rise and fall calculations |  |
|  |  | Site conditions report |  |
|  |  | Soil and sedimentation report |  |

What is the difference between the Prime Cost Item Schedule and the Provisional Sum Schedule in a contract? Provide an example of each type to help explain your response.

| Answer | Prime cost item schedule is a part in the contract that list the cost of materials that don't have an exact price yet. An example of this is taps or shower heads. Prime cost does not list the labour included to install these items. Provisional sums are similar to prime cost but provisional sums include the total approximate price. For example item cost and the labour to install them. |  |
| --- | --- | --- |

Cost adjustment provisions under a contract address risk by providing mechanisms for adjusting contract payment to reflect changes in costs. What can cost adjustment apply to?

| Answer | Cost adjustments can apply to things like extra labour, materials needed. |  |
| --- | --- | --- |

True or False (Tick your response): Variations can be requested by both the client and the builder.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- How should you deal with a client variation request that consequently requires a time extension? How are time extensions addressed within the contract?

| Answer | A variation request that puts the project back in time must be put in writing. The builder will issue the client an ‘extension of time’ form – essentially asking the client to grant you an extension of the contract period to allow for delays caused by the variations |  |
| --- | --- | --- |

Name the Fair Trade legislation that applies in your state and identify which persons/bodies it applies to.

| Answer | Building Industry Fairness (Security of Payment) Act 2017. Applies to people in construction issuing contracts to provide for adjudication of payment disputes under construction contracts, and for other purposes |  |
| --- | --- | --- |

Under the National Consumer Credit Code, before entering into a credit contract, what must the credit provider do?

| Answer | Make reasonable inquiries about why you want to borrow the money Make reasonable inquiries about your financial situation Take reasonable steps to verify your financial situation Assess whether you can meet the financial obligations of the credit contract Determine that the credit contract is ‘not unsuitable’ for you |  |
| --- | --- | --- |

What does the ‘cooling off’ period refer to when undertaking domestic building work with a total contract price of $20,000 or more?

| Answer | The cooling off period is the time where parties may change their mind in going ahead with the terms of the contract. Schedule 1B of the QBCC Act provides for a cooling off period, giving the consumer the option to withdraw from the contract within five days of receipt of the signed contract |  |
| --- | --- | --- |

What are the maximum deposits recommended for a residential building project?

| Answer | For work is priced at $20,000 or more, the maximum deposit is 5%. If the contract price is more than $3,300 and less than $20,000, the deposit must not exceed 10% |  |
| --- | --- | --- |

Throughout the building schedule, progress payments are made when each new stage is ready to commence. 

Identify the recommended stages and percentages for these progress payments on a typical new residential housing building project.

| Answer | Deposit - 5% Base stage- 10% Frame stage- 15% Enclosed stage- 20% Fixing stage- 20% Practical completion- 15% |  |
| --- | --- | --- |

- You have been engaged by a client to construct their residential dwelling for $550,000. Your client is pressuring you to accept a $70,000 deposit to get priority on their construction. Should you accept the deposit? Explain your response.

| Answer | The maximum deposit for this build should be 5% of the total build cost, which would work out to be $27,500. By accepting a larger deposit there is a risk that if the first stage cost more than anticipated you use up the client's money when the extra cost should be in the cost adjustment clause. The extra deposit could throw out the whole pricing schedule. I would advise not to take the money and stick to the contracted prices. |  |
| --- | --- | --- |

- Explain the following types of contractual breach and identify the consequences for the contractual arrangement due to each type of breach.

| Answer | Breach | Explanation |  |
| --- | --- | --- | --- |
|  | Breach of condition under contract | Breaching a "condition" of the contract is when one of the parties do not honour their side of the agreement in the contract. This means the other side may cancel the contract and sue for damages |  |
|  | Breach of warranty under contract | If a warranty is not fulfilled, the nature of the contract is not drastically changed. The aggrieved party cannot elect to terminate or discharge the contract, they may only seek damages. |  |

What does repudiation of a contract mean?

| Answer | Repudiation means when a party to a contract is unwilling to perform their contractual obligations. |  |
| --- | --- | --- |

True or False (Tick your response): In the event of repudiation, the injured party has two options:

- Continue with the contract

- Accept the repudiation and move to terminate the contract

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

Why should you exercise caution, even if you are sure that the other party has repudiated the contract?

| Answer | The ‘injured’ party must act with caution, because if the situation is not deemed to be a repudiation, by acting the terminate the contract the ‘injured’ party may themselves be repudiating the contract and could be liable to pay damages. |  |
| --- | --- | --- |

What does ‘abandonment of contract’ mean?

| Answer | Abandonment of contract is when both parties have conducted themselves in such a way that the original construct is not longer valid. |  |
| --- | --- | --- |

A contract can be terminated for ‘cause’ or for ‘convenience’. 
Explain these two terms.

| Answer | Terminating a contract for 'cause' is where one party fails to meet the terms of the contract, the aggrieved party’s action may be deemed a termination for ‘cause’. Termination of a contract via term of 'convenience’ is where a party is unwilling to perform under the agreement this may be deemed a termination of ‘convenience'. |  |
| --- | --- | --- |

Yes or No (Tick your response): Referring to Section 25 of Schedule 2 of the Competition and Consumer Act 2010 (Cth), would a contract be unfair if it contains a term that permits the builder, but not the client, to terminate the contract?

| Answer |  | Yes |  |  |
| --- | --- | --- | --- | --- |
|  |  | No |  |  |

If time is not of the essence for contract completion and one party fails to perform on time, the other party may terminate the contract after serving notice – specifying a time for performance on the first party. What are the requirements of a valid notice to complete?

| Answer | What must occur to perform the contract A reasonable time in which the contract must be completed A statement of the consequences of not performing in accordance with the notice |  |
| --- | --- | --- |

True or False (Tick your response): Where the notice given (as per Q39. ) is deemed invalid, the innocent party must either serve another notice or prove repudiation by the defaulting party, in order to terminate the contract.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

When is the client owner required to pay the final contract payment? How might this be affected by defects and omissions?

| Answer | The final payment is required to be paid by the client on practical completion of the project. This may be affected by defects as if there is a defect on the project the client may hold money as retention for when the defects are fixed. |  |
| --- | --- | --- |

Explain the concept ‘conditions for completion at the cost of the contractor’.

| Answer | This term basically means that all defects and omissions are to be fixed by the contractor at his own cost if it is within 6 months of practical completion date. |  |
| --- | --- | --- |

Describe what must be stated in a ‘warranty against defects’ about the person who gives the warranty [as per Section 90 of the Competition and Consumer Regulations 2010 (Cth)].

| Answer | It must be stated who is responsible for rectifying the defect |  |
| --- | --- | --- |

Name one (1) person you should consult if you are considering ousting a contractor from a building site.

| Answer | You should consult your lawyer to understand your rights and obligations |  |
| --- | --- | --- |

What document should you refer to if you are considering ousting a contractor from a building site?

| Answer | You would apply the dismissal in the contract |  |
| --- | --- | --- |

How should you handle a customer complaint?

| Answer | While dealing with the complaint remember to stay calm. You should record all complaints, act promptly, do what you say you are going to do and do not make unrealistic promises. |  |
| --- | --- | --- |

How do you reduce the risk of dispute?

| Answer | You should maintain records of discussions, make sure the contract is clear and precise and hold up your side of the contract to reduce the risk of dispute. |  |
| --- | --- | --- |

What is the process for dispute resolution?

| Answer | When dealing with a dispute you refer to your contract first. If a resolution cannot be agreed upon by both parties. You should consult your lawyer then approach QBCC |  |
| --- | --- | --- |

- During your build the client has emailed you at 7:00pm to say they have been to the premises and noticed the installed bath in the bathroom is the wrong style.

You check the contract and the white goods and chattels list selected by the client. You cross check this with the specifications and your materials order and the receivable order sheets. You establish that the bath, as per these details, is correct and there has been no mistake on your part.

Draft a detailed response email to your client alerting them to the pertinent parts of the contract and specification, cross-referencing the details in regard to this item and its installation.

| Answer | Good Morning Client, In regard to your earlier email stating that the bath installed is the wrong style, I have checked the contract and the white goods and chattels list selected by the yourself. I have also cross checked this with the specifications and your materials order and the receivable order sheets. After checking all these documents, the bath as per these details, is correct and there has been no mistake on my part. Feel free to look over the following documents I have referenced (please find all attached to this email). Kind Regards, Adam |  |
| --- | --- | --- |

Where would you find any possible penalties associated with a build?

| Answer | Under the liquidated damage clause in the contract |  |
| --- | --- | --- |

Explain the process for obtaining the final inspection certificate. 
Explain how such documentation is to be stored/lodged.

| Answer | Once practical completion is reached the builder will engage a building certifier, who can be either a local government building certifier or a private certifier, to obtain the final inspection certificate. The local council will require a copy of this certificate. The client is then required to receive the Building Code Assessment from the Building Certifier which grants the right of occupancy to the building owners/users. Both client and builder should keep copy of these documents. |  |
| --- | --- | --- |

- Select and prepare an appropriate standardised contract for the client in the scenario below.

Mr. and Mrs. Cousins intend to engage your company Resilient Homes Pty Ltd (License 141526) in order to build a new low-rise residential dwelling as their future retirement property. Mid-term of this build the clients intend putting their current home on the real estate market for sale.

Additional details:

  - The land has been secured and paid for by the Clients.

  - Proposed contract amount is $580,000.00 plus $85,000 for a kidney shaped 9m x 6m in-ground swimming pool, landscaping, gardens and lawns.

  - Mr. and Mrs. Cousins have finance approval from the Commonwealth Bank for $390,000.00 and the balance in cash. You have received written assurance from the Clients finance company and bank that their finances for the build are fully secured.

  - Mr. and Mrs. Cousins want to pay you $75,000.00 upon signing of the contract to get their build at the top of your priority list.

  - The residential dwelling will be a low set single skin masonry structure with hip and valley roof using glazed clay tiles, contrast metal fascia and gutters and colour/rendered finish on a 1000m² level block upon which there are three large standing hardwood trees which will need to be fully removed.

  - The Clients want the largest tree wood chipped and the chipped bark retained on site for the future gardens and landscaping.

  - Mr. and Mrs. Cousins operate an aluminium window supply company and have advised they will supply all the windows and shower glass for the build.

  - The dwelling has four bedrooms with built-ins. The master bedroom has ensuite with toilet, spa bath and double shower and walk-in robe and dressing area. There is an office, gourmet kitchen with stone bench tops and butler’s pantry, media room, separate open plan dining adjacent to the kitchen plus slate tiled outdoor entertaining area adjacent to the pool, two living areas (formal and informal), two bedrooms share a bathroom with bath, shower, double vanity and toilet and the guest bedroom is ensuited with shower only, toilet and single vanity, there is a powder room (toilet and vanity only), three car garage (one double and one single) and a store/workshop room at the rear of the double bay garage. A slab is to be put down in the back corner of the allotment for a 5m x 3m garden shed.

  - The council approved building plans have been provided by Mr. and Mrs. Cousins these do not include the garden shed slab.

  - The construction period excluding inclement weather and possible delays is 23 weeks

  - Provisional sums are required for the wet areas, alfresco area and living area tiling. (Only the bedrooms are carpeted).

  - Prime costs are required for the solar hot water system and ducted air conditioning

  - Provide fictitious details for all other sections of the contract.

  - 18 solar panels are to be installed on the roof

| Answer |  |  |
| --- | --- | --- |

CPCCBC4003A Select and prepare a construction contract

CPCCBC4016A Administer a construction contract

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | Adam Copland |
| --- | --- |
| Participant signature | Adam Copland |
| Date | 13/06/2020 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4003A Select and prepare a construction contract,

CPCCBC4016A Administer a construction contract &

CPCCBC4032A Apply contract law to sales processes

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to apply contract law to residential and/or commercial construction sales processes. The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - Copy of a contract issued to sub-contractor for your project with relevant AS code on the front - Proof of consultation with sub-contractor regarding contract and contract terms, inclusions and omissions (emails) - Copy of HSE minimum requirements sent as contract condition - Construction contracts that have been developed, signed off, or contributed to by the candidate - Proof of correspondence with client regarding construction contract. Redact sensitive information as required. The assessor is to verify the observer’s comments and provide the outcome for the practical task on the front cover of the Practical Assessment. |  |  |  |
| Resources required: Two (2) pre-contract agreements; two (2) sales contracts (e.g. QBCC contracts), telephone, facsimile machine, computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: |  |  |  |
| Name of observer: |  |  |  |
| Role of observer (Confirm suitability to sign) |  |  |  |
| Email address of observer |  |  |  |
| Signature of observer: |  |  |  |
| Date: | Click here to enter a date. |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Explain to the client: - Essential terms and elements of a valid contract - Types and purposes of agreements employed with the industry (including sales contracts and pre-contract agreements) - The range of documents that collectively make up a contract (including construction schedules, reports, specifications) - The importance of the contract to sales process - Implications of legislation, regulations and codes of practice (including Australian Consumer Law) |  |  |  |
| - Discuss and agree upon clauses of a pre-contract agreement, including payment or deposit. |  |  |  |
| - Ensure the pre-contract agreement is signed and processed according to organisational requirements. |  |  |  |
| - Select appropriate contract and seek expert advice in the preparation of the contract, considering: - Contract rise and fall amounts - Schedule of progress payments - Processes for applying of extensions of time |  |  |  |
| - Break down contract clauses/terms/conditions with the client, including: - Rights, liabilities and potential penalties of parties under the contract - Definitions of building work, common contract terms and procedures, considering – - Practical completion and issuing a final certificate - Defects liability and completion at the cost of the contractor - Effect of ousting the contractor from the building or site - Cooling off periods - Provisional sum and prime cost allowances - Measures to be taken in the event of an anomaly in the rendering of the contract, considering – - Variations - Circumstances that bring about a breach and termination of contract, considering – - Unreasonable/vexatious notice - Abandonment of a contract - Methods for resolving contractual disputes |  |  |  |
| - Effectively communicated with clients, subcontractors, colleagues and external parties using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication - Using technology (including telephone, facsimile, email) - In writing (including drafting responses to queries about contracts) |  |  |  |
| The participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments