## Cashflow
Job Number | Job Description | Retention Type | 10% |  | 44742 |  | 44773 |  | 44804 |  | 44834 |  | 44865 |  | 44895 |  | 44926 |  | 44957 |  | 44985 |  | 45016 |  | 45046 |  | 45077 |  | 45107 |  | 45138 |  | 45169 |  | 45199 |  | 45230 |  | 45260
22066 | ROCKPOOL PELICAN WATERS | BOND/BG | 5%
Commence Date | Job Forecast Completion Date | Contract Completion Date | Total duration
2022-08-01 | 2023-11-28 | 2023-11-28 | 485 | [19 empty] | Claim |  | Claim |  | Claim |  | Claim |  | Claim |  | Claim |  | Claim |  | Claim |  | Claim
Reporting Date | 2023-05-01 17:10 | [21 empty] | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18
Notes / Comments
[5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0
Item | Trade |  | Amount | 2022-06-30 |  | 2022-07-31 |  | 2022-08-31 |  | 2022-09-30 |  | 2022-10-31 |  | 2022-11-30 |  | 2022-12-31 |  | 2023-01-31 |  | 2023-02-28 |  | 2023-03-31 |  | 2023-04-30 |  | 2023-05-31 |  | 2023-06-30 |  | 2023-07-31 |  | 2023-08-31 |  | 2023-09-30 |  | 2023-10-31 |  | 2023-11-30
|  |  |  | Actual |  | Actual |  | Actual |  | Actual |  | Actual |  | Actual |  | Actual |  | Actual |  | Actual |  | Actual |  | Forecast |  | Forecast |  | Forecast |  | Forecast |  | Forecast |  | Forecast |  | Forecast |  | Forecast
|  | FF Revenue | FF Cost | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue |  | Revenue
| DESIGN | [5 empty] | 0 | [5 empty] | 0 |  | 0 | [5 empty] | 0 |  | 0 | 0% | 0
| DESIGN FEES | 139640 | 0 | 7.5% | 10473 | 15% | 20946 | 22.5% | 31419 | 30% | 41892 | 37.5% | 52365 | 45% | 62838 | 52.5% | 73311 | 60% | 83784 | 67.5% | 94257 | 75% | 104730 | 82.5% | 115203 | 90% | 125676 | 95% | 132658 | 100% | 139640 |  | 139640 |  | 139640 |  | 139640 |  | 139640
| TOTAL PRELIMS | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0
| Preliminaries | 4315552.5 | 0 | 1.865% | 80479.8 | 8.52% | 367685.07 | 15.18% | 655100.86 | 21.84% | 942516.66 | 28.5% | 1229932.46 | 35.16% | 1517348.26 | 41.82% | 1804764.05 | 48.48% | 2092179.85 | 55.14% | 2379595.64 | 61.8% | 2667011.44 | 68.46% | 2954427.24 | 75.12% | 3241843.038 | 81.78% | 3529258.8345 | 88.44% | 3816674.631 | 95.1% | 4104090.4275 | 100% | 4315552.5 |  | 4315552.5 |  | 4315552.5
| Development Management Fee | 75000 | 0 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 | 100% | 75000 |  | 75000 |  | 75000 |  | 75000 |  | 75000 |  | 75000 |  | 75000 |  | 75000
| TRADES |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0
| Bulk Earthworks | 201242 | 0 | 10.83% | 21790 | 64.33% | 129464.5 | 86.84% | 174758.55 | 87.17% | 175423.78 | 87.17% | 175423.78 | 87.17% | 175423.78 | 87.17% | 175423.78 | 87.17% | 175423.78 | 87.17% | 175423.78 | 87.17% | 175423.78 | 87.17% | 175423.78 | 88% | 177092.96 | 88% | 177092.96 | 100% | 201242 |  | 201242 |  | 201242 |  | 201242 |  | 201242
| Piling | 1349563 | 0 |  | 0 | 6.069% | 81901.58 | 80.38% | 1084757.58 | 95.34% | 1286673.36 | 100% | 1349563 | 100% | 1349563 | 100% | 1349563 | 100% | 1349563 | 100% | 1349563 | 100% | 1349563 | 100% | 1349563 |  | 1349563 |  | 1349563 |  | 1349563 |  | 1349563 |  | 1349563 |  | 1349563 |  | 1349563
| Termite Treatment | 8580 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100% | 8580 | 100% | 8580 | 100% | 8580 | 100% | 8580 | 100% | 8580 | 100% | 8580 | 100% | 8580 |  | 8580 |  | 8580 |  | 8580 |  | 8580 |  | 8580 |  | 8580 |  | 8580
| Detailed Excavation | 91545 | 0 |  | 0 |  | 0 | 30% | 27463.5 | 85% | 77813.25 | 100% | 91545 | 100% | 91545 | 100% | 91545 | 100% | 91545 | 100% | 91545 | 100% | 91545 | 100% | 91545 |  | 91545 |  | 91545 |  | 91545 |  | 91545 |  | 91545 |  | 91545 |  | 91545
| Concrete Supply | 538076 | 0 |  | 0 |  | 0 |  | 0 | 12.3% | 66183.34 | 28.19% | 151683.62 | 48.46% | 260751.63 | 59.45% | 319886.18 | 70.51% | 379397.38 | 81.99% | 441168.51 | 89.14% | 479640.94 | 89.14% | 479640.94 | 89.14% | 479640.9464 | 89.14% | 479640.9464 | 94% | 505791.44 | 100% | 538076 |  | 538076 |  | 538076 |  | 538076
| Concrete Labour | 529368 | 0 |  | 0 |  | 0 |  | 0 | 7.3% | 38643.86 | 29.32% | 155210.69 | 45.02% | 238321.47 | 53.53% | 283370.69 | 62.79% | 332390.16 | 73.93% | 391361.76 | 79.71% | 421959.23 | 79.71% | 421959.23 | 79.8% | 422435.664 | 79.8% | 422435.664 | 94% | 497605.92 | 100% | 529368 |  | 529368 |  | 529368 |  | 529368
| Concrete Pumping | 143597 | 0 |  | 0 |  | 0 |  | 0 | 12.3% | 17662.43 | 26.18% | 37593.69 | 43.39% | 62306.73 | 53.96% | 77484.94 | 65.7% | 94343.22 | 79.32% | 113901.14 | 86.23% | 123823.69 | 86.23% | 123823.69 | 86.23% | 123823.6931 | 86% | 123493.42 | 94% | 134981.18 | 100% | 143597 |  | 143597 |  | 143597 |  | 143597
| Concrete Testing and Sundries | 62421 | 0 |  | 0 |  | 0 |  | 0 | 12.3% | 7677.78 | 26.3% | 16416.72 | 47.08% | 29387.8 | 52.95% | 33051.91 | 63.4% | 39574.91 | 79.81% | 49818.2 | 89% | 55554.69 | 89% | 55554.69 | 89% | 55554.69 | 89% | 55554.69 | 94% | 58675.74 | 100% | 62421 |  | 62421 |  | 62421 |  | 62421
| Reinforcement Supply | 727261 | 0 |  | 0 |  | 0 |  | 0 | 7.27% | 52871.87 | 22.23% | 161670.12 | 47.88% | 348212.57 | 57.72% | 419775.04 | 71.74% | 521737.04 | 91.51% | 665516.54 | 96.44% | 701370.5 | 96.44% | 701370.5 | 96.5% | 701806.865 | 96.5% | 701806.865 | 97.5% | 709079.475 | 100% | 727261 |  | 727261 |  | 727261 |  | 727261
| Reinforcement Placing | 214152 | 0 |  | 0 |  | 0 |  | 0 | 11.45% | 24520.4 | 18.78% | 40217.74 | 47.32% | 101336.73 | 58.04% | 124293.82 | 73.58% | 157573.04 | 94.66% | 202716.28 | 100% | 214152 | 100% | 214152 | 100% | 214152 | 100% | 214152 | 100% | 214152 |  | 214152 |  | 214152 |  | 214152 |  | 214152
| Formwork | 994001 | 0 |  | 0 |  | 0 |  | 0 | 5% | 49700.05 | 18.58% | 184685.38 | 38.46% | 382292.78 | 55.79% | 554553.15 | 73.69% | 732479.33 | 95.37% | 947978.75 | 100% | 994001 | 100% | 994001 |  | 994001 |  | 994001 |  | 994001 |  | 994001 |  | 994001 |  | 994001 |  | 994001
| Masonry - Blockwork | 1817765 | 0 |  | 0 |  | 0 |  | 0 | 5% | 90888.25 | 30.61% | 556417.86 | 45.67% | 830173.27 | 58.76% | 1068118.71 | 69.66% | 1266255.09 | 82.09% | 1492203.28 | 98.73% | 1794679.38 | 98.73% | 1794679.38 | 99% | 1799587.35 | 99% | 1799587.35 | 100% | 1817765 |  | 1817765 |  | 1817765 |  | 1817765 |  | 1817765
| Waterproofing & Tanking | 256310 | 0 |  | 0 |  | 0 |  | 0 | 5% | 12815.5 | 5% | 12815.5 | 5% | 12815.5 | 5% | 12815.5 | 14.07% | 36062.81 | 19.06% | 48852.68 | 32.01% | 82044.83 | 47.33% | 121311.52 | 56% | 143533.6 | 70% | 179417 | 90% | 230679 | 100% | 256310 |  | 256310 |  | 256310 |  | 256310
| Structural Steel | 176000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 13.84% | 24358.4 | 29.18% | 51356.8 | 39.4% | 69344 | 60.31% | 106145.6 | 70% | 123200 | 70% | 123200 | 90% | 158400 | 100% | 176000 |  | 176000 |  | 176000 |  | 176000
| Roofing | 255327 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 85.44% | 218151.38 | 90% | 229794.3 | 90% | 229794.3 | 95% | 242560.65 | 100% | 255327 |  | 255327 |  | 255327 |  | 255327
| Roof Access & Safety | 28265 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 50% | 14132.5 | 100% | 28265 |  | 28265 |  | 28265 |  | 28265 |  | 28265 |  | 28265
| Aluminium Windows and Doors | 1189248 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1% | 11892.48 | 1% | 11892.48 | 1% | 11892.48 | 5.28% | 62792.29 | 19.28% | 229287.01 | 46.4% | 551811.07 | 68.95% | 819986.49 | 81% | 963290.88 | 83% | 987075.84 | 95% | 1129785.6 | 100% | 1189248 |  | 1189248 |  | 1189248 |  | 1189248
| Metalwork | 646695 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 25.56% | 165295.24 | 52% | 336281.4 | 70% | 452686.5 | 80% | 517356 | 90% | 582025.5 | 95% | 614360.25 | 100% | 646695 |  | 646695
| Rubbish/ Laundry Chute System | 20530 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2% | 410.6 | 2% | 410.6 | 2% | 410.6 | 2% | 410.6 | 2% | 410.6 | 2% | 410.6 | 2% | 410.6 | 90% | 18477 | 100% | 20530 |  | 20530 |  | 20530 |  | 20530 |  | 20530 |  | 20530
| Roller Doors | 5697 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | 100% | 5697 |  | 5697 |  | 5697 |  | 5697 |  | 5697
| Carpentry | 124888 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 18.38% | 22954.41 | 40.84% | 51004.25 | 41% | 51204.08 | 55% | 68688.4 | 75% | 93666 | 87% | 108652.56 | 95% | 118643.6 | 100% | 124888 |  | 124888
| Trusses | 196190 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2% | 3923.8 | 2% | 3923.8 | 2% | 3923.8 | 2% | 3923.8 | 2% | 3923.8 | 42.94% | 84243.98 | 92.94% | 182338.98 | 93% | 182456.7 | 93% | 182456.7 | 100% | 196190 |  | 196190 |  | 196190 |  | 196190 |  | 196190
| Timber Doors and Frames | 252679 | 0 |  | 0 |  | 0 |  | 0 | 3% | 7580.37 | 3% | 7580.37 | 3% | 7580.37 | 5.94% | 15009.13 | 10.51% | 26556.56 | 23.21% | 58646.79 | 34.2% | 86416.21 | 40.66% | 102739.28 | 52% | 131393.08 | 75% | 189509.25 | 90% | 227411.1 | 100% | 252679 |  | 252679 |  | 252679 |  | 252679
| Door and Sundry Hardware | 144710 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 4% | 5788.4 | 35% | 50648.5 | 55% | 79590.5 | 90% | 130239 | 95% | 137474.5 | 100% | 144710 |  | 144710
| Ceilings and Partitions | 3016797 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.5% | 15083.98 | 10.14% | 305903.21 | 20.74% | 625683.7 | 37.17% | 1121343.44 | 60.35% | 1820636.98 | 81% | 2443605.57 | 95% | 2865957.15 | 99% | 2986629.03 | 100% | 3016797 | 100% | 3016797 |  | 3016797 |  | 3016797
| Toilet Partitions | 1557 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 | 100% | 1557 |  | 1557 |  | 1557 |  | 1557 |  | 1557 |  | 1557
| Tiling Supply | 155550 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4.93% | 7668.61 | 15.5% | 24110.25 | 40% | 62220 | 60% | 93330 | 80% | 124440 | 100% | 155550 |  | 155550 |  | 155550
| Tiling Install | 383457 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6.75% | 25883.34 | 18.5% | 70939.545 | 40% | 153382.8 | 60% | 230074.2 | 80% | 306765.6 | 100% | 383457 |  | 383457 |  | 383457
| Cladding | 64499 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 | 50% | 32249.5 | 100% | 64499 |  | 64499 |  | 64499 |  | 64499
| Floor Coverings | 1057328 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2.38% | 25164.4 | 8.35% | 88286.88 | 25% | 264332 | 50% | 528664 | 70% | 740129.6 | 90% | 951595.2 | 100% | 1057328 |  | 1057328 |  | 1057328
| Stainless Steel | 281266 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 5% | 14063.3 | 25% | 70316.5 | 50% | 140633 | 85% | 239076.1 | 100% | 281266 |  | 281266 |  | 281266
| Hydraulic Services | 2420741 | 0 | 1.239% | 30000 | 1.239% | 30000 | 5.555% | 134472.59 | 16.8% | 406684.49 | 31.08% | 752366.3 | 34.73% | 840723.35 | 37.71% | 912861.43 | 43.46% | 1052054.03 | 52.16% | 1262658.5 | 58.27% | 1410565.78 | 67.67% | 1638115.43 | 73% | 1767140.93 | 82% | 1985007.62 | 87% | 2106044.67 | 90% | 2178666.9 | 95% | 2299703.95 | 100% | 2420741 |  | 2420741
| Electrical Services | 2186001 | 0 |  | 0 |  | 0 | 1.24% | 27106.41 | 1.441% | 31501.41 | 3.09% | 67547.43 | 4.97% | 108644.24 | 6.19% | 135313.46 | 13.66% | 298607.73 | 21.37% | 467148.41 | 31.26% | 683343.91 | 37.74% | 824996.77 | 42% | 918120.42 | 52% | 1136720.52 | 70% | 1530200.7 | 80% | 1748800.8 | 90% | 1967400.9 | 100% | 2186001 |  | 2186001
| Mechanical Services | 1556200 | 0 |  | 0 |  | 0 | 1.24% | 19296.88 | 1.24% | 19296.88 | 1.24% | 19296.88 | 2% | 31124 | 2% | 31124 | 11.61% | 180674.82 | 38.04% | 591978.48 | 59.22% | 921581.64 | 69.54% | 1082181.48 | 75% | 1167150 | 80% | 1244960 | 85% | 1322770 | 95% | 1478390 | 100% | 1556200 | 100% | 1556200 |  | 1556200
| Fire Services | 618960 | 0 |  | 0 | 1.24% | 7675.1 | 1.24% | 7675.1 | 1.24% | 7675 | 2% | 12379.2 | 5.64% | 34909.34 | 5.64% | 34909.34 | 31.57% | 195405.67 | 43.71% | 270547.41 | 66.61% | 412289.25 | 81.38% | 503709.64 | 86% | 532305.6 | 90% | 557064 | 95% | 588012 | 100% | 618960 | 100% | 618960 | 100% | 618960 |  | 618960
| Lift Services | 363688 | 0 |  | 0 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 1.24% | 4509.73 | 80% | 290950.4 | 95% | 345503.6 | 95% | 345503.6 | 95% | 345503.6 | 95% | 345503.6 | 100% | 363688 |  | 363688
| Landscaping | 428931 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 30% | 128679.3 | 65% | 278805.15 | 100% | 428931 |  | 428931
| Painting | 496356 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2% | 9927.12 | 12.77% | 63384.66 | 35% | 173724.6 | 55% | 272995.8 | 70% | 347449.2 | 85% | 421902.6 | 90% | 446720.4 | 100% | 496356 |  | 496356
| Render | 283729 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 11.72% | 33253.03 | 61.52% | 174550.08 | 80% | 226983.2 | 90% | 255356.1 | 100% | 283729 |  | 283729 |  | 283729 |  | 283729 |  | 283729
| Signage | 38210 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 | 10% | 3821 | 10% | 3821 | 40% | 15284 | 70% | 26747 | 100% | 38210 |  | 38210
| Trade Contingency | 201521.5 | 0 |  | 0 | 6.66% | 13421.33 | 13.32% | 26842.66 | 19.98% | 40263.99 | 26.64% | 53685.32 | 39.96% | 80527.99 | 46.62% | 93949.32 | 53.28% | 107370.65 | 59.94% | 120791.98 | 66.6% | 134213.31 | 73.26% | 147634.65 | 79.92% | 161055.9828 | 86.58% | 174477.3147 | 93.24% | 187898.6466 | 95% | 191445.425 | 100% | 201521.5 |  | 201521.5 |  | 201521.5
| Joinery & Benchtops | 1497650 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.44% | 6589.66 | 15.87% | 237677.05 | 43% | 643989.5 | 70% | 1048355 | 82% | 1228073 | 90% | 1347885 | 100% | 1497650 |  | 1497650 |  | 1497650
| Sanitary Hardware/ Hydraulic | 735256 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2.5% | 18381.4 | 4.08% | 29998.44 | 4.76% | 34998.18 | 18% | 132346.08 | 43% | 316160.08 | 62% | 455858.72 | 85% | 624967.6 | 100% | 735256 |  | 735256 |  | 735256
| PROVISIONAL SUMS |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0
| Corporate Signage | 35000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 75% | 26250 | 75% | 26250 | 90% | 31500 | 100% | 35000 | 100% | 35000 | 100% | 35000 |  | 35000
| Wayfinding Signage | 30000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 | 50% | 15000 | 100% | 30000 |  | 30000
| Corner and Door Protection | 30000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 | 100% | 30000 |  | 30000 |  | 30000 |  | 30000
| Reception, Hairsalon and | 22000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 | 25% | 5500 | 50% | 11000 | 100% | 22000 |  | 22000 |  | 22000 |  | 22000
| Nurse Call, Electronic Access | 600000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 14.66% | 87960 | 26.66% | 159960 | 29.99% | 179940 | 40% | 240000 | 60% | 360000 | 80% | 480000 | 100% | 600000 |  | 600000 |  | 600000 |  | 600000
| Interior Designer Lounge | 50000 | 0 |  | 0 |  | 0 | 100% | 50000 | 100% | 50000 | 100% | 50000 | 100% | 50000 | 100% | 50000 | 100% | 50000 | 100% | 50000 | 100% | 50000 | 100% | 50000 |  | 50000 |  | 50000 | 50% | 50000 | 100% | 50000 |  | 50000 |  | 50000 |  | 50000
| Metalwork AL1 Design | 100000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 | 50% | 50000 | 100% | 100000 |  | 100000 |  | 100000 |  | 100000
| D&C Margin | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0
| Margin Allowance | 3108400 | 0 | 0.4592% | 14274.28 | 2.35% | 73047.4 | 7.44% | 231264.96 | 11.32% | 351870.88 | 17.04% | 529671.36 | 21.57% | 670481.88 | 24.97% | 776167.48 | 31.29% | 972618.36 | 39.79% | 1236832.36 | 48.65% | 1512236.6 | 58.43% | 1816238.12 | 67.18% | 2088099.3249 | 76.44% | 2376004.2779 | 84.86% | 2637914.2051 | 92.25% | 2867581.2183 | 100% | 3108400 |  | 3108400 |  | 3108400
[9 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0
| Variations | 410185.47 | 0 |  | 0 |  | 0 | 100% | 15769 | 70.49% | 15769 | 52.99% | 23160.65 | 66.94% | 140692 | 74.8% | 157213.99 | 71.9% | 174085.03 | 58.28% | 192125.57 | 66.72% | 219956.12 | 60.78% | 249326.12 | 75% | 307639.1025 | 80% | 328148.376 | 90% | 369166.923 | 95% | 389676.1965 | 100% | 410185.47 |  | 410185.47 |  | 410185.47
|  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[7 empty] | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0% | 0
75
76 | Check Line | 0 | #REF! |  | 0 |  | 0 |  | 0 |  | -41362.28 |  | 0 |  | 140692 |  | 0 |  | 0 |  | -6472320.41 |  | 137997.24 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Revenue | Cummulative Total Revenue | 34677585.47 | 0 | 0.6771% | 232017.08 | 2.345% | 803650.71 | 7.483% | 2565436.82 | 11.36% | 3895434.28 | 16.99% | 5835545 | 21.84% | 7531316.3 | 25.27% | 8713905.51 | 31.57% | 10895159.49 | 39.79% | 13799724.1 | 48.82% | 16889192.18 | 58.46% | 20272044.51 | 68.06% | 23602659.9517 | 77.38% | 26835062.3585 | 85.93% | 29797971.2307 | 93.38% | 32380666.0273 | 98.18% | 34047724.82 | 100% | 34677585.47 | 100% | 34677585.47
| Monthly Revenue |  |  |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1695771.3 |  | 1182589.21 |  | 2181253.98 |  | 2904564.61 |  | 3089468.08 |  | 3382852.33 |  | 3330615.4417 |  | 3232402.4068 |  | 2962908.8722 |  | 2582694.7966 |  | 1667058.7927 |  | 629860.65 |  | 0
| Totals (Prev Month) | [5 empty] | 512838.5211 |  | 1699464.6542 |  | 1762062.0076 |  | 1770199.5996 |  | 1594565.5352 |  | 1117577.9796 |  | 1616975.166 |  | 2796332.0328 |  | 3001205.7157 |  | 3358517.4868 |  | 3405127.025 |  | 3311827.7457 |  | 3036447.8575 |  | 2292729.2886 |  | 1673348.7665 |  | 629860.65 |  | 0
| Difference |  |  | #DIV/0! | 232017.08 | 11.46% | 58795.1089 | 3.667% | 62321.4558 | -24.52% | -432064.5476 | 9.181% | 162519.1504 | 6.347% | 101205.7648 | 5.817% | 65011.2304 | 34.9% | 564278.814 | 3.871% | 108232.5772 | 2.941% | 88262.3643 | 0.7246% | 24334.8432 | -2.188% | -74511.5834 | -2.398% | -79425.3389 | -2.422% | -73538.9852 | 12.65% | 289965.508 | -0.3759% | -6289.9738 | 0% | 0 | #DIV/0! | 0
CM DATA
|  | 2022-06-01 | 34267400 |  | 232017.08 |  | 500000 |  | 1800000 |  | 1800000 |  | 1700000 |  | 1700000 |  | 2000000 |  | 2300000 |  | 2800000 |  | 3200000 |  | 3200000 |  | 2900000 |  | 2600000 |  | 2300000 |  | 2200000 |  | 2200000 |  | 835382.92
|  | 2022-07-01 | 34267400 |  | 232017.08 |  | 571633.63 |  | 1600000 |  | 1600000 |  | 1700000 |  | 1700000 |  | 1600000 |  | 2000000 |  | 2800000 |  | 3300000 |  | 3300000 |  | 3000000 |  | 2800000 |  | 2500000 |  | 2400000 |  | 2400000 |  | 763749.29
|  | 2022-09-01 | 34283169 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1600000 |  | 1700000 |  | 1700000 |  | 1600000 |  | 2000000 |  | 2800000 |  | 3300000 |  | 3300000 |  | 3000000 |  | 2800000 |  | 2500000 |  | 2400000 |  | 2400000 |  | 617732.18
|  | 2022-10-01 | 34289769 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1600000 |  | 1500000 |  | 1300000 |  | 1500000 |  | 3000000 |  | 3300000 |  | 3300000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 2400000 |  | 2400000 |  | 1094334.72
|  | 2022-11-01 | 34322487.75 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1500000 |  | 1000000 |  | 1500000 |  | 3000000 |  | 3300000 |  | 3300000 |  | 3000000 |  | 3000000 |  | 3000000 |  | 2400000 |  | 2400000 |  | 1094334.72
|  | 2022-12-01 | 34477566.47 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1695771.3 |  | 1000000 |  | 1500000 |  | 2300000 |  | 3000000 |  | 3300000 |  | 3500000 |  | 3300000 |  | 3200000 |  | 2400000 |  | 2400000 |  | 1053642.14
|  | 2023-01-01 | 34477566.47 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1695771.3 |  | 1182589.21 |  | 1500000 |  | 2300000 |  | 3000000 |  | 3300000 |  | 3500000 |  | 3300000 |  | 3200000 |  | 2400000 |  | 2400000 |  | 871052.93
|  | 2023-02-01 | 34509526.47 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1695771.3 |  | 1182589.21 |  | 2181253.98 |  | 2600000 |  | 3000000 |  | 3300000 |  | 3500000 |  | 3300000 |  | 3200000 |  | 2400000 |  | 1500000 |  | 821758.95
|  | 2023-03-01 | 34597051.16 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1695771.3 |  | 1182589.21 |  | 2181253.98 |  | 2904564.61 |  | 3000000 |  | 3300000 |  | 3500000 |  | 3300000 |  | 3200000 |  | 2400000 |  | 1500000 |  | 604719.03
|  | 2023-04-01 | 34597051.16 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1695771.3 |  | 1182589.21 |  | 2181253.98 |  | 2904564.61 |  | 3089468.08 |  | 3300000 |  | 3400000 |  | 3300000 |  | 3000000 |  | 2300000 |  | 1500000 |  | 915250.95
|  | 2023-05-01 17:10 | 20264652.54 |  | 232017.08 |  | 571633.63 |  | 1761786.11 |  | 1329997.46 |  | 1932718.75 |  | 1695771.3 |  | 1182589.21 |  | 2181253.98 |  | 2904564.61 |  | 3089468.08 |  | 3382852.33
14412932.93
ACCOUNTS USE ONLY
| Cummulative Retention Held | 1733879.2735 | 866939.6368 |  | 23201.708 |  | 80365.071 |  | 256543.682 |  | 389543.428 |  | 582815.303 |  | 753131.63 |  | 871390.551 |  | 1089515.949 |  | 1379972.41 |  | 1688919.218 |  | 1733879.2735 |  | 1733879.2735 |  | 1733879.2735 |  | 1733879.2735 |  | 1733879.2735 |  | 1733879.2735 |  | 1733879.2735 |  | 866939.6368
| Cummulative Revenue |  |  |  | 208815.372 |  | 723285.639 |  | 2308893.138 |  | 3505890.852 |  | 5245337.727 |  | 6778184.67 |  | 7842514.959 |  | 9805643.541 |  | 12419751.69 |  | 15200272.962 |  | 18538165.2365 |  | 21868780.6782 |  | 25101183.085 |  | 28064091.9572 |  | 30646786.7538 |  | 32313845.5465 |  | 32943706.1965 |  | 33810645.8333
| McNab Labour |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| Subbie Retention Held | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| Cummulative Costs (Exc Labour) |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Monthly Revenue |  |  |  | 208815.372 |  | 514470.267 |  | 1585607.499 |  | 1196997.714 |  | 1739446.875 |  | 1532846.943 |  | 1064330.289 |  | 1963128.582 |  | 2614108.149 |  | 2780521.272 |  | 3337892.2745 |  | 3330615.4417 |  | 3232402.4068 |  | 2962908.8722 |  | 2582694.7966 |  | 1667058.7927 |  | 629860.65 |  | 866939.6368
| Monthly Costs (Exc Labour) |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Reporting Cashflow |  |  | 100% | 208815.372 | 100% | 514633.63 | 100% | 1585786.11 | 100% | 1196997.46 | 100% | 1739718.75 | 99.54% | 1525771.3 | 100% | 1064589.21 | 65.3% | 1282000 | 76.89% | 2010000 | 96.78% | 2691000 | 97.52% | 3255000 | 105.1% | 3500000 | 102.1% | 3300000 | 108% | 3200000 | 92.93% | 2400000 | 144% | 2400000 | 138.3% | 871052.93 | 100% | 867000
| Ret Held | 1677.5655 |  |  | 23201.708 |  | 57000 |  | 176000 |  | 133000 |  | 193000 |  | 170000 |  | 118000 |  | 218000 |  | 290000 |  | 309000 |  | 45000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -867000
| Costs |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Accrual
Job Number | Job Description | Retention Type | 10% |  |  | 0 |  | 0 |  | 0 | #REF!
22066 | ROCKPOOL PELICAN WATERS | BOND/BG | 5%
Commence Date | Job Forecast Completion Date | Contract Completion Date | Total duration
2022-08-01 | 2023-11-28 | 2023-11-28 | 485
Reporting Date | 2020-12-13
Notes / Comments
Item | Trade |  | Amount
[5 empty] | Actual |  | Actual |  | Over/Under Claim |  | Margin to Date
|  | FF Revenue | FF Cost | FF Margin | Revenue |  | Costs |  | Costs |  | Based on Trades
Design
| DESIGN | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
Preliminaries
| Preliminaries | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
Trades
| DEMOLITION | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| BULK EARTHWORKS & RETENTION | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| ROADWORKS & CIVIL | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| PILING AND PIERING | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| CONCRETE WORK | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| RE-INFORCEMENT | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| FORMWORK | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| PRE-CAST & TILT PANELS | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| MASONRY | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| STRUCTUAL STEEL | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| METAL WORKS | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| ROOFING, RF PLUMBING, WALL CLA | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| RENDERING & WATERPROOFING | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| CARPENTRY | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| ALUMINIUM DOORS AND WINDOWS | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| DOORS & FRAMES, HARDWARE | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| CEILINGS & PARTITIONS | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| JOINERY | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| STAINLESS STEEL | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| FLOOR COVERINGS | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| TILING | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| PAINTING | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| HYDRAULIC, PLUMBING,DRAINAGE | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| ELECTRICAL SERVICES | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| MECHANICAL SERVICES | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| VERTICAL & HORIZONTAL TRANSPOR | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| FIRE SERVICES | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| LANDSCAPING and IRRIGATION | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| FENCING | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| SIGNAGE | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
[5 empty] | 0% | 0
| SUNDRY INCOME | 0 | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
| VARIATIONS | 410185.47 | 0 | 410185.47 | 60.78% | 249326.12 | 0% | 0 | 60.78% | 0 | 249326.12
| PENDING INVOICES |  |  |  |  | 0 |  | 0 |  | 0 | 0
57
58 | Check Line | -34267400 | -32762739.68 |  |  | -20022718.39 |  | -16826594.5 |  | 0
| Cummulative Totals | 410185.47 | 0 | 410185.47 | 60.78% | 249326.12 | 0% | 0 | 0% | 0 | 249326.12
100%
| Accrual |  |  | 0
R&O Margin
| Variance for R&O Margin |  |  | -249326.12

## Charts
|  | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31
|  | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue | Revenue
Current | 2023-05-01 17:10 | 232017.08 | 803650.71 | 2565436.82 | 3895434.28 | 5835545 | 7531316.3 | 8713905.51 | 10895159.49 | 13799724.1 | 16889192.18 | 20272044.51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 2018-09-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-10-31
| 2018-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018-12-31
2019-01-31
2019-02-28
2019-03-31
2019-04-30
2019-05-31
2019-06-30
2019-07-31
2019-08-31
2019-09-30
2019-10-31
2019-11-30
2019-12-31
2020-01-31
2020-02-29
2020-03-31
2020-04-30
2020-05-31
2020-06-30
2020-07-31
2020-08-31

## Info
34677585.47 | Total Contract | 45047.715 | Job Description |  | Job Contract Commencement Date | Job Forecast Completion Date | Job Current Contract Completion Date | Bank Guarantee Amount | Bank Guarantee Amount | Bank Guarantee Amount | [9 empty] | Total Actual | 15319157.86
20272044.51 | Claimed To Date | 22066 | ROCKPOOL PELICAN WATERS | BOND/BG | 2022-08-01 | 2023-11-28 | 2023-11-28 | [12 empty] | Total Incurred | 1507436.64
16564506.06 | Prev Claim | [18 empty] | Total Prev Act | 15319157.86
[20 empty] | Exp Amt | 16826594.5
[20 empty] | Total Forecast | 32762739.68
[20 empty] | % Complete Labour | #DIV/0!
[20 empty] | Total Expense Amt | Cashflow Code
#N/A |  | Firm Code | Job Number | Job Description | Trade Code | Item Number | Description | Claimable Amount | Current Claimed Amount | Previous Claimed Amount | Firm Code | Job Number | Cost Code | Cost Type | Job Code Description | Actual Cost Amount | Incurred Cost Amount | Prev Act | Forecast Final Cost Amount
#N/A | [10 empty] | 202209 | 45047.715
DESIGN FEES |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 01 | 01 | DESIGN FEES | 139640 | 115203 | 0 | 2022-11-11 | INV-1356 | LIZA01 | LIZARD CONCRETE PUMPING | PENDING INVOICES |  | 1264 |  |  | 1264 | #N/A
Development Management Fee |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 02 | 01 | Development Management Fee | 75000 | 75000 | 75000 | 2023-03-13 | INV-8594 | SUNC20 | SUNCOAST CONCRETE DRILLING | PENDING INVOICES |  | 282.8 | P |  | 282.8 | #N/A
Preliminaries |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 02 | 02 | Preliminaries | 4315552.5 | 2954427.24 | 2667011.44 | 2023-03-22 | INV-8699 | SUNC20 | SUNCOAST CONCRETE DRILLING | PENDING INVOICES |  | 1043.97 | P |  | 1043.97 | #N/A
Bulk Earthworks |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 01 | Bulk Earthworks | 201242 | 175423.78 | 175423.78 | 2023-03-24 | INV-8733 | SUNC20 | SUNCOAST CONCRETE DRILLING | PENDING INVOICES |  | 516.3 | P |  | 516.3 | #N/A
Piling |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 02 | Piling | 1349563 | 1349563 | 1349563 | 2023-04-04 | 212954561 | HAFE01 | HAFELE AUSTRALIA PTY LTD | PENDING INVOICES |  | 45 |  |  | 45 | #N/A
Termite Treatment |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 03 | Termite Treatment | 8580 | 8580 | 8580 | 2023-04-04 | 212954708 | HAFE01 | HAFELE AUSTRALIA PTY LTD | PENDING INVOICES |  | 138 |  |  | 138 | #N/A
Detailed Excavation |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 04 | Detailed Excavation | 91545 | 91545 | 91545 | 2023-04-13 | INV-0992 | M&CJ01 | M&C JOINT SEALING PTY LTD | PENDING INVOICES |  | 10613.4 |  |  | 10613.4 | #N/A
Concrete Supply |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 05 | Concrete Supply | 538076 | 479640.94 | 479640.94 | 2023-04-18 | 9/01367265 | BUNN01 | BUNNINGS BUILDING SUPPLIES PTY | PENDING INVOICES |  | 391.95 | P |  | 391.95 | #N/A
Concrete Labour |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 06 | Concrete Labour | 529368 | 421959.23 | 421959.23 | 2023-04-19 | 94789 | NORT55 | NORTH QLD CUSTOMS SERVICES | PENDING INVOICES |  | 9124.4 |  |  | 9124.4 | #N/A
Concrete Pumping |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 07 | Concrete Pumping | 143597 | 123823.69 | 123823.69 | 2023-04-19 | 9/99850072 | BUNN01 | BUNNINGS BUILDING SUPPLIES PTY | PENDING INVOICES |  | 217.27 | P |  | 217.27 | #N/A
Concrete Testing and Sundries |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 08 | Concrete Testing and Sundries | 62421 | 55554.69 | 55554.69 | 2023-04-20 | 9/00964946 | BUNN01 | BUNNINGS BUILDING SUPPLIES PTY | PENDING INVOICES |  | 462.01 | P |  | 462.01 | #N/A
Reinforcement Supply |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 09 | Reinforcement Supply | 727261 | 701370.5 | 701370.5 | 2023-04-24 | 00046948 | ACTI02 | ACTIVE CRANE HIRE PTY LTD | PENDING INVOICES |  | 6200 |  |  | 6200 | #N/A
Reinforcement Placing |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 10 | Reinforcement Placing | 214152 | 214152 | 214152 | 2023-04-24 | 00199425 | WHAL01 | WHALE BINS | PENDING INVOICES |  | 1200 | P |  | 1200 | #N/A
Formwork |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 11 | Formwork | 994001 | 994001 | 994001 | 2023-04-24 | 00989/7 | ASPI03 | ASPIRE TOWER CRANES | PENDING INVOICES |  | 37645.47 |  |  | 37645.47 | #N/A
Masonry - Blockwork |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 12 | Masonry - Blockwork | 1817765 | 1794679.38 | 1794679.38 | 2023-04-24 | I007453 | FITO01 | FITOUT GLASS & ALUMINIUM | PENDING INVOICES |  | 148623.5 |  |  | 148623.5 | #N/A
Waterproofing & Tanking |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 13 | Waterproofing & Tanking | 256310 | 121311.52 | 82044.83 | 2023-04-24 | LWI449 | LAGW01 | LAGWORKS PTY LTD | PENDING INVOICES |  | 4740 |  |  | 4740 | #N/A
Structural Steel |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 14 | Structural Steel | 176000 | 106145.6 | 69344 | 2023-04-25 | 22066-08 | TKFO01 | TK FORMBUILD CONSTRUCTIONS PTY | PENDING INVOICES |  | 70834 |  |  | 70834 | #N/A
Roofing |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 15 | Roofing | 255327 | 218151.38 | 0 | 2023-04-25 | 7294 | CUST09 | CUSTOM METAL SOLUTIONS | PENDING INVOICES |  | 58500 |  |  | 58500 | #N/A
Roof Access & Safety |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 16 | Roof Access & Safety | 28265 | 0 | 0 | 2023-04-25 | INV-2933 | MARS07 | MARSH HEIGHT SAFETY (AUST) | PENDING INVOICES |  | 34081 |  |  | 34081 | #N/A
Aluminium Windows and Doors |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 17 | Aluminium Windows and Doors | 1189248 | 819986.49 | 551811.07 | 2023-04-26 | 00002643 | BEEL02 | BEEL WELDING & FABRICATION | PENDING INVOICES |  | 27981 |  |  | 27981 | #N/A
Metalwork |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 18 | Metalwork | 646695 | 165295.24 | 0 | 2023-04-26 | 00004903 | MMWA01 | M & M WATERPROOFING BRISBANE | PENDING INVOICES |  | 1250 |  |  | 1250 | #N/A
Rubbish/ Laundry Chute System |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 19 | Rubbish/ Laundry Chute System | 20530 | 410.6 | 410.6 | 2023-04-26 | 00020481 | BOUT06 | BOUTIQUE KITCHENS & JOINERY-FA | PENDING INVOICES |  | 57877.22 |  |  | 57877.22 | #N/A
Roller Doors |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 20 | Roller Doors | 5697 | 0 | 0 | 2023-04-26 | 00199386 | WHAL01 | WHALE BINS | PENDING INVOICES |  | 1200 | P |  | 1200 | #N/A
Carpentry |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 21 | Carpentry | 124888 | 51004.25 | 22954.41 | 2023-04-26 | 01503719 | BULK01 | BULK FUEL AUSTRALIA | PENDING INVOICES |  | 556.59 | P |  | 556.59 | #N/A
Trusses |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 22 | Trusses | 196190 | 182338.98 | 84243.98 | 2023-04-26 | 1300 | UNIV24 | UNIVERSAL COATINGS PTY LTD | PENDING INVOICES |  | 117993.7 |  |  | 117993.7 | #N/A
Timber Doors and Frames |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 23 | Timber Doors and Frames | 252679 | 102739.28 | 86416.21 | 2023-04-26 | 16164 | YORK02 | YORKE CONSULTING PTY LTD | PENDING INVOICES |  | 1187.31 | P |  | 1187.31 | #N/A
Door and Sundry Hardware |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 24 | Door and Sundry Hardware | 144710 | 0 | 0 | 2023-04-26 | 22066-01 | UNDE06 | UNDERCOVER ROOFING PTY LTD | PENDING INVOICES |  | 178941.9 |  |  | 178941.9 | #N/A
Ceilings and Partitions |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 25 | Ceilings and Partitions | 3016797 | 1820636.98 | 1121343.44 | 2023-04-26 | 24931837 | KENN01 | KENNARDS HIRE | PENDING INVOICES |  | 542.63 |  |  | 542.63 | #N/A
Toilet Partitions |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 26 | Toilet Partitions | 1557 | 0 | 0 | 2023-04-26 | 25593 | CABL04 | CABLECOMM PTY LTD | PENDING INVOICES |  | 34183.2 |  |  | 34183.2 | #N/A
Tiling Supply |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 27 | Tiling Supply | 155550 | 7668.61 | 0 | 2023-04-26 | 32744925 | REEC02 | REECE PTY LTD | PENDING INVOICES |  | 3316 | P |  | 3316 | #N/A
Tiling Install |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 28 | Tiling Install | 383457 | 25883.34 | 0 | 2023-04-26 | 32744927 | REEC02 | REECE PTY LTD | PENDING INVOICES |  | 725 |  |  | 725 | #N/A
Cladding |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 29 | Cladding | 64499 | 0 | 0 | 2023-04-26 | INV-0924 | DYFA03 | DYFA PLUMBING | PENDING INVOICES |  | 171338.55 |  |  | 171338.55 | #N/A
Floor Coverings |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 30 | Floor Coverings | 1057328 | 88286.88 | 25164.4 | 2023-04-26 | TSS/17528 | TRAD08 | TRADELINE SITE SOLUTIONS | PENDING INVOICES |  | 285.4 | P |  | 285.4 | #N/A
Stainless Steel |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 31 | Stainless Steel | 281266 | 0 | 0 | 2023-04-27 | 00024328 | RICK01 | RICKS DOORS | PENDING INVOICES |  | 43386.17 |  |  | 43386.17 | #N/A
Hydraulic Services |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 32 | Hydraulic Services | 2420741 | 1638115.43 | 1410565.78 | 2023-04-27 | 614801 | FORK01 | FORKFORCE | PENDING INVOICES |  | 1720 |  |  | 1720 | #N/A
Electrical Services |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 33 | Electrical Services | 2186001 | 824996.77 | 683343.91 | 2023-04-28 | 106001329 | ACOR01 | ACOR CONSULTANTS | PENDING INVOICES |  | 4247.5 |  |  | 4247.5 | #N/A
Mechanical Services |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 34 | Mechanical Services | 1556200 | 1082181.48 | 921581.64 | 2023-04-28 | INV-1635 | SIXS01 | SIX STAR TILING | PENDING INVOICES |  | 118943.62 |  |  | 118943.62 | #N/A
Fire Services |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 35 | Fire Services | 618960 | 503709.64 | 412289.25 | 2023-05-01 | 7384646 | AUSC05 | AUSCO MODULAR | PENDING INVOICES |  | 7097.58 |  |  | 7097.58 | #N/A
Lift Services |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 36 | Lift Services | 363688 | 4509.73 | 4509.73 | 30 | 22066 | D1A | CT | Access Consultant | 0 | 0 | 0 | 500 | 0 | #N/A
Landscaping |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 37 | Landscaping | 428931 | 0 | 0 | 30 | 22066 | D1AE | CT | Acoustic Engineer | 1750 | 0 | 1750 | 6950 | 1750 | #N/A
Painting |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 38 | Painting | 496356 | 63384.66 | 9927.12 | 30 | 22066 | D1BC | CT | Building Certifier | 0 | 0 | 0 | 0 | 0 | #N/A
Render |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 39 | Render | 283729 | 174550.08 | 33253.03 | 30 | 22066 | D1CE | CT | Civil Engineer | 11402.27 | 0 | 11402.27 | 16064.77 | 11402.27 | #N/A
Signage |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 40 | Signage | 38210 | 0 | 0 | 30 | 22066 | D1EE | CT | Fire / Elec / Mech Consultant | 4920 | 0 | 4920 | 23160 | 4920 | #N/A
Trade Contingency |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 41 | Trade Contingency | 201521.5 | 147634.65 | 134213.31 | 30 | 22066 | D1F | CT | Facade (Compliance Peer Revie | 0 | 0 | 0 | 0 | 0 | #N/A
Joinery & Benchtops |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 42 | Joinery & Benchtops | 1497650 | 237677.05 | 6589.66 | 30 | 22066 | D1FE | CT | Fire Engineer | 0 | 0 | 0 | 3800 | 0 | #N/A
Sanitary Hardware/ Hydraulic |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 03 | 43 | Sanitary Hardware/ Hydraulic | 735256 | 34998.18 | 29998.44 | 30 | 22066 | D1FS | CT | Fire Services | 0 | 0 | 0 | 0 | 0 | #N/A
Margin Allowance |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 04 | 01 | Margin Allowance | 3108400 | 1816238.12 | 1512236.6 | 30 | 22066 | D1HE | CT | Hydraulic Engineer | 2500 | 0 | 2500 | 5570 | 2500 | #N/A
Corporate Signage |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 05 | 01 | Corporate Signage | 35000 | 0 | 0 | 30 | 22066 | D1HV | CT | HV Electrical Engineer | 0 | 0 | 0 | 0 | 0 | #N/A
Wayfinding Signage |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 05 | 02 | Wayfinding Signage | 30000 | 0 | 0 | 30 | 22066 | D1KS | CT | Kitchen and Laundry Specialist | 8500 | 0 | 8500 | 15000 | 8500 | #N/A
Corner and Door Protection |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 05 | 03 | Corner and Door Protection | 30000 | 0 | 0 | 30 | 22066 | D1LD | CT | Landscaping | 1960 | 0 | 1960 | 7415 | 1960 | #N/A
Reception, Hairsalon and |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 05 | 04 | Reception, Hairsalon and | 22000 | 0 | 0 | 30 | 22066 | D1ME | CT | Mechanical Engineer | 0 | 0 | 0 | 0 | 0 | #N/A
Nurse Call, Electronic Access |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 05 | 05 | Nurse Call, Electronic Access | 600000 | 179940 | 159960 | 30 | 22066 | D1NC | CT | Section J | 4250 | 0 | 4250 | 9250 | 4250 | #N/A
Interior Designer Lounge |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 05 | 06 | Interior Designer Lounge | 50000 | 50000 | 50000 | 30 | 22066 | D1SE | CT | Structural Engineer | 13765 | 0 | 13765 | 26165 | 13765 | #N/A
Metalwork AL1 Design |  | 30 | 22066 | ROCKPOOL PELICAN WATERS | 05 | 07 | Metalwork AL1 Design | 100000 | 0 | 0 | 30 | 22066 | D1SL | CT | External Programming | 810 | 0 | 810 | 810 | 810 | #N/A
Sundry Income |  |  | 22066 | ROCKPOOL PELICAN WATERS |  | 98 | Sundry Income | 0 | 0 |  | 30 | 22066 | D1SP | CT | Structural Peer Review | 5200 | 0 | 5200 | 5200 | 5200 | #N/A
Variations |  |  | 22066 | ROCKPOOL PELICAN WATERS |  | 99 | Variations | 410185.47 | 249326.12 |  | 30 | 22066 | D1SU | CT | Survey | 0 | 0 | 0 | 0 | 0 | #N/A
#N/A | [10 empty] | 30 | 22066 | D1TM | CT | Traffic Engineer | 3062.5 | 0 | 3062.5 | 7132.5 | 3062.5 | #N/A
#N/A | [10 empty] | 30 | 22066 | D1WF | CT | Web FM | 24875 | 0 | 24875 | 38175 | 24875 | #N/A
#N/A | [10 empty] | 30 | 22066 | D1WM | CT | Waste Management Consultant | 400 | 0 | 400 | 500 | 400 | #N/A
#N/A | [10 empty] | 30 | 22066 | D2 | ST | Development Management Fee | 75000 | 0 | 75000 | 75000 | 75000 | #N/A
#N/A | [10 empty] | 30 | 22066 | P01BG | PF | Bank Gaurantee Fees | 125 | 0 | 125 | 28125 | 125 | #N/A
#N/A | [10 empty] | 30 | 22066 | P01CW | PF | Contract Works Insurance | 109779.74 | 0 | 109779.74 | 222738.1 | 109779.74 | #N/A
#N/A | [10 empty] | 30 | 22066 | P02 | ST | General Consultancy | 0 | 0 | 0 | 0 | 0 | #N/A
#N/A | [10 empty] | 30 | 22066 | P03BS | PF | BSA - Insurance Contract Cover | 0 | 0 | 0 | 0 | 0 | #N/A
#N/A | [10 empty] | 30 | 22066 | P03CF | PF | Council Fees | 16541.19 | 0 | 16541.19 | 28500 | 16541.19 | #N/A
#N/A | [10 empty] | 30 | 22066 | P03FE | OT | Fire Extinguishers | 511.5 | 0 | 511.5 | 6250 | 511.5 | #N/A
#N/A | [10 empty] | 30 | 22066 | P03LF | PF | Legal Fees | 3500 | 0 | 3500 | 3500 | 3500 | #N/A
#N/A | [10 empty] | 30 | 22066 | P03LS | PF | Portable Long Service Leave | 0 | 0 | 0 | 0 | 0 | #N/A
#N/A | [10 empty] | 30 | 22066 | P03TE | OT | Temporary Electricity | 7635.68 | 0 | 7635.68 | 24584.4 | 7635.68 | #N/A
#N/A | [10 empty] | 30 | 22066 | P03WH | PF | Workplace Health & Saftey Fees | 0 | 0 | 0 | 0 | 0 | #N/A
#N/A | [10 empty] | 30 | 22066 | P04DI | ST | Dilap Report Subcontract | 1200 | 0 | 1200 | 1200 | 1200 | #N/A
#N/A | [10 empty] | 30 | 22066 | P04HS | MT | Temporary Harstanding | 0 | 0 | 0 | 0 | 0 | #N/A
#N/A | [10 empty] | 30 | 22066 | P04TF | XP | Temporary Fencing | 14212 | 0 | 14212 | 17725 | 14212 | #N/A
#N/A | [10 empty] | 30 | 22066 | P04TR | MT | Temporary Roads | 0 | 0 | 0 | 5000 | 0 | #N/A
#N/A | [10 empty] | 30 | 22066 | P04TS | MT | Temporary Signage & Banners | 10115.7 | 0 | 10115.7 | 10198.83 | 10115.7 | #N/A
#N/A | [10 empty] | 30 | 22066 | P05 | LW | Labour for Site Establishment | 2975.98 | 0 | 2975.98 | 2975.98 | 2975.98 | #N/A
#N/A | [10 empty] | 30 | 22066 | P05OS | MT | Office Sheds & Furnishings | 111504.67 | 0 | 111504.67 | 175900.13 | 111504.67 | #N/A
#N/A | [10 empty] | 30 | 22066 | P05SC | MT | Site Communications | 7282.49 | 0 | 7282.49 | 13795.13 | 7282.49 | #N/A
#N/A | [10 empty] | 30 | 22066 | P05SS | MT | Site Security | 2597.2 | 0 | 2597.2 | 2597.2 | 2597.2 | #N/A
#N/A | [10 empty] | 30 | 22066 | P05TE | MT | Temporary Electricity | 1085.12 | 0 | 1085.12 | 1085.12 | 1085.12 | #N/A
#N/A | [10 empty] | 30 | 22066 | P05TL | OT | Temporary Lighting | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | P07 | IP | McNAB Equipment Hire | 2456.85 | 0 | 2456.85 | 4424.85 | 2456.85 | #N/A
[11 empty] | 30 | 22066 | P10BC | LW | Building Cadet | 54975.6 | 0 | 54975.6 | 81047.76 | 54975.6 | #N/A
[11 empty] | 30 | 22066 | P10CA | LW | Contracts Administrator | 235476.36 | 0 | 235476.36 | 386986.44 | 235476.36 | #N/A
[11 empty] | 30 | 22066 | P10DM | LW | Design Manager | 85526.88 | 0 | 85526.88 | 90347.88 | 85526.88 | #N/A
[11 empty] | 30 | 22066 | P10EM | LW | ECI MANAGER | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | P10ES | LW | Estimator/ Cost Planner | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | P10FM | LW | Foreman | 187522.4 | 0 | 187522.4 | 561391.96 | 187522.4 | #N/A
[11 empty] | 30 | 22066 | P10FM | OT | Foreman Fuel | 370.36 | 0 | 370.36 | 370.36 | 370.36 | #N/A
[11 empty] | 30 | 22066 | P10HS | LW | HSEQ Co-Ordinator | 26452.06 | 0 | 26452.06 | 54601.24 | 26452.06 | #N/A
[11 empty] | 30 | 22066 | P10LH | LW | Leading Hand | 1670.38 | 0 | 1670.38 | 1670.38 | 1670.38 | #N/A
[11 empty] | 30 | 22066 | P10PM | LW | Project Manager | 239302.32 | 0 | 239302.32 | 409492.84 | 239302.32 | #N/A
[11 empty] | 30 | 22066 | P10SL | LW | Site Labourer | 51410.86 | 0 | 51410.86 | 126720.5 | 51410.86 | #N/A
[11 empty] | 30 | 22066 | P10SL | ST | External Labour Hire | 28326.97 | 0 | 28326.97 | 34059.66 | 28326.97 | #N/A
[11 empty] | 30 | 22066 | P10SM | LW | Site Manager | 130172.8 | 0 | 130172.8 | 300454.4 | 130172.8 | #N/A
[11 empty] | 30 | 22066 | P10WH | LW | HSE Advisor | 109752.42 | 0 | 109752.42 | 219967.14 | 109752.42 | #N/A
[11 empty] | 30 | 22066 | P11AC | OT | Staff Accommodation | 11827.85 | 0 | 11827.85 | 26685 | 11827.85 | #N/A
[11 empty] | 30 | 22066 | P12 | ST | Surveyor | 35520 | 0 | 35520 | 51800 | 35520 | #N/A
[11 empty] | 30 | 22066 | P13ES | XP | External Scaffolding Hire | 358116.33 | 0 | 358116.33 | 542763 | 358116.33 | #N/A
[11 empty] | 30 | 22066 | P14MC | XP | Mobile Crane Hire | 54953.29 | 0 | 54953.29 | 72301.98 | 54953.29 | #N/A
[11 empty] | 30 | 22066 | P14TC | ST | Cranes, Gantries & Hoists | 333029.35 | 0 | 333029.35 | 586553.46 | 333029.35 | #N/A
[11 empty] | 30 | 22066 | P15 | ST | Cleaning | 2395 | 0 | 2395 | 39395 | 2395 | #N/A
[11 empty] | 30 | 22066 | P15 | XP | Bin Hire | 73430.08 | 0 | 73430.08 | 143922.3 | 73430.08 | #N/A
[11 empty] | 30 | 22066 | P15FC | ST | Final Clean | 0 | 0 | 0 | 106900 | 0 | #N/A
[11 empty] | 30 | 22066 | P99 | ST | Preliminary Contingency | 0 | 0 | 0 | 60000 | 0 | #N/A
[11 empty] | 30 | 22066 | PO1CW | PF | Contract Works Insurance | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | PO2GO | CT | Geotechnical Consultant | 450 | 0 | 450 | 2500 | 450 | #N/A
[11 empty] | 30 | 22066 | PO3TS | OT | Temporary Sewer & Water Connec | 0 | 0 | 0 | 16200 | 0 | #N/A
[11 empty] | 30 | 22066 | PO4SE | MT | Site Expenses | 17962.19 | 0 | 17962.19 | 25516.18 | 17962.19 | #N/A
[11 empty] | 30 | 22066 | PO5CA | MT | Covered Areas & Walkways | 7899.24 | 0 | 7899.24 | 9924.78 | 7899.24 | #N/A
[11 empty] | 30 | 22066 | PO5SC | MT | Site Communications | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | PO5TE | MT | Generators | 41118.4 | 0 | 41118.4 | 37794.86 | 41118.4 | #N/A
[11 empty] | 30 | 22066 | PO5TM | MT | Traffic Management Signage | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | PO5TT | ST | Traffic Control | 2422.5 | 0 | 2422.5 | 11634.06 | 2422.5 | #N/A
[11 empty] | 30 | 22066 | PO5TW | MT | Temporary Water | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | PO6 | OT | Stationary and Office Supplies | 588.74 | 0 | 588.74 | 9241.06 | 588.74 | #N/A
[11 empty] | 30 | 22066 | PO7 | IP | McNab Equipment Hire | 22183.35 | 0 | 22183.35 | 69803.44 | 22183.35 | #N/A
[11 empty] | 30 | 22066 | PO7 | MT | Dewatering | 164.53 | 0 | 164.53 | 164.53 | 164.53 | #N/A
[11 empty] | 30 | 22066 | PO7 | XP | Small Tools | 11342 | 0 | 11342 | 17447.96 | 11342 | #N/A
[11 empty] | 30 | 22066 | PO8 | MT | Site Safety Equipment | 11249.37 | 0 | 11249.37 | 16241.56 | 11249.37 | #N/A
[11 empty] | 30 | 22066 | POOECI | CT | ECI Costs | 176154.77 | 0 | 176154.77 | 176154.77 | 176154.77 | #N/A
[11 empty] | 30 | 22066 | T06 | ST | BULK EARTHWORKS | 335272.35 | 0 | 335272.35 | 407994.85 | 335272.35 | #N/A
[11 empty] | 30 | 22066 | T06DE | ST | DETAILED EXCAVATION | 31798.13 | 0 | 31798.13 | 39139.13 | 31798.13 | #N/A
[11 empty] | 30 | 22066 | T08 | ST | PILING | 1185566.25 | 0 | 1185566.25 | 1185566.25 | 1185566.25 | #N/A
[11 empty] | 30 | 22066 | T091 | MT | CONCRETE SUPPLY | 576652.05 | 0 | 576652.05 | 680189.17 | 576652.05 | #N/A
[11 empty] | 30 | 22066 | T091 | ST | CONCRETE LABOUR | 489238.53 | 0 | 489238.53 | 616776.83 | 489238.53 | #N/A
[11 empty] | 30 | 22066 | T091PU | XP | CONCRETE PUMPING | 110869.2 | 0 | 110869.2 | 139683.7 | 110869.2 | #N/A
[11 empty] | 30 | 22066 | T091T | MT | CONCRETE TESTING & SUNDRIES | 0 | 0 | 0 | 20856 | 0 | #N/A
[11 empty] | 30 | 22066 | T091TT | ST | TERMITE TREATMENT | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | T092 | MT | REINFORCEMENT SUPPLY | 1094442.31 | 0 | 1094442.31 | 1131791.83 | 1094442.31 | #N/A
[11 empty] | 30 | 22066 | T092 | ST | REINFORCEMENT PLACING | 251206.84 | 0 | 251206.84 | 270299.71 | 251206.84 | #N/A
[11 empty] | 30 | 22066 | T093 | ST | FORMWORK | 1268247.1 | 0 | 1268247.1 | 1344003.6 | 1268247.1 | #N/A
[11 empty] | 30 | 22066 | T094 | MT | Permanent Formwork | 42713.22 | 0 | 42713.22 | 69103.01 | 42713.22 | #N/A
[11 empty] | 30 | 22066 | T094 | ST | Permanent Formwork | 41386.7 | 0 | 41386.7 | 43886.7 | 41386.7 | #N/A
[11 empty] | 30 | 22066 | T11 | ST | MASONRY - BLOCKWORK | 1173300.05 | 0 | 1173300.05 | 1477524.4 | 1173300.05 | #N/A
[11 empty] | 30 | 22066 | T12 | ST | STRUCTURAL STEEL | 9050 | 0 | 9050 | 113348 | 9050 | #N/A
[11 empty] | 30 | 22066 | T13 | ST | METALWORK | 0 | 0 | 0 | 638270.77 | 0 | #N/A
[11 empty] | 30 | 22066 | T13RC | ST | RUBBISH/LAUNDRY CHUTE SYSTEM | 0 | 0 | 0 | 20500 | 0 | #N/A
[11 empty] | 30 | 22066 | T14 | ST | ROOFING | 0 | 0 | 0 | 290282.6 | 0 | #N/A
[11 empty] | 30 | 22066 | T14RS | ST | ROOF ACCESS & SAFETY | 0 | 0 | 0 | 47480 | 0 | #N/A
[11 empty] | 30 | 22066 | T15 | ST | WATERPROOFING & TANKING | 54817.5 | 0 | 54817.5 | 288180 | 54817.5 | #N/A
[11 empty] | 30 | 22066 | T16 | LW | CARPENTRY | 40382.64 | 0 | 40382.64 | 38037.1 | 40382.64 | #N/A
[11 empty] | 30 | 22066 | T16 | ST | CARPENTRY - MISCELLANEOUS | 11311.83 | 0 | 11311.83 | 281980.89 | 11311.83 | #N/A
[11 empty] | 30 | 22066 | T16TT | ST | TRUSSES | 177447.68 | 0 | 177447.68 | 209065 | 177447.68 | #N/A
[11 empty] | 30 | 22066 | T17 | ST | ALUMINIUM WINDOWS & DOORS | 599245.3 | 0 | 599245.3 | 1366928.3 | 599245.3 | #N/A
[11 empty] | 30 | 22066 | T18 | MT | DOOR & SUNDRY HARDWARE | 0 | 0 | 0 | 103793.08 | 0 | #N/A
[11 empty] | 30 | 22066 | T18 | ST | TIMBER DOORS & FRAMES | 102821.85 | 0 | 102821.85 | 288114.77 | 102821.85 | #N/A
[11 empty] | 30 | 22066 | T19 | ST | CEILINGS & PARTITIONS | 1150000 | 0 | 1150000 | 3122346 | 1150000 | #N/A
[11 empty] | 30 | 22066 | T20 | ST | JOINERY & BENCHTOPS | 131332.11 | 0 | 131332.11 | 1291997.15 | 131332.11 | #N/A
[11 empty] | 30 | 22066 | T21 | ST | STAINLESS STEEL | 49000 | 0 | 49000 | 245000 | 49000 | #N/A
[11 empty] | 30 | 22066 | T22 | ST | FLOOR COVERINGS | 26552.56 | 43408.5 | 26552.56 | 880260.8 | 69961.06 | #N/A
[11 empty] | 30 | 22066 | T23 | MT | TILING SUPPLY | 44733.92 | 0 | 44733.92 | 134287.16 | 44733.92 | #N/A
[11 empty] | 30 | 22066 | T23 | ST | TILING INSTALL | 18795.26 | 0 | 18795.26 | 643301.07 | 18795.26 | #N/A
[11 empty] | 30 | 22066 | T23C | ST | CLADDING | 12566.13 | 0 | 12566.13 | 12566.13 | 12566.13 | #N/A
[11 empty] | 30 | 22066 | T24 | ST | PAINTING | 29082 | 0 | 29082 | 608000 | 29082 | #N/A
[11 empty] | 30 | 22066 | T24R | ST | RENDER | 129421.2 | 0 | 129421.2 | 322500 | 129421.2 | #N/A
[11 empty] | 30 | 22066 | T25 | ST | HYDRAULIC SERVICES | 1501606.28 | 0 | 1501606.28 | 2372345.44 | 1501606.28 | #N/A
[11 empty] | 30 | 22066 | T25HF | MT | SANITARY HARDWARE/HYDRAULIC FF | 49793.02 | 0 | 49793.02 | 705030 | 49793.02 | #N/A
[11 empty] | 30 | 22066 | T26 | ST | ELECTRICAL SERVICES | 402791 | 0 | 402791 | 2319525.5 | 402791 | #N/A
[11 empty] | 30 | 22066 | T27 | ST | MECHANICAL SERVICES | 746526.1 | 253699.2 | 746526.1 | 1564700 | 1000225.3 | #N/A
[11 empty] | 30 | 22066 | T28 | ST | LIFT SERVICES | 296382 | 0 | 296382 | 344157 | 296382 | #N/A
[11 empty] | 30 | 22066 | T29 | ST | FIRE SERVICES | 273242.28 | 51632.5 | 273242.28 | 590000 | 324874.78 | #N/A
[11 empty] | 30 | 22066 | T30 | ST | LANDSCAPING | 0 | 0 | 0 | 359307 | 0 | #N/A
[11 empty] | 30 | 22066 | T32 | ST | SIGNAGE | 0 | 0 | 0 | 38210 | 0 | #N/A
[11 empty] | 30 | 22066 | T98 | ST | Trade Contingency | 0 | 0 | 0 | 122137 | 0 | #N/A
[11 empty] | 30 | 22066 | T9901 | ST | Corporate Signage | 0 | 0 | 0 | 27455 | 0 | #N/A
[11 empty] | 30 | 22066 | T9902 | ST | Wayfinding Signage | 0 | 0 | 0 | 30000 | 0 | #N/A
[11 empty] | 30 | 22066 | T9903 | ST | Corner and Door Protection | 0 | 0 | 0 | 30000 | 0 | #N/A
[11 empty] | 30 | 22066 | T9904 | ST | Reception, Hairsalon and Priva | 0 | 0 | 0 | 22000 | 0 | #N/A
[11 empty] | 30 | 22066 | T9905 | ST | Nurse Call, Electronic Access | 97880.18 | 0 | 97880.18 | 683472.23 | 97880.18 | #N/A
[11 empty] | 30 | 22066 | T9906 | ST | Interior Designer Lounge Scree | 0 | 0 | 0 | 0 | 0 | #N/A
[11 empty] | 30 | 22066 | T9907 | ST | Metalwork AL1 Design Rationali | 0 | 0 | 0 | 100000 | 0 | #N/A
[11 empty] | 30 | 22066 | TO92 | MT | REINFORCEMENT SUPPLY DONT USE | 2000 | 0 | 2000 | 2000 | 2000 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A
[20 empty] | 0 | #N/A

## Breakup
Job Cost Code | Job Cost Type Code | Job Code Description | Cashflow Claim
|  |  |  | DESIGN FEES | DESIGN FEES
|  |  |  | Development Management Fee | Development Management Fee
|  |  |  | Preliminaries | Preliminaries
|  |  |  | Bulk Earthworks | Bulk Earthworks
|  |  |  | Piling | Piling
|  |  |  | Termite Treatment | Termite Treatment
|  |  |  | Detailed Excavation | Detailed Excavation
|  |  |  | Concrete Supply | Concrete Supply
|  |  |  | Concrete Labour | Concrete Labour
|  |  |  | Concrete Pumping | Concrete Pumping
|  |  |  | Concrete Testing and Sundries | Concrete Testing and Sundries
|  |  |  | Reinforcement Supply | Reinforcement Supply
|  |  |  | Reinforcement Placing | Reinforcement Placing
|  |  |  | Formwork | Formwork
|  |  |  | Masonry - Blockwork | Masonry - Blockwork
|  |  |  | Waterproofing & Tanking | Waterproofing & Tanking
|  |  |  | Structural Steel | Structural Steel
|  |  |  | Roofing | Roofing
|  |  |  | Roof Access & Safety | Roof Access & Safety
|  |  |  | Aluminium Windows and Doors | Aluminium Windows and Doors
|  |  |  | Metalwork | Metalwork
|  |  |  | Rubbish/ Laundry Chute System | Rubbish/ Laundry Chute System
|  |  |  | Roller Doors | Roller Doors
|  |  |  | Carpentry | Carpentry
|  |  |  | Trusses | Trusses
|  |  |  | Timber Doors and Frames | Timber Doors and Frames
|  |  |  | Door and Sundry Hardware | Door and Sundry Hardware
|  |  |  | Ceilings and Partitions | Ceilings and Partitions
|  |  |  | Toilet Partitions | Toilet Partitions
|  |  |  | Tiling Supply | Tiling Supply
|  |  |  | Tiling Install | Tiling Install
|  |  |  | Cladding | Cladding
|  |  |  | Floor Coverings | Floor Coverings
|  |  |  | Stainless Steel | Stainless Steel
|  |  |  | Hydraulic Services | Hydraulic Services
|  |  |  | Electrical Services | Electrical Services
|  |  |  | Mechanical Services | Mechanical Services
|  |  |  | Fire Services | Fire Services
|  |  |  | Lift Services | Lift Services
|  |  |  | Landscaping | Landscaping
|  |  |  | Painting | Painting
|  |  |  | Render | Render
|  |  |  | Signage | Signage
|  |  |  | Trade Contingency | Trade Contingency
|  |  |  | Joinery & Benchtops | Joinery & Benchtops
|  |  |  | Sanitary Hardware/ Hydraulic | Sanitary Hardware/ Hydraulic
|  |  |  | Corporate Signage | Corporate Signage
|  |  |  | Wayfinding Signage | Wayfinding Signage
|  |  |  | Corner and Door Protection | Corner and Door Protection
|  |  |  | Reception, Hairsalon and | Reception, Hairsalon and
|  |  |  | Nurse Call, Electronic Access | Nurse Call, Electronic Access
|  |  |  | Interior Designer Lounge | Interior Designer Lounge
|  |  |  | Metalwork AL1 Design | Metalwork AL1 Design
|  |  |  | Margin Allowance | Margin Allowance
|  |  |  | Sundry Income | Sundry Income
|  |  |  | Variations | Variations

## Margin Calculation
2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 0 | 0 | 0 | 0
2318402.86 | 3527794.4 | 5282712.67 | 6720142.42 | 7780524.04 | 9748456.1 | 12370766.17 | 15156999.46 | 18206480.27 | 21206921.5243 | 24130909.7046 | 26790890.1026 | 29123408.6125 | 30529139.35 | 31159000 | 31159000 | 0 | 0
31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47 | 31569185.47
7.344% | 11.17% | 16.73% | 21.29% | 24.65% | 30.88% | 39.19% | 48.01% | 57.67% | 67.18% | 76.44% | 84.86% | 92.25% | 96.71% | 98.7% | 98.7% | 0% | 0%