## Sheet1
[5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18
Project | Lot 8 Rees Court Palm Beach
Site Manager | John Doe
Area | Activity | Days | Start Date | Finish Date | time axis 2021-06-01 to 2021-10-04
 | time axis 2021-06-01 to 2021-10-04
Temporary Services |  | 1 | 2021-06-01 | 2021-06-01 | bar: 2021-06-01
| Fencing | 1 | 2021-06-01 | 2021-06-01 | bar: 2021-06-01
| Electrical | 1 | 2021-06-01 | 2021-06-01 | bar: 2021-06-01
| Plumbing | 1 | 2021-06-01 | 2021-06-01 | bar: 2021-06-01
Excavation |  | 9 | 2021-06-02 | 2021-06-12 | bar: 2021-06-02 to 2021-06-05; 2021-06-08 to 2021-06-12
| Clear Site | 1 | 2021-06-02 | 2021-06-02 | bar: 2021-06-02
| Cut & Fill/Foundation Prep | 8 | 2021-06-03 | 2021-06-12 | bar: 2021-06-03 to 2021-06-05; 2021-06-08 to 2021-06-12
Concrete |  | 5 | 2021-06-15 | 2021-06-19 | bar: 2021-06-15 to 2021-06-19
| Pour Foundations | 2 | 2021-06-15 | 2021-06-16 | bar: 2021-06-15 to 2021-06-16
| Slab Prep | 1 | 2021-06-17 | 2021-06-18 | bar: 2021-06-17 to 2021-06-18
| Slab Pour | 2 | 2021-06-19 | 2021-06-19 | bar: 2021-06-19
Framing |  | 12 | 2021-06-22 | 2021-07-07 | bar: 2021-06-22 to 2021-06-26; 2021-06-29 to 2021-07-03; 2021-07-06 to 2021-07-07
| Wall frames | 8 | 2021-06-22 | 2021-07-01 | bar: 2021-06-22 to 2021-06-26; 2021-06-29 to 2021-07-01
| Roof Trusses | 4 | 2021-06-30 | 2021-07-03 | bar: 2021-06-30 to 2021-07-03
| Roof Sheeting | 3 | 2021-07-03 | 2021-07-07 | bar: 2021-07-03; 2021-07-06 to 2021-07-07
Plumbing |  | 75 | 2021-06-04 | 2021-09-15 | bar: 2021-06-04 to 2021-06-05; 2021-06-08 to 2021-06-12; 2021-06-15 to 2021-06-19; 2021-06-22 to 2021-06-26; 2021-06-29 to 2021-07-03; 2021-07-06 to 2021-07-10; 2021-07-13 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-31; 2021-08-03 to 2021-08-07; 2021-08-10 to 2021-08-14; 2021-08-17 to 2021-08-21; 2021-08-24 to 2021-08-28; 2021-08-31 to 2021-09-04; 2021-09-07 to 2021-09-11; 2021-09-14 to 2021-09-16
| Ground Work | 3 | 2021-06-04 | 2021-06-08 | bar: 2021-06-04 to 2021-06-05; 2021-06-08
| Rough In - Slab | 1 | 2021-06-18 | 2021-06-18 | bar: 2021-06-18
| Rough In - Shell | 3 | 2021-07-07 | 2021-07-09 | bar: 2021-07-07 to 2021-07-09
| Set toilets, sinks etc | 2 | 2021-08-17 | 2021-08-18 | bar: 2021-08-17 to 2021-08-18
| Appliance connections | 1 | 2021-09-15 | 2021-09-15 | bar: 2021-09-16
Windows |  | 3 | 2021-07-06 | 2021-07-08 | bar: 2021-07-06 to 2021-07-08
| Wrap Sills | 1 | 2021-07-06 | 2021-07-06 | bar: 2021-07-06
| Install Windows | 2 | 2021-07-07 | 2021-07-08 | bar: 2021-07-07 to 2021-07-08
Electrical |  | 45 | 2021-07-09 | 2021-09-16 | bar: 2021-07-09 to 2021-07-10; 2021-07-13 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-31; 2021-08-03 to 2021-08-07; 2021-08-10 to 2021-08-14; 2021-08-17 to 2021-08-21; 2021-08-24 to 2021-08-28; 2021-08-31 to 2021-09-04; 2021-09-07 to 2021-09-11; 2021-09-14 to 2021-09-16
| Rough In | 4 | 2021-07-09 | 2021-07-14 | bar: 2021-07-09 to 2021-07-10; 2021-07-13 to 2021-07-14
| Fitt off | 6 | 2021-09-09 | 2021-09-16 | bar: 2021-09-09 to 2021-09-11; 2021-09-14 to 2021-09-16
Insulation |  | 14 | 2021-07-14 | 2021-07-31 | bar: 2021-07-14 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-31
| Internal Walls | 1 | 2021-07-14 | 2021-07-14 | bar: 2021-07-14
| Roof Space | 1 | 2021-07-31 | 2021-07-31 | bar: 2021-07-31
Scaffolding |  | 17 | 2021-07-09 | 2021-07-31 | bar: 2021-07-09 to 2021-07-10; 2021-07-13 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-31
| Erection | 1 | 2021-07-09 | 2021-07-09 | bar: 2021-07-09
| Dismantle | 1 | 2021-07-31 | 2021-07-31 | bar: 2021-07-31
External Walls |  | 18 | 2021-07-07 | 2021-07-30 | bar: 2021-07-07 to 2021-07-10; 2021-07-13 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-30
| Sarking | 1 | 2021-07-07 | 2021-07-07 | bar: 2021-07-07
| External Brick Walls | 15 | 2021-07-10 | 2021-07-30 | bar: 2021-07-10; 2021-07-13 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-30
Internal Walls |  | 13 | 2021-07-15 | 2021-07-31 | bar: 2021-07-15 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-31
| Gyprock Delivery | 1 | 2021-07-15 | 2021-07-15 | bar: 2021-07-15
| Hang & Set | 12 | 2021-07-16 | 2021-07-31 | bar: 2021-07-16 to 2021-07-17; 2021-07-20 to 2021-07-24; 2021-07-27 to 2021-07-31
Bathrooms/Laundry |  | 7 | 2021-08-03 | 2021-08-11 | bar: 2021-08-03 to 2021-08-07; 2021-08-10 to 2021-08-11
| Waterproofing | 3 | 2021-08-03 | 2021-08-05 | bar: 2021-08-03 to 2021-08-05
| Tile Prep | 2 | 2021-08-06 | 2021-08-07 | bar: 2021-08-06 to 2021-08-07
| Tile Install | 3 | 2021-08-07 | 2021-08-11 | bar: 2021-08-07; 2021-08-10 to 2021-08-11
Flooring |  | 7 | 2021-08-12 | 2021-08-20 | bar: 2021-08-12 to 2021-08-14; 2021-08-17 to 2021-08-20
| Tile Delivery | 1 | 2021-08-12 | 2021-08-12 | bar: 2021-08-12; 2021-09-16
| Tile Prep | 2 | 2021-08-13 | 2021-08-14 | bar: 2021-08-13 to 2021-08-14
| Tile Install | 5 | 2021-08-14 | 2021-08-20 | bar: 2021-08-14; 2021-08-17 to 2021-08-20
| Carpet Delivery | 1 | 2021-08-17 | 2021-08-17 | bar: 2021-08-17
| Carpet Install | 3 | 2021-08-18 | 2021-08-20 | bar: 2021-08-18 to 2021-08-20
Cabinets |  | 10 | 2021-08-03 | 2021-08-14 | bar: 2021-08-03 to 2021-08-07; 2021-08-10 to 2021-08-14
| Bathrooms | 3 | 2021-08-12 | 2021-08-14 | bar: 2021-08-12 to 2021-08-14
| Built Ins | 4 | 2021-08-03 | 2021-08-06 | bar: 2021-08-03 to 2021-08-06
| Kitchen/Pantry | 4 | 2021-08-06 | 2021-08-11 | bar: 2021-08-06 to 2021-08-07; 2021-08-10 to 2021-08-11
| Laundry | 2 | 2021-08-07 | 2021-08-10 | bar: 2021-08-07; 2021-08-10
Interior Doors |  | 13 | 2021-08-21 | 2021-09-08 | bar: 2021-08-21; 2021-08-24 to 2021-08-28; 2021-08-31 to 2021-09-04; 2021-09-07 to 2021-09-08
| Delivery | 1 | 2021-08-21 | 2021-08-21 | bar: 2021-08-21
| Hang | 2 | 2021-08-24 | 2021-08-25 | bar: 2021-08-24 to 2021-08-25
| Install Hardware | 1 | 2021-09-08 | 2021-09-08 | bar: 2021-09-08
Interior |  | 18 | 2021-08-19 | 2021-09-11 | bar: 2021-08-19 to 2021-08-21; 2021-08-24 to 2021-08-28; 2021-08-31 to 2021-09-04; 2021-09-07 to 2021-09-11
| Trims, Molding, Finishes | 6 | 2021-08-19 | 2021-08-26 | bar: 2021-08-19 to 2021-08-21; 2021-08-24 to 2021-08-26
| Paint Prep | 5 | 2021-08-24 | 2021-08-28 | bar: 2021-08-24 to 2021-08-28
| Paint & Cure | 10 | 2021-08-31 | 2021-08-11 | bar: 2021-08-30 to 2021-09-04; 2021-09-06 to 2021-09-11
Bathroom Glass |  | 4 | 2021-09-11 | 2021-09-16 | bar: 2021-09-11; 2021-09-14 to 2021-09-16
| Delivery | 1 | 2021-09-11 | 2021-09-11 | bar: 2021-09-11
| Hang | 3 | 2021-09-14 | 2021-09-16 | bar: 2021-09-14 to 2021-09-16
Appliances |  | 4 | 2021-09-11 | 2021-09-16 | bar: 2021-09-11; 2021-09-14 to 2021-09-16
| Delivery | 1 | 2021-09-11 | 2021-09-11 | bar: 2021-09-11
| Install | 3 | 2021-09-14 | 2021-09-16 | bar: 2021-09-14 to 2021-09-16
Closeout |  | 7 | 2021-09-17 | 2021-09-25 | bar: 2021-09-17 to 2021-09-18; 2021-09-21 to 2021-09-25
| Clean Up/Finishing Touches | 4 | 2021-09-17 | 2021-09-22 | bar: 2021-09-17 to 2021-09-18; 2021-09-21 to 2021-09-22
| Final Walk Through | 1 | 2021-09-23 | 2021-09-23 | bar: 2021-09-23
| Punch List | 1 | 2021-09-24 | 2021-09-24 | bar: 2021-09-24
| Handover | 1 | 2021-09-25 | 2021-09-25 | bar: 2021-09-25
Cost Schedule
| Project Manager | 1 | various | various | bar: 2021-06-19; 2021-06-26; 2021-07-03; 2021-07-10; 2021-07-17; 2021-07-24; 2021-07-31; 2021-08-07; 2021-08-14; 2021-08-21; 2021-08-28; 2021-09-04; 2021-09-11; 2021-09-18; 2021-09-25
| Foreman | 1 | 2021-06-11 | 2021-09-25 | bar: 2021-06-11 to 2021-09-25
| Labor | 1 | 2021-06-01 | 2021-09-11
|  | 2 | 2021-06-22 | 2021-08-28 | bar: 2021-06-22 to 2021-08-28
|  | 3 | 2021-06-22 | 2021-08-28 | bar: 2021-06-22 to 2021-08-28
| Amenities | 1 | 2021-06-01 | 2021-09-23 | bar: 2021-06-01 to 2021-09-18; 2021-09-21 to 2021-09-23