## Sheet1
QUOTATION
CONTRACT | CN-13723 Townsville Northern Access Intersection Upgrade
Assumptions
DESCRIPTION |  |  | DATE | 2021-01-01 |  |  |  | - Piling pad is 400mm of rock and 200mm of 2.5 capping
|  |  | JOB No | 4242 |  |  |  | - Pad area 30x10m and 15x10m track to build on.
- Pile from ground level
In accordance with the contract, we submit for your approval, our quotation to carry out the | [7 empty] | - Assumed we dispose of excavation
works at the above site as per Schedule of Rates set out below. | [7 empty] | - Pricing bassed on MRTS63A Nov 2020
Our estimate sheet is attached.
ITEM | DESCRIPTION | QUOTATION PRICE
|  | Unit | Approx Qty | Rate | Amount
2021-01-01
Description of Works:
Piling Works & Certifacation
| Establishment | Each | 1 |  | 0
| Dis Establishment | Each | 1 |  | 0
70501 | Supply of Steel Liners - 940 ID | m | 19.2 |  | 0
| Syppy and Fixing of stiffening bands 940 ID | Each | 2 |  | 0
70502 | Handling and Pitching of steel liners | Each | 2 |  | 0
70503 | Driving steel liners | m | 15.6 |  | 0
70504P | Extension of steel liners | hr
| Onsite Welding (splice Cages) | hr
70508 | Excavation of liners | m3 | 12 |  | 0
70509 | Excavation below toe of liner | m3 | 1.3 |  | 0
70511 | Steel Reinforcing bar in lined and bored pile | tonne | 1.1 |  | 0
70515 | Certifacation of pile capacity | hr | 40 |  | 0 | 2 days for geotec on site, report prep & desk top review 4 days total
70516 | Pile Integrity Testing | each | 2 |  | 0
| Cocrete Class [40] Mpa/20 in lined pile | m3 | 18.62 |  | 0 | allowance for over pour & wastage
| Downhole Camera | week | 1 |  | 0
| Downhole Camera Freight | Each | 1 |  | 0
| Crane pad desgin and certification | LS | 1 |  | 0 | pilling pad design
| Tester Travel | Each | 7 |  | 0 | 1 for DCP, Pile and pile cap, 4 for backfilling
| Slump/Cure/Compress | Each | 7 |  | 0 | 2 per pile and 3 for pile cap
| DCP | M | 6 |  | 0 | DCPs for crane pad
| Survey | hr | 4 |  | 0 | Set out & As-Built Pile
Pad Construction
PLANT & EQUIPMENT
| Excavator 30 tonne | Hour | 15 |  | 0
| Truck 10m3 approx. Capacity | Hour | 15 |  | 0
| Pad Foot Roller 12-20 tonne | Hour | 15 |  | 0
| Water Truck | Hour | 7 |  | 0
| Nuke | Each | 2 |  | 0
| Lab Compaction | Each | 2 |  | 0
| Geofabric | m2 | 300 |  | 0
| Delivery of geofabric | LS | 1 |  | 0
| 200 minus rock | tonne | 140 |  | 0
| Type 2.5 | tonne | 90 |  | 0
Pile Cap Construction
MATERIAL
| Hold Down Bolt assembly | Each | 1 |  | 0
| Reinforcing Bar | tonne | 2.672 |  | 0
| Reinforcing Bar delivery | each | 1 |  | 0
| Misc Accessorys I.e. Tie wire, aspros, etc | lump | 1000 |  | 0
| Concrete [40MPa] 20/100 | m3 | 19.5 |  | 0
| Concrete Wasteage [40MPa] 20/100 | m3 | 1.95 |  | 0
| Additional Ice 3 bags per m3 | each | 66 |  | 0
| HB70 Grout | bags | 10 |  | 0 | Grout pad
| N20/20 Blinder | m3 | 5 |  | 0 | including wastage
| Curing oil | Each | 1 |  | 0
| Anti-vap | Each | 1 |  | 0
| Conduits (Allowance) | LS | 1 |  | 0
| Concrete Blanket | each | 1 |  | 0
| Form Ply | each | 18 |  | 0
| White Ply | each | 12 |  | 0
| LVL | each | 20 |  | 0
| RMD Hire | lump | 1 |  | 0
PLANT & EQUIPMENT
| 32m Concrete Pump | hr | 4 |  | 0 | Blinder | hour added for wash out
| 32m Concrete Pump Mobilisation | Each | 2 |  | 0 | Blinder
| 32m Concrete Pump - Pumped Concrete | m3 | 5 |  | 0 | Blinder
| 32m Concrete Pump | hr | 5 |  | 0 | Pile Cap | hour added for wash out
| 32m Concrete Pump Mobilisation | Each | 2 |  | 0 | Pile Cap
| 32m Concrete Pump - Pumped Concrete | m3 | 21.45 |  | 0 | Pile Cap
| Excavator 30 tonne | Hour | 10 |  | 0 | Excavate down to pile cap - detailed excavation
| Truck 10m3 approx. Capacity | Hour | 10 |  | 0 | Excavate down to pile cap - detailed excavation
| Franna + Dogman | Hour | 15 |  | 0 | Shift Reo, lift onto blinder install Rag bolt assembly, lift in forms and pull out forms
| Compressor | Day | 2 |  | 0
| Knuckle Scabbler | Day | 2 |  | 0
| Disposal of excavated material | m3 | 40 |  | 0
LABOUR
| Survey | hr | 3 |  | 0 | set out blinder for forms
| Tradesman x 5 | hr | 15 |  | 0 | Pour Blinder
| Tradesman x 2 | hr | 35 |  | 0 | scabble pile after pile break back and remove concrete stuck to reo & Repair any damage from break back
| Tradesman x 4 | hr | 140 |  | 0 | tie cage 4 men 3 days additional hours for not being able to use S bar and adjustments required for pile startes and assembly
| Tradesman x 5 | hr | 200 |  | 0 | Build and stand forms, Hang Rag Bolt assembly 5 men by 4 days
| Survey | hr | 4 |  | 0 | Pre pour inspection
| Tradesman x 5 | hr | 20 |  | 0 | Pour Pile Cap
| Tradesman x 2 | hr | 8 |  | 0 | Finish pile cap
| Survey | hr | 3 |  | 0 | As-Built
| Tradesman x 2 | hr | 8 |  | 0 | Grout up base plate
| Labour | hr | 2 |  | 0 | instalation and monitor of temp probe
| Tradesman x 3 | hr | 30 |  | 0 | strip and cure & dissassembly
SUBCONTRACT
| Cut steel liners | each | 2 |  | 0 | initial price per pile
| Cut steel liners | m | 3 |  | 0 | Liners will be approx 1.5 above cut off height
| Pile Break Back | each | 2 |  | 0 | initial price per pile
| Pile Break Back | m | 2 |  | 0 | Over pour of 2m allowed for - extra over for anything greater than 1m
| Travel & Accomadation | lump | 1 |  | 0
| Testing - UCS & Slump | each | 4 |  | 0
Backfill of Pile Cap
MATERIAL
| Type 2.3 - Pugged & Delivered | tonne | 60 |  | 0 | 2.5 does not come pugged
PLANT
| Excavator 30 tonne | Hour | 30 |  | 0 | 100mm layers as per confined excavation
| Water Truck | Hour | 15 |  | 0
| Ramer | day | 3 |  | 0
| Trench Roller | day | 3 |  | 0
LABOUR
| Labourer x 2 | Hour | 60 |  | 0
Enviro Controls, Clean Up And Removal of Piling Pad
| Install Enviro Controls |  |  |  |  | over spill from piling
| Backhoe | hour | 10 |  | 0
| Labour | hour | 10 |  | 0
| 200 minus | T | 30 |  | 0
| 20mm agg | T | 20 |  | 0
| Geofabric | m2 | 120 |  | 0
| Excavator 30 tonne | Hour | 10 |  | 0
| Truck 10m3 approx. Capacity x 2 | Hour | 20 |  | 0
| Backhoe | hour | 10 |  | 0 | Concrete Spoil cleanup
| Labour | hour | 10 |  | 0
Day Works
| Drill Rig | hour
| Foreman’s Gang box, welder, oxy, misc small tools | hour
| Crawler crane | hour
| Impact Hammer | hour
| Vibratory Hammer | hour
| Franna | hour
| Concrete Pump | hour
| Ground Engaging Tools | hour
| Excavator/Bobcat | hour
| EWP | hour
| Air Compressor | hour
| Site Vehicle | hour
| Demurrage – Float | hour
| Demurrage – Semi-trailer | hour
| Supervisor | hour
| Project Manager | hour
| Project Engineer | hour
| Machine Operator | hour
| Welder | hour
| Labourer | hour
| Project Administrator | hour
| LAHA per man | Day
| Variation Sub Total |  |  |  | 0
| On-site Overheads | 20% |  |  | 0
| Off-site Overheads | 6% |  |  | 0
| Profit Margin | 6% |  |  | 0
| Variation Total |  |  |  | 0