Assessment Workbook 5

BSB51415 Diploma

of Project Management

Integration Management

Version 1.01 Produced 18 October 2018

Copyright © 2021 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 5 May 2016 | Version 1.0 produced following assessment validation. | 1.0 |
| 18 October 2018 | Version 1.01 Change to Practical Assessment | 1.01 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Coversheet	4

Case Study	5

Instructions to Student	5

Introduction	6

Workbook Checklist	17

# Assessment Workbook Coversheet

| WORKBOOK: | Workbook 5 |  |  |
| --- | --- | --- | --- |
| TITLE: | Integration Management |  |  |
| FIRST AND SURNAME: | Trae Grimley |  |  |
| PHONE: | 0406705844 |  |  |
| EMAIL: | traegrimley1997@gmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Trae Grimley |  | Signature: TG | Date: 20/7/2021 |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant advisor to the project team at Awesome Landscapes Pty Ltd. Specifically you are required to provide independent advice on seeing their current project through the entire life cycle. You have already provided advice to them in the previous four workbooks. The project manager has advised the project is now complete, and is about to archive all the project documentation. Your task is to evaluate the supplied project documentation and to ensure all due diligence has been completed. You will need to compare the project plan with the previous version to ensure it is ready for closure. Project Charter version 4 (.pdf) Project Plan version 4 (.pdf) Project Gantt Chart version 4 (.mpp) Project Gantt Chart version 4 (.pdf) Project Network Diagram version 4 (.pdf) (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

- Sam has asked to you check the Project Plan for anything that is missing. He has been very busy but appears to have done all the necessary finalisation of the plan ready for sign off. He has mentioned the final report or lessons learnt documentation has not been included, and the project archiving checklist have not been completed either. You will be assigned to complete these later. Examine the Project Charter (version 4) and Project Plan (version 4) and identify four (4) things that are missing. Guidance: - Assume the Project Gantt Chart and the financial figures in the summary/detailed costing tables are up to date as these have already been audited. Also remember this final project plan is in draft, and will not be signed off until the final acceptance meeting in a few days’ time. - Take note of the following: - Version control. - The updates from the project in the other workbooks you have completed in previous workbooks. - Check the project archiving checklist for everything that should be included

- Appendix 8, Project cash flow - Appendix 13, Responsibility assignment matrix - Appendix 19, Issues Register - Appendix 39, Project status reports

- Sam is in the process of developing a set of Lessons Learnt Documentation for the project. - Access and review the four (4) previous workbooks you have completed and derive three (3) different lessons learnt throughout the project. - Document each lessons learnt using the Lessons Learnt Documentation Template provided. Use one template for each lessons learnt.

| Lessons Learnt Documentation Template 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalet Projects |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Trae Grimley |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 20/7/2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 01 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Additional works added to scope |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | identifying areas of additional scope ASAP in the planning phase |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| organising |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| change to management procedures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Addition contruction of retaining walls required at the beginning of the project. Awesome raised a variation to the PC so works could continue/proceed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | Change to budget, adjusted timeframe to project and reactive measures that followed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | timeframe adjustment. change to budget and reactive measures. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | Additional scope works added to the project plan, correct request procedures. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| variation of scope |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| To truly understand the whole project plan,knowing the inclusions and exclusions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A high proactive input would be required, get to know the smallest of details. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identification procedures. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peak Chalet Project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Trae Grimley |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 20/7/2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 02 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | low level of reporting on the project and poor reporting processes |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | improving project recording and reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| QA, Quility control, Record keeping |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project plan, Audits, Gantt chart(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Unsatisfactory project recording and reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | a low level of understanding, causing confusion in areas including budget, schedules, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | all works running to schedule and completed on time. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | correct recording of data in the project plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Correct procedures to the recording process need to be followed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| QA audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| high proactive behaviour to recording process at all times |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Should be used throughout the duration of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Lessons Learnt Documentation Template 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  | Cascade Peaks Chalet Project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by |  |  |  |  |  |  |  | Trae Grimley |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  |  |  |  |  |  |  | 20/07/2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  |  |  |  |  |  |  | Sam Ng |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lessons Learnt Number |  |  |  |  |  |  |  | 03 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lesson Learned Proposed Name: |  |  |  |  |  |  |  | Staff Relationshps and Understanding |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Team Role: |  |  |  |  |  |  |  | To improve staff relationships and morlae and roles and responsiblilties moving forward |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Group* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Initiating |  |  |  | Planning |  |  |  | Executing |  |  |  |  |  | Controlling |  |  |  |  | Closing |
| Specific project management process being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| HR Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specific practice, tool or technique being used: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Relating to all staff, Face to face meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What action was undertaken? |  |  |  |  |  |  | Staff leaving when contractors changed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What was the result? |  |  |  |  |  |  | New staff members (landscapers) employed at short notice to finish project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have been a more preferred result? |  |  |  |  |  |  | Original employees to work through to the completion of the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What might have created the more preferred result? |  |  |  |  |  |  | The staff that left could have maybe been afford chance to take annual leave, or work on other projects whilst issuses are resolved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What is the specific lesson learnt? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How the relationship between management and all employees is important |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How could one identify a similar situation in the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Early identification process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| What behaviour is recommended for the future? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Early and proactive behaviour |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Where and how can this knowledge be used later in this current project? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Learn and take on board known mistakes and not to make them again through the project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Who should be informed about this Lesson Learnt: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Executive(s) |  |  |  |  |  | Project Manager(s) |  |  |  |  |  |  | Project team (s) |  |  |  |  | All staff |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How should this Lesson Learnt be disseminated? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | E-mail |  |  |  |  |  | Intranet/Web site |  |  |  |  |  | Tip Sheet/FAQ |  |  |  |  |  | Library |  |  |
|  | Others |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Sam has asked you to write the final report for the project. Complete the final report using the template below, assuming the things missing from the project plan in the question above have been included. Guidance: - Access and carefully review the project documentation you were provided with along with the case study scenario and populate all the fields with the required information. - Provide a date that is later than the last date in the Project Gantt Chart version 4. - Assume that this report will be submitted to Terrence Mackay, Stephen Lyons, Kate Chan, and Kim Nguyen. - Provide a brief summary of the project in terms of the four project constraints (Scope, Cost, Time, and Quality). - Provide a detailed summary of the project covering the functions of project management listed below. Further guidance is provided for you within the template.

| Project Name: | Cascade Peaks Chalet Project |  |  |
| --- | --- | --- | --- |
| Prepared by: | Trae Grimley |  |  |
| Date: | 20/07/2021 |  |  |
| Project Summary |  |  |  |
| Scope (What was included and excluded) |  |  |  |
| Inclusions: Clearing of all vegetation Installation of temporary access roads for the chalets Maintaining the area in the contruction phase and excavation works for the service utilities. Replanting of the plants that were removed at an earlier stage Contruction of streams around chalets Construction of carparks around resort. |  |  |  |
| Exclusions Any installation of service utilities Construction of chalets Advertising and marketing of chalets and resort |  |  |  |
| Cost (Budget vs. actual) |  |  |  |
| was budgeted at $414892 but came to $514892 |  |  |  |
| Time (Estimate vs. Actual) |  |  |  |
| estimated: 11th of March 2016, actual: 12th April 2017 |  |  |  |
| Project Report Submitted to: |  |  |  |
| Name: Terence McKay |  | Title: General Manager of The Cascade Peaks Hotel | Date: |
| Name: Stephen Lyons |  | Title: Planning Manager- Cascade Peak Shire Council | Date: |
| Name: Kate Chan |  | Title: Project Manager- Timber Home COnstruction | Date: |
| Name: Kim Nguyen |  | Title: Director- Awesome Landscapes | Date: |
| Analysis of Project Guidance: - Process Review - Describe all of the processes used during the planning, implementation and closure stages. - Lessons Learnt - Describe what went right and or what went wrong and how effective were the management and the processes you used. If necessary, state how you overcame any problems. - Recommendations – Make recommendations as a result of the lessons learned. |  |  |  |
| Scope |  |  |  |
| Process Review Increase to scope before project began for the additional retaining walls. Addition to scope for repair(s) caused by erosion damage when project was put on hold. Additional plants required for completion of project after project put on hold |  |  |  |
| Lessons Learnt Employees would have been needed to maintain project site when project was on hold |  |  |  |
| Recommendations Have contingency plans in place should any issuses occur |  |  |  |
| Time |  |  |  |
| Process Review Subcontractors and suppliers given more time to set up at beginning of project. Due to change to ownership, the project incurred delays |  |  |  |
| Lessons Learnt More time required to inform project subcontrators, suppliers and delivery companies |  |  |  |
| Recommendations Possible a minimum two week notice for site deliveries and access |  |  |  |
| Cost |  |  |  |
| Process Review Due to change requests the original project cost of $441,892 increased to $541,892. Part of the extra $100,000 was due to project being on hold and change of ownership. |  |  |  |
| Lessons Learnt A cashflow shortfall at the commencement of the project was caused by payment structure of Massive Eco Developments |  |  |  |
| Recommendations Adopt a different payment schedule to ease cashflow issuses on furture projects |  |  |  |
| Quality |  |  |  |
| Process Review QA inspections and audits completed and kept up to date at all times |  |  |  |
| Lessons Learnt QA inspections and audits were not completed in the project plan, thus missing information and lessons learnt are not documented, and can not be used in furture projects |  |  |  |
| Recommendations Ensure that QA inspections and audits are completed and documented to help assist for future projects |  |  |  |
| Human Resources |  |  |  |
| Process Review Two valued landscapers resigned when ownership change occurred, two new landscapers hired on short notice as replacements after an interview process |  |  |  |
| Lessons Learnt The change to the landscapers led to new workers having to learn the companies policies and workings. |  |  |  |
| Recommendations Find alternate work/project for workers if a project should come to a sudden stop. |  |  |  |
| Communications |  |  |  |
| Process Review A lack of progress reports detailing status of the project were not included in the project plan. |  |  |  |
| Lessons Learnt Communication documentation needs to be included in the project plan to make it of value and to be of success. |  |  |  |
| Recommendations All progress status reports included in the project plan and communicated to all members of the project team |  |  |  |
| Procurement |  |  |  |
| Process Review A change in the excavation contractor in the middle of the project |  |  |  |
| Lessons Learnt The new contractor was a success despite the rushed replacement process to get them to price the work and get them on site to start. |  |  |  |
| Recommendations To have backup replacement contractors should problems occur in furture. |  |  |  |
| Risk |  |  |  |
| Process Review Risks in regards to project ownership were not considered. |  |  |  |
| Lessons Learnt Stakeholder and staff changes were not considered in the risk management documentation, thus new staff replacement rushed through, backup staff need to be regarded. |  |  |  |
| Recommendations Above risks need to be documented and used for furture projects. |  |  |  |
| Project Integration |  |  |  |
| Process Review The project ownership change did not have too much impact on the project integration |  |  |  |
| Lessons Learnt The project plan overall had strong procedures that meant that the project was able to keep on course even with change of ownership and new landscapers issuses. |  |  |  |
| Recommendations Furture project plans should include project status reports and project history of other projects, this would provide backgrounds for similar projects. |  |  |  |

- Sam has approved the report in the above question to be distributed. He has also updated the project plan following your advice. Now he is ready for the project closure meeting. He has assigned you the task of organising this meeting. Answer the questions that follow.

- Who will attend this meeting? Guidance: List the attendees by name, job title, and organisation).

Sam Ng - Project Manager ( Awesome Landscapes Pty Ltd ) Kim Nguyen - Director ( Awesome Landscapes Pty Ltd ) Terrence Mackay - General Manager ( Cadcade Peak Hotel ) Stephen Lyons - Planning Manager ( Cascade Peak Shire Council ) Kate Chan - Project Manager ( Timber Home Construction Ltd )

- What information will each person need before the meeting?

Locations, date and time of meetings. draft copies of the documents that are required to be signed off.

- Which documents (and which version number of each document) will need to be printed off for the meeting?

The final version of the project plan and the project charter. Also, the project sign off sheet and the project report.

- Which of these documents will require signatures?

All of them

- Who will need to sign off on these documents?

members of the steering committee (signatories)

- Do you believe the project objectives aligned with the objectives of Awesome Landscapes throughout the entire project life cycle? Explain your answer.

Yes. the scope of the project remained true to the vision at the start.

- What needs to be done after the meeting to complete the closure of the project?

project manager must ensure all documents have been signed. The final invoice must be issued. the final financial audit shall be filed and project documents must be archived.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document