## Cover Page - Index
Quality Management Plan / Checklist
Project Name: | Kingsgate Offices | Job No.: | 800729
Project Manager: | Daniel Moller | Date: | 20.6.2020
Supervisor | Jesse Ace
TABLE OF CONTENTS
|  |  |  | 1 | Project Initiation
|  |  |  | 2 | Pre-Restoration
|  |  |  | 3 | Final Inspections - Certificates
|  |  |  | 4 | Health, Safety & Environment
|  |  |  | 5 | Site Setup
|  |  |  | 6 | Remediation Works
|  |  |  | 7 | Flooring Reinstatement
|  |  |  | 8 | Gyprock Reinstatement
|  |  |  | 9 | Skirtings & Architraves
|  |  |  | 10 | Painting
|  |  |  | 11 | Contents Return
|  |  |  | 12 | Project Completion

## QMP Instruction Sheet
QUALITY MANAGEMENT PLAN INSTRUCTION SHEET
Quality Management Plans are a means of checking and verifying conformance of completed work, to specified requirements prior to returning to service, or handing-over to the Client.
1. | The Project Manager shall prepare QMP from the master copy adding or omitting additional Quality Management activities required specific to the project
2. | Have Supervisor check QMP and comment
3. | Issue signed ITP’s to Supervisor with a copy for distribution and file
4. | Ensure that completed sheets are returned at completion of project and deadfiled
5. | Prepare further QMP sheet for variations when required
6. | (H) Hold Point – work must not proceed until the inspection and/or test has been completed.
(W) Witness Point – 3rd party to be advised when inspection or test is to be performed.
(D) Document Point – certificate or report is required.

## Template
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor Name | Jesse Ace
Job No: | 800729 | Task: | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA | ITP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No, IICRC Standard ) | (Specific requirements of Aust. Standard, IICRC Standards Contract Clauses, Manufacturers Recommendations)
|  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
H = Hold Point Work must not proceed until the inspection and/or test has been completed
W = Witness Point 3rd party to be advised when inspection or test is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “ITP Verifications” column.
When preparing the ITP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed Solutions: Remeed Solutions S/Contr: Subcontractor

## Project Initi
Quality Management Plan / Checklist
Project: | Brassall Offices | Supervisor: |  | Jesse Ace
Job No: | 800123 | Task | Project Initiation
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No, IICRC Standards Contract Clause, Manufacturers Recommendations. | (Specific requirements of Aust. Standard, IICRC Standards, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
PROJECT INITIATION
New Enquiry Memo |  | Claims Coordinator to document restoration request |  | D
Job Folders |  | Standard Suite of Folders created on the S Drive under Jobs & Encircle. Relevant information from submissions folder transferred |  | D
Signed Authority to proceed |  | Copy of Authority to Proceed (ATP) signed by client, scanned and saved in to job file & uploaded to encircle |  | D
Visual Reference |  | Site meeting with Project manager & supervisor for a visual breakdown of what is required |  | W
Project Contact List |  | Project contact list generated and uploaded to job file & Encircle |  | D
Constraints |  | Dicuss constraints of project with supervisor |  | W
Quality Requiments |  | Discuss quality requirements with supervisor |  | W
Project Deadlines |  | Discuss project deadlines and task dependancies with supervisor |  | W
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection
is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Pre-Restoration
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task | Pre-Restoration | [9 empty] | Cost Code: 800
Project Manager | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No, IICRC Standard, Contract Clauses, Specifications & Manufacturers Recommendations ) | (Specific requirements of Aust. Standard, IICRC Standards, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | GM | Initial | Date | Client / Consult | Initial | Date
ESTIMATING
Bill of Purchases | Completed and on file | Issued by Estimating |  | D
Sign off SOW to match estimate | Completed and on file | Estimating to review contract drawings |  |  |  |  | D
Prepare Contract Documents | Completed and on file | Complete DOW and contract set of documents |  |  |  |  | D
Estimate Review | Completed and on file | General Manager to approve |  |  |  |  | D
Project Commitment Review | Completed and on file | General Manager to approve |  |  |  |  | D
SCOPE
Restoration SOW | IICRC Standard S520 & S500 | General Manager to approve |  |  |  |  | D
Environmental | IICRC Standard S520 & S500, Sustainable Planning ACT 2009 | Satisfy council and environmental requirements & Requirements of body coorporate | [7 empty] | D
Quality Management Plan |  | As per contract |  |  |  |  | D |  |  | D
Electrical Isolation & Reinstatement | AS2293, AS 3000 | Must satisy legislative & WHS Standards | [7 empty] | D
WHS Documentation | WHS Act 2011 | As per contract |  |  |  |  | D
Gyprock Reinstatement | AS2589, AS2017 | Must satisy legislative & WHS Standards
Pre restoration Handover meeting | Project Quality & Scope documentation | As per contract |  | W |  |  | W |  |  | W
Flooring Reinstatement | AS1884, AS2012 | Must satisy legislative & WHS Standards
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Final Inspections-Certificates
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task | Final Inspections and Certificates | [9 empty] | Cost Code: N/A
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No., IICRC Standard, Contract Clause, Manufacturers Recommendations | (Specific requirements of Aust. Standard, IICRC Standard, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
COMPLETION
Inspections
Surface & Air Testing | IICRC Standard S520-2015 | [5 empty] | D
Project Manager |  | QMP |  | H
Certificates
Structural | AS 4100 | Form 16 |  |  |  |  | D
Electrical Installation– Emergency Lighting , and Exits | AS3012, AS019 | Form 16 |  |  |  |  | D
Waterproofing | AS3740 | Form 16 |  |  |  |  | D
General Power and Lighting | AS3002 | Form 16 |  |  |  |  | D
Floor Coverings | AS1884 | Form 16 |  |  |  |  | D
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## HSE
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor |  | Jesse Ace
Job No: | 800729 | Task | Health, Safety and Environment | [9 empty] | Cost Code: N/A
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No., IICRC Standard, Contract Clause, Manufacturers Recommendations | (Specific requirements of Aust. Standard, IICRC Standard, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
Work Health Safety and Environmental Management Plan
Developed and approved | WHS Act 2011 & Regulation 2011 | Signed off by Restoration Manager |  | D
Distribution | WHS Act 2011 & Regulation 2011 | Issued to Site |  | D
Safety Plans (site specific)
Restoration Works | IICRC Standards, WHS Act 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS
Carpentry Trades | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist HSE-DOC-010-02 |  |  |  |  | D/H
Electrical Services | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist HSE-DOC-010-02 |  |  |  |  | D/H
Gyprock Installation | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist HSE-DOC-010-02 |  |  |  |  | D/H
Floor Coverings | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist HSE-DOC-010-02 |  |  |  |  | D/H
Painting | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist HSE-DOC-010-02 |  |  |  |  | D/H
H = Hold Point
Work must not proceed until the inspection
has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Site Setup
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task | Site Setup | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No. IICRC Standard , Contract Clause,, Manufacturers Recommendations | (Specific requirements of Aust. Standard, IICRC Standard, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
RISK ASSESSMENT/ SWMS | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS, SWMS review sheet completed |  | H |  |  | D
WHSE MANAGEMENT PLAN | WHS Act 2011 & Regulation 2011. | Signed off by Restoration Manager, Copy of WHSE Management Plan on site |  | H
PERIMETER TEMPORARY FENCING | WHS Management Plan | Works completed as per WHS Mangement Plan |  | W
|  | Visual inspection |  | W
PEDESTRIAN MANAGEMENT PLAN | WHS Act 2011 & Regulation 2011 | Install as per approved pedestrian management plan Copy of plan on site |  | H |  |  | W
HAZARDOUS CHEMICALS | WHS Act 2011 & Regulation 2011. | Visual inspection of site and prepare hazardous chemicals report. Obtain copy of hazardous chemicals report held on site & discussed in site inductions |  | H | [5 empty] | D
WASTE MANAGEMENT PLAN | WHS Act 2011 & Regulation 2011. | Waste management plan has been prepared and forwarded to construction |  | W |  |  | D |  |  | D
Specification
| EPA guidelines | Waste material classification received. Obtain copy of approved waste management plan for the site
TEMPORARY SERVICES |  | Electrical cerificate from the contractor |  | D |  |  | D
H = Hold Point
Work must not proceed until the inspection and/or test has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Remediation Works
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task | Remediation - Structural & Contents | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No., IICRC Standard, Contract Clause, Manufacturers Recommendations | (Specific requirements of Aust. Standard, IICRC Standard, Contract Clauses, Specifications, Manufacturers Recommendations.
|  |  |  | Remeed | Initial | Date | PM | Initial | Date | Client / Consult | Initial | Date
HEPA Vacuum | WHS ACT 2011 | Safe work method statement complies with WHS Regulations, Filtration meets IICRC Requirements |  |  |  |  | D
Wire Brushing / Abrasive Scrubbing | WHS ACT 2011 | Safe work method statement complies with WHS Regulations, methodology meets IICRC Requirements |  |  |  |  | D
Antimicrobial Application | WHS ACT 2011 | Safe work method statement complies with WHS Regulations, methodology meets IICRC Requirements, MSDS supplied and in date |  |  |  |  | D
Air Monitoring | WHS ACT 2011 & IICRC Standards | Safe work method statement complies with WHS Regulations, Filtration / Capacity meets IICRC requirements |  |  |  |  | D
Containment | WHS ACT 2011 & IICRC Standard | Safe work method statement complies with WHS regulations, Meets IICRC Standards |  |  |  |  | D
Removal Works | WHS ACT 2011 & IICRC Standard | Safe work method statement complies with WHS regulations, Meets IICRC Standards |  |  |  |  | D
Risk Assessment / SWMS | WHS ACT 2011 & IICRC Standard | Safe work method statement complies with WHS Regulations. |  |  |  |  | D
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Flooring Reinstament
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task: | Flooring Reinstatement | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No., IICRC Standards, Contract Clause, , Manufacturers Recommendations | (Specific requirements of Aust. Standard, IICRC Standard, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
RISK ASSESSMENT/ SWMS | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist
PRODUCT SELECTION | Design,Australian Standard Specification description of works | Client sign off of floor coverings | [7 empty] | D
DRAWINGS | Drawings | Floor finishes plan issued | [7 empty] | D
SITE MEASURE | Approved shop drawings | Flooring contractor to provide shop drawing |  |  |  |  | D
OFF SITE FABRICATION | Specification,Drawing | Flooring contractor to confirm lead times |  |  |  |  | D
DELIVERY INSPECTION | Specification | Floor coverings matches colour boards |  | W
INSTALLATION | Setout as per architectural documents | Floor coverings installed as per finisshes plan, Remeed to monitor |  | W
| Australian Standard | Moisture tests undertaken |  |  |  |  | W
| Australian Standard | Ventilation requirements for adhesives reviewed and are being implemented and monitored |  | W |  |  | W
COMPLETION | Description of works | Verify against DOW
| Operation manuals and product data | Contractor to provide |  |  |  |  | D
| Defects | Defects developed and comlpleted, contractor is to sign off |  |  |  |  | D
| Specification | Operation manuals and product data contractor to provide |  |  |  |  | D
| Australian Standard | Form 16 from installer |  |  |  |  | D
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Gyprock Reinstatement
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task | Gyprock Reinstatement | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc)
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
RISK ASSESSMENT/ SWMS | WHS Act 2011 & Regulation 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | H
Drawings | WHS Act 2011 | Meets requirements of drawings & codes |  | H
Delivery |  | Visual inspection |  | H
Installation | WHS Act 2011
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection or test is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Skirtings & Architraves
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task | Skirtings & Architraves | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No, IICRC Standard ) | (Specific requirements of Aust. Standard, IICRC Standards Contract Clauses, Manufacturers Recommendations)
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
RISK ASSESSMENT / SWMS | WHS Regulations 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | D
DRAWINGS | WHS Regulations 2011, AS 1684 | Meets requirements of drawings and codes |  | D
DELIVERY |  | Visual Inspection |  | D
INSTALLATION | WHS Regulations 2011, AS 1684 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | D
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed Solutions: Remeed Solutions S/Contr: Subcontractor

## Painting
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task: | Painting | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No., IICRC Standard, Contract Clause, Manufacturers Recommendations | (Specific requirements of Aust. Standard, IICRC Standard, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
RISK ASSESSMENT / SWMS | WHS Regulations 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | D
DRAWINGS | WHS Regulations 2011, AS2311, AS2017 | Meets requirements of drawings and codes |  | D
DELIVERY |  | Visual Inspection
APPLICATION | WHS Regulations 2011, AS2311,AS2017 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | D
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solutions S/Contr: Subcontractor

## Contents Return
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Task: | Contents Return | [9 empty] | Cost Code: 800
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No, IICRC Standard ) | (Specific requirements of Aust. Standard, IICRC Standards Contract Clauses, Manufacturers Recommendations)
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
RISK ASSESSMENT/ SWMS | WHS Regulations ACT 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | D
Delivery | WHS Regulations ACT 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | D
Installation | WHS Regulations ACT 2011 | Safe Work Method Statement complies with WHS Regulations and approved SWMS review checklist |  | D
Client Sign off |  | Client / Occupant to sign off on contents restoration and placement. | [7 empty] | D
H = Hold Point
Work must not proceed until the inspection has been completed
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed Solutions: Remeed Solutions S/Contr: Subcontractor

## Project Completion
Quality Management Plan / Checklist
Project: | Kingsgate Offices | Supervisor: |  | Jesse Ace
Job No: | 800729 | Trade: | Project Completion | [9 empty] | Cost Code: N/A
Project Manager: | Daniel Moller
Date Created: | 20.6.2020
WORK ACTIVITY | REFERENCE | ACCEPTANCE CRITERIA |  | QMP VERIFICATIONS (Initial & Date) | [8 empty] | COMMENTS / RECORDS (Evidence)
| (Aust. Standard No.,IICRC Standards, Contract Clause, Manufacturers Recommendations | (Specific requirements of Aust. Standard, IICRC Standard, Contract Clauses, Specifications, Manufacturers Recommendations
|  |  |  | Remeed | Initial | Date | S/contr | Initial | Date | Client / Consult | Initial | Date
QMP COMPLETION |  | Approved and signed off by Restoration Manager |  | W
IEP | As per contract documents |  |  | D
Final Report | As per contract documents |  |  | D
SITE PERSONNEL REGISTER | As per contract documents |  |  | D
Final Report | As per contract documents |  |  | D
SUBCONTRACTOR SUPPLIER ASSESSMENT | As per contract documents | PM to ensure that the assesment is completed |  | D |  |  | W
CLIENT SATISFACTION | As per contract documents | PM to ensure that the assesment is completed |  | D |  |  | D |  |  | D
PROJECT COMPLETION REVIEW MEETING | As per contract documents | Restoration Manager Review project with Project Manager |  | W
PROJECT COMPLETION FINAL SIGN OFF | As per contract documents | Approved and signed off by General Manager, Restoration Manager & Client |  | W/D | [5 empty] | D/W
W = Witness Point
3rd party to be advised when inspection is to be performed
D = Document Certificate or report is required
Note: Signatures & dates are required under “QMP Verifications” column.
When preparing the QMP, consider consequences of failure including safety of workers & public
PM: Project Manager Remeed: Remeed Solution S/Contr: Subcontractor
H = Hold Point
Work must not proceed until the inspection
has been completed