| JOB NUMBER: | P18-07 |  |  |
| --- | --- | --- | --- |
| CLIENT: | DTMR |  |  |
| PROJECT: | Rockhampton Northern Access Upgrade |  |  |
| LOCATION: | Site Office, Olive Street |  |  |
| DATE: | Wednesday 04th March 2020 |  |  |
| TIME: | 2:30pm |  |  |
| MEETING No: | #50 Chairperson Melanie Johnston |  |  |
| ATTENDANCE: | Karen Edgerton (KE) Ross Matthews (RM) Lawrence Siron (LS) Shannen Cassidy (SC) Pam Thomas (PT) | Bronson Butler (BB) Brendon Riddell (BR) Ben McKinnon (BM) Chris McPherson (CM) | Mel Johnston (MJ) Craig Southon (CS) Andrew Moore (AM) Siobhan Pagliano (SP) Heather Richards (HR) Dan Everson (DE) |
| APOLOGIES: | Heulyn Mix (HM) Dylan Stevens (DS) Jim Gabriel (JG) | Ivan Ridley (IR) Dale Graham (DG) David West (DW) | Nathan Clarke (NC) Claire Driessen (CD) Mark Stone (MS) |

| NO. | ITEM | ACTION | DATE |
| --- | --- | --- | --- |
|  | Safety Management |  |  |
|  | High Risk Audits for March; (MS to allocate Engineers to Audits) - Traffic – - Plant – - Chemicals – - First Aid – - Excavations – - Work @ Heights – - Electrical installation – |  | Ongoing |
|  | KPI’s:- Safety to provide statues update – has been sent out Aim for 1 per week – New Weekly inspection should help increase KPI’s | Safety MS | Ongoing |
|  | PTA’s: - - Engineers to get out on site to ‘approve’ PTAs - Needs to be specific to job – Task Specific - If you see PTA’s on site, please bring them back to the office - Please ensure Engineers are signing off - PTA’s found with missing information – Training to come - Challenge operator knowledge | Engineers | Ongoing |
|  | PJO’s:- Should have actions raised - Engage Workforce – ask them what they are doing and what are the hazards – compare to PTA - Challenge operators to know service locations - Ensure more photos are added - Permit number is now on | All | Note |
|  | SWMS Reviews: - Upcoming Subcontractor SWMS for review - RNAJV SWMS still reviewing – new packs to be issued – emergency response plan included - Engineers to review - Register to be made by Shannen | All RM | Ongoing |
|  | Training:- - TMI Training also needed - Dogman training to be organised 09/03/20 – 13/03/20 (Dan E, Jordan, Jeff & Alex) - NOTE: Let Mel know any training hours & names | DE | Ongoing Ongoing |
|  | NCR’s related to safety please be forwarded to Safety Team |  | Note |
|  | Plant register Review done – VOC Audit is underway Stickers on hard hats |  |  |
|  | Inductions to be completed on Monday & Wednesday only – Keep Safety updated email to Safety email in case one is away/sick. Note: Visitor inductions to be logged in visitor register | SC |  |
|  | Heat exposure potential |  | Note |
|  | Walk & talk inspection (weekly at 11am) |  | Note |
|  | Risk assessment for excavation permits |  |  |
|  | Environment |  |  |
|  | Air Quality currently at – max is 80 |  |  |
|  | Ensure subcontractors areas are tidy |  | Note |
|  | Dust collection monitors went out (01.12.19) (will be sent individually) – One to possible be put at Cap Motel |  | Note |
|  | PJO’s Environmental aspects as well | BB |  |
|  | Throwing out cans & plastic bottles – need to remind staff at prestart to use correct bins |  |  |
|  | Lucidity report to come from today’s inspection with actions required before we get any rain. |  |  |
|  | Weeds growing at both complexes “control regrowth” – Weed spraying to be organised |  |  |
|  | EMP updated |  |  |
|  | 150m rain |  |  |
|  | Rock filling dam |  |  |
|  | Sediment drains to be cleaned out |  |  |
|  | Rainfall Recording Dylan |  |  |
|  | TOPO audit |  |  |
|  | Sustainability | DS |  |
|  | Waste productions report sent - Demolition report to come from Abbyss |  |  |
|  | Profiling material being stockpiled for later use, reclaimed materials – Testing is it any good? |  |  |
|  | Jan Sustainability Report Received |  |  |
|  | Stakeholders – Comms, Relationships, Complaints etc. |  |  |
|  | VCV and Tony Champion have raised concerns about the temporary fencing arrangement in front of their property and the period it has been implemented for. They are particularly concerned about security. PT to be updated with all progress to keep them informed and reduce the frustration. |  | Ongoing |
|  | Spoil Agreements – Council issued Breeches – need to check what has been delivered and ensure we are following council permits. | PT |  |
|  | - Heritage Village Bus Parking arrangements finalised waiting on construction date and implementation period – Agreement is ready |  |  |
|  | Cav’s have asked for complaint & accident register |  |  |
|  | CQU requested a site visit |  |  |
|  | Construction Program |  |  |
|  | Current Approved Contract Program is Rev 04.07 1/08/2019 Upcoming Milestones: - Ramsay Creek Switch 16/04/20 - B6 & B7 08/04/20 - Y4 20/03/20 |  | Ongoing |
|  | 10 at 2 meeting summary |  |  |
|  | PUP Works by PUP Authorities: APA - Done Telstra - Will be back on site NBN - Done FRW - Removal of redundant pipes ongoing. APA procedures pending to complete - Old Watermain Ergon | Note Note |  |
|  | PUP Works by JV: Water - Water main @ Ramsey W11 after existing bridge demolition Sewer - Sewer S3 redesign done - S2 Levels Gas - S2 Commenced | KE/DS KE/DS |  |
|  | Electrical Works (Signals & Road Lighting): - Ergon Signals Road Lighting | Note |  |
|  | Structures: Limestone Creek NB - Remob Avopiling Ramsay Creek NB South Bound | BB |  |
|  | Project Documentation and RFI’s |  |  |
|  | - Do not make changes to confirmed Lots – tell Karen as Cavs need to be informed of changes. | Note |  |
|  | - Archiving ongoing | Note |  |
|  | - RFI- Pretesting subgrade |  |  |
|  | - Rejected lots need documentation – amount outstanding is increasing (28 lots outstanding)– 04/03/20 - Close out RFI’s |  |  |
|  | Contract Issues, Variations and Status of Variations |  |  |
|  | Potential Variations: -. - Retaining Wall Fencing – RFI received but poor response - Cap motel sign - Sub soil Boundary Road – landscaping - Water main @ Terranova - Painting noise wall - Landscape - Notice of potential delays - If it’s your domain, please ensure you state how & why it is a discrepancy - Disruption claim | BM BB | Note |
|  | Progress Claims, EOT’s and Status of EOT’s |  |  |
|  | EOT:- - Original PC Date: 20/05/2020 - Approved delays: 286.5 days - Revised PC Date: 08/05/2021 - Further EOT to be claimed for PUP delays - EOT-012 (Approved) | Note |  |
|  | Draft Claim Due 30/03/20 EP Forecast |  |  |
|  | Wet weather days need to be emailed | CS | Note |
|  | Notices of possible delay to be submitted: - 14 submitted to date |  | Note |
|  | Subcontractors & Suppliers |  |  |
|  | Complete checklist prior to bringing subcontractor on board – Also let Mel know so account can be opened, and they get MCE approved. |  | Note |
|  | Packages still to be let: Noise walls BB Driveway Pavements |  |  |
|  | Upcoming - Allstate |  | Ongoing |
|  | Resources & HR |  |  |
|  | Upcoming Leave - 13/03/20 CM - 20/03/20 – 09/04/20 HM - 27/03/20- 31/03/20 SP - 14/04/20 SP - 14/04/20 – 19/4/20 MJ - 8/05/20-18/05/20 MS - 30/05/20 – 19/06/20 BB - 24/06/20 - 29/06/20 KE & BR | Note |  |
|  | Site Facilities |  |  |
|  | - Toilets to be checked Twice a week minimum for toilet paper, hand towels and soap supply levels | Note |  |
|  | - Please ensure you are washing and putting your dishes away | Note |  |
|  | - Storage container needs to be closed at all times |  |  |
|  | Traffic Management |  |  |
|  | Long Term (CTGS) Current Arrangements: - CTGS03 Stg 2 - Nuttall St to Bdy Rd Sth - CTGS06 Stg 1 – Boundary Rd Nth intersection - CTGS02 – JRT to Ramsay Creek - CTGS09 Stg 1 – Ramsay Creek to Nth Limit of Works - CTGS08 Stg 2 – Boundary Rd Sth Upcoming Staging: - CTGS03-3 Nuttall St to Bdy Rd Sth. - Concept with HDR - CTGS02-1 JRT to Ramsay Ck - CTGS09-2 Ramsay Ck to Nth Limit of Works - CTGS11-1 Barriers for C3/C4 Culvert – Approved - CTGS08-3 Boundary Rd Sth – Approved - CTGS08-4 Boundary Rd Sth – with HDR MS to ask CAVS about smiley face signs – monthly meeting | AMc/KE MS | 13/02/20 |
|  | Short Term (TGS) Requested TGS: JRT Driveway Upcoming TGS Requirements: - Drainage works at Terranova – to be sent to Schramm for drafting - Night shift drainage works (highway crossings) – TGS063 to be used | KE KE |  |
|  | Lighting needs to be checked – not compliant in areas |  |  |
|  | Quality Management |  |  |
|  | Lot status - Target to keep closed lots at 81%. 85% closed Current stats (Refer attached Civil pro summary charts) - Guaranteed 7% - Open 12 % - Conformed 73% - Rejected 7% Notes: - 117 Lots older than 60 days - Priority to keep working on these lots over 60days - Do not change numbers - Close out as many as possible before claim - Check all supporting documents are also sent - Target is to have 50 remaining |  |  |
|  | Client & Consultants |  |  |
|  | - Engage with Civil Support while on site - While doing walk the talk ensure you are talking to the subcontractors etc |  |  |
|  | Other Business |  |  |
|  | Next Site BBQ: Evolution |  | Note |
|  | Chairperson next week – Mark |  | Note |
|  | Minute Taker next week – Siobhan |  | Note |
|  | NEXT MEETING: 11th March 2020 | TIME: | 2.30pm |