## Construction Schedule
STATUS
Construction Schedule | [6 empty] | Not Started
Project Name: |  | Strart Date: |  | Total Duration: |  |  | In Progress
Complete
Project Manager: |  | End Date: |  |  |  |  | On Hold
TASK DESCRIPTION | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION | COMMENTS
Planning | Complete |  | 2025-09-21 | 2025-09-30 | 10
Raw Material Accumulation | Complete |  | 2025-10-01 | 2025-10-06 | 6
Basement Creation | Complete |  | 2025-10-06 | 2025-10-24 | 19
Floors Creation | Complete |  | 2025-10-25 | 2025-10-29 | 5
Light Fittings | Complete |  | 2025-11-01 | 2025-11-13 | 13
Sewage Pipelines | Complete |  | 2025-11-13 | 2025-11-15 | 3
Painting | In Progress |  | 2025-10-25 | 2025-12-05 | 20
Accessories Installation | In Progress |  | 2025-11-19 | 2025-12-10 | 22
AC Installation | In Progress |  | 2025-10-29 | 2025-12-09 | 5
Fire Extingushers | In Progress |  | 2025-11-22 | 2025-12-15 | 24
Parking Space | Not Started |  | 2025-11-29 | 2025-12-20 | 22
Appliances | On Hold |  | 2025-12-10 | 2025-12-22 | 13
Plumbing | In Progress |  | 2025-12-10 | 2025-12-15 | 6
Final Inspections | Not Started |  | 2025-12-27 | 2025-12-30 | 4
Wrap up | Not Started |  | 2025-12-03 | 2025-12-21 | 19
House Cleaning | Not Started |  | 2026-01-03 | 2026-01-23 | 21
Complete | Not Started |  | 2026-01-03 | 2026-01-17 | 15