## Sheet1
Planning permission |  | 200 | Planning permission $200 |  |  |  |  | 200
Preparing ground |  |  | Preparing ground
|  |  | Trenching machine | 8 hours X $140 |  |  |  | 1120
Trenching machine | 8 hours X $140 | 1120 | Labour |  | 8 hours X $32 |  |  | 256
Labour | 8 hours X $28 | 224
|  |  | Slab $3400 |  |  |  |  | 3200
Slab |  | 3200
|  |  | Shed cost $4500 |  |  |  |  | 4500
Shed cost $4500 |  | 4500 | Labour – 5.5 labour days X 8 hours per day X $32 |  |  |  |  | 1408
Labour – 5 labour days X 8 hours per day X $28 |  | 1120
Installing electrics
Installing electrics |  |  | Electrician budget $110 X 3 hours |  |  |  |  | 330
Electrician $90 X 3 hours |  | 2700 | Electrical goods $185 |  |  |  |  | 185
Electrical goods $185 |  | 185
|  |  | Work bench $650 |  |  |  |  | 650
Work bench $500 |  | 500
Cupboards
Cupboards |  |  | Cupboard packs $250 |  |  |  |  | 250
Cupboard packs $250 |  | 250 | Constructing cupboards – labour 2 hours X $32/hr |  |  |  |  | 64
Constructing cupboards – labour 2 hours X $32/hr |  | 64
Total |  | 14063 | Actual cost |  |  |  | Total | 12163
Variance threshold is 10% |  | 15469.3
|  |  | Variance threshold is 10% |  |  | 15469.3
|  |  | Actual cost |  |  | 12163
|  |  | Margain |  |  | 3306.3