Practical task work plan.

| Team leader | Delegates works, supports team, focus on goals |
| --- | --- |
| Steel stud framers | Construction of steel frames and ceilings |
| Gyprockers | Construction of internal and external linings |
| Plasterers | Provides required finish for painters |
| Client builder | Inspection and approvals, |
| Foreman | Contact between builder and construction team, provides planning and knowledge. |

Practical task:   Construct elevator lobby

Progress schedule.

10/10/19, meeting with foreman and client builder to discuss upcoming works to elevator lobby. Discussed timeframe and design specifics.

Held toolbox meeting before works with necessary trades persons required for project to show project plan specifics, discuss roles and responsibilities and timeframes required.

11/10/19, problem with existing plumbing services obstructing design specific curved walls. Instructed tradesmen to work in another area until problem resolved. Meeting with client builder and plumbing supervisor to resolve issue, conclusion variation to curved wall resulting in additional works and loss of productivity at cost of builder.

14/10/19, steel framing complete and electrical and fire services installed and inspected by appropriate persons. Started to install gyprock ceilings and feature ply wall panelling.

15/10/19 completed gyprock and ply panelling ahead of required time. Plasterer to apply appropriate compound and finish.

16/10/19, completed elevator lobby construction ahead of predicted schedule, inspected by foreman and handed over to next team of tradesmen to complete necessary works.

Email to client builder in regards to service obstruction.

ClientBuilder@assesment.com

Subject: service obstructions and rectifications

Client builder, upon beginning construction in elevator lobby zone it has been found that pre existing plumbing services are to interfere with the agreed plans specifically curved wall zone rectification is required to continue construction.

Attached are a possible variation to resolve the issue please inspect and approve to continue work in this zone.

Morgan Chambers.

Team leader.

Email to construction team.

constructionteam@assesment.com

subject: service obstructions and rectifications

construction team,

we will be holding a toolbox meeting today after lunch at 11.00 am Infront of site office to discuss project delays and issue new and revised plans regarding the elevator lift lobby.

Morgan Chambers.

constructionteam@assesment.com

Subject: great work well done

Construction team,

On behalf of myself and our client builder I would like to thank and reward you all for you hard work going above and beyond in recent works.

This Friday I would like to invite you to a BBQ at 10.30 hosted by our client builder as a big thank you for completing the lift lobby area ahead of projected schedule.

Morgan Chambers.