CPCCBC4005A

Produce labour and material schedules for ordering

ASSESSMENT SUMMARY

The assessment activities for CPCCBC4005A Produce labour and material schedules for ordering cover all aspects of the unit of competency required. To demonstrate competence in this unit, a participant must undertake all tasks and complete them satisfactorily and consistently. For Apprentices and Trainees, this includes employer completion of the Employer Record Book (ERB).

Participants must read all the information given before starting any assessment task. The assessment tasks are intended to be equitable, fair and flexible. If a participant has any questions or requires alternative arrangements to be made such requests should be directed to their Trainer/Assessor, who should note such arrangements in the ‘Assessor Comments’ on the affected assessment. If a participant feels they are not yet ready to be assessed, they should discuss their options with their Trainer/Assessor.

To satisfactorily complete the assessment, the participant is required to answer all questions correctly and demonstrate their skills to industry standards. If a participant does not answer some questions or perform some tasks, they will be deemed ‘Not Satisfactory’ for the task and ‘Not Yet Competent’ for the unit of competency. The Trainer/Assessor is able to provide the participant with additional information on interpreting the assessment outcomes and provide guidance on the participant’s options. Should a participant still be deemed ‘Not Satisfactory’ they will have the opportunity to undertake a supplementary assessment or appeal the result.

By signing the cover page for each assessment item, the participant acknowledges they understand the assessment instructions and requirements and consent to being assessed. The participant also verifies and assures the RTO that the work submitted is their own work.

| Participant Name | Christine Muter |
| --- | --- |

| Task | Assessment Results |  |
| --- | --- | --- |
| Theory Exam | Satisfactory | Not Yet Satisfactory |
| Practical Assessment | Satisfactory | Not Yet Satisfactory |
| Outcome for Unit of Competency | Competent | Not Yet Competent |

| Assessor Name |  |
| --- | --- |
| Assessor Signature |  |
| Unit Competence Determination Date | Click here to enter a date. |

CPCCBC4005A

Produce labour and material schedules for ordering

THEORY EXAM INSTRUCTIONS - This exam will occur under standard assessment conditions. - An oral examination may be allowed under certain circumstances, whereby the Participant’s answers will be documented by a party other than the Participant. This must be acknowledged in writing (e.g. FT001 and Assessor Comments) - Participants must provide enough detail in their responses to demonstrate their knowledge and skills. - Please fill in the details below, providing your name, signature and date of assessment. - Your signature acknowledges that this is your own work. - Assessors are to complete marking in pen of a different colour to the Participant. - If a Participant initially answers a question incorrectly but modifies their response, they must follow the instructions below: - If a Participant changes their response in writing, they must put their initials next to the written change. - If a Participant changes their response verbally, this must be noted on the exam paper by the assessor.

| Participant name | Christine Muter |
| --- | --- |
| Participant signature |  |
| Date | 22/11/2021 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Number of questions | Number of questions answered correctly | Task outcome (Tick) |  |
| --- | --- | --- | --- |
| 30 |  | Satisfactory | Not Yet Satisfactory |

ASSESSOR Comments

- Which of the following contractual requirements will influence orders and labour and material schedules? Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Commencement date |  |
|  |  | Completion date |  |
|  |  | Contract price |  |

- Identify three (3) suppliers and three (3) contractors that you may need to work with when undertaking a building project.

| Answer | Suppliers | Contractors |  |
| --- | --- | --- | --- |
|  | Timber | Carpenter |  |
|  | Cement | Concreter |  |
|  | Roof Tiles | Plumber |  |

- Explain the difference between employees and contractors and how they are influenced by scheduling.

| Answer | An employee is one who is directed to compete work/tasks that are to be undertaken whereas a contractor can decide what work it is that they do, when they are to have it competed by and how the work is to be carried out. |  |
| --- | --- | --- |

- Identify one (1) local government authority and one (1) regulatory body that must be considered when producing schedules.

| Answer | Govt Authority: Local Council for eg the Gold Coast Council Regulatory Body: QBCC –Qld Building and Construction Commission |  |
| --- | --- | --- |

- Why should colour selections be included on the schedules?

| Answer | Colour selections should always be clear and in writing, this avoids the potential for variations that may lead to delays in completion and an unhappy client. It also confirms the availability of the product in that colour selection. |  |
| --- | --- | --- |

- True or False (Tick your response): If a project is in a heritage protected area, the council may specify the colours that should be used.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify your local council’s requirements regarding working hours and days. Explain how these requirements may affect your schedules.

| Answer | The Gold Coast City Council has outlined that building ork and or deliveries that make an audible noise must only take place between the hours of 6.30am to 6.30pm Monday to Saturday. No such works are permitted on a Sunday. A permit must also be obtained for construction works outside of these hours. Any restrictions could impact the construction life of a project so it is important to schedule works to fall within these parameters so the correct projection can be made for the project completion. Fines can also be issued if works carried out outside these hours of around $6892.00. |  |
| --- | --- | --- |

- Identify three (3) common drawings/specifications commonly used in the industry. Explain what information is provided by each document and how this influences labour and material schedules for ordering.

| Answer | Drawing/Specification | Information provided for labour and material schedules |  |
| --- | --- | --- | --- |
|  | Site plans | An overall view of the project on the building site, these can provide the builder/ surveyor with information about the required excavation works required for the project |  |
|  | Elevation Plans | A plan that shows what the building will look like from north, south, west and west |  |
|  | Sectional plans | A sectional view of the plan that allows the builder to identify the heights of the building from the ground level to the floor level and floor to ceiling heights to assist in identifying the amount of materials such as timber / beams are required |  |

- What three (3) things should a builder do when variations are made to a contract for a project?

| Answer | 1.If requested by the client, ask they put the variation in writing before work can commence on the work both the client and contractors must agree. 2.If it is not possible to put the variation in writing before the work commences it must be done within 24 hours of the works commencing and the client be made aware of any additional costs or delays due to the variation eg Unforseen issues at the time of excavation may increases costs and could result in an extension of time form being submitted. 3.All subsequent documents ie the contract signed by all parties within 5 business days of when the variation was agreed to . |  |
| --- | --- | --- |

- Identify two (2) variations that may be raised by the client and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Adding a room to the plan | Additional time would be required for the draftsperson to redraw the plans to include the room this may also result in delays fr approvals depending on when the decision was made my the client in the approvals process. The building site would then also need to be increased in is footprint. The materials would also increase as would the labour to create the additional room |  |
|  | Imported goods such as tiles | The shipment and delivery of the items may delay the works if international shipping is held up. |  |

- Identify two (2) variations that may be raised by the builder and explain how it would affect the schedules.

| Answer | Variation | Effect on schedules |  |
| --- | --- | --- | --- |
|  | Inclement weather | Weather delays particularly for external works such as landscaping, concreting etc will delay schedules until the weather clears and the site dries to a point it is safe/practical to again resume works |  |
|  | Material supply shortages | If previously advised that materials were available and ordered to arrive on a set date are delayed by transport/ shipping will effect scheduled and cause delays to the life cycle of the project until the materials arrive |  |

- Order the following steps from 1 to 5 to outline how a builder should select a supplier/contractor.

| Answer | Step Number | Steps |  |
| --- | --- | --- | --- |
|  | 1 | Builder to seek quotes from suppliers/contractors |  |
|  | 5 | Builder to note supplier/contractor details and ordering times on schedule |  |
|  | 3 | Builder to accept a tender |  |
|  | 2 | Suppliers/Contractors tender prices back to the builder |  |
|  | 4 | Parties to sign agreement |  |

- What is an ‘overlay drawing’?

| Answer | It provides some more visual clarity/ details on top of existing plans, they can be sketched by the builder or architect, if the drawings don’t encroach over the existing envelope, and don’t fundamentally change the structure of the building, no further building approvals are required |  |
| --- | --- | --- |

- Which of the following individuals may sketch overlay drawings? 
Tick all that apply.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Architects |  |
|  |  | Builder |  |
|  |  | Draftsmen |  |
|  |  | Engineers |  |

- Identify three (3) details that should be included on a work order and reflected on the labour schedule.

| Answer | Task Details Time line required Agreed rate |  |
| --- | --- | --- |

- Identify nine (9) details that should be included on a purchase order.

| Answer | 1 Order and Delivery date 2 Purchase order number 3 Supplier details 4 Delivery details – site address 5 Supplier contact information 6 Project manager/ site managers details 7 Product/ item description 8 Terms and conditions / special instructions eg – deliver to right side of driveway 9 Total order cost |  |
| --- | --- | --- |

- What is a ‘call forward sheet’?

| Answer | A call forward sheet is a document that is used by builders to track when materials are needed and when they should be ordered in accordance with the work schedule. It identifies a list of detailed tasks to be completed in chronological order. |  |
| --- | --- | --- |

- True or False (Tick your response): A builder would usually complete all the purchase orders before preparing a call forward sheet.

| Answer |  | True |  |  |
| --- | --- | --- | --- | --- |
|  |  | False |  |  |

- Identify two (2) approved plans that should be included with the site documents.

| Answer | Floor (architectural) plans of the building and its Elevation plans |  |
| --- | --- | --- |

- Match the site files and definitions below by writing the appropriate letter next to each number in the centre column.

| Answer | Document |  | Answers | Definition |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 | Permits | 1 - B | A | May include engineering data |  |
|  | 2 | Quotes | 2 - E | B | Council inspectors may issue a stop work notice until these documents are produced |  |
|  | 3 | Reports | 3 - A | C | Changes requested using a standard form in writing. Need to be signed by both builder and client. |  |
|  | 4 | Specifications | 4 - D | D | List the materials to be used, fittings and fixtures to be installed, and types of finishing required. |  |
|  | 5 | Variations | 5 - C | E | Used to ensure purchase orders are developed using the correct price. |  |

- In the table below, estimates for labour and actual costs for each trade are listed. Calculate the cost difference for each trade.

| Answer | Trade | Estimate | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Carpentry | 10,000 | 8,500 | -1,500 |  |
|  | Electrical | 3,000 | 4,250 | 1,250 |  |
|  | Painting | 4,000 | 3,900 | -$100 |  |
|  | Plumbing | 8,000 | 8,000 | $0.00 |  |
|  | Tiler | 4,500 | 4,750 | $250 |  |

- In the table below, the Prime Cost (PC) sums from a contract and actual costs for items are listed. Calculate the cost difference for each item.

| Answer | Item | PC sum | Actual cost | Cost difference |  |
| --- | --- | --- | --- | --- | --- |
|  | Basin taps | 100 | 130 | 30 |  |
|  | Oven | 2,500 | 1,500 | -1000 |  |
|  | Rangehood | 500 | 900 | 400 |  |
|  | Shower bases | 250 | 265 | 15 |  |
|  | Shower screen | 400 | 350 | -50 |  |
|  | Shower taps | 150 | 120 | -30 |  |
|  | Stove | 900 | 1,200 | 300 |  |

- Where the actual costs are higher than the estimated costs due to a client variation, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- Where the actual costs are higher than the estimated costs due to price increases of materials, who is responsible to pay the difference? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Builder |  |
|  |  | Client |  |
|  |  | Supplier |  |

- You are given the following table containing the costs for each month of the project.

| - Month | - Estimated cost | - Actual cost |
| --- | --- | --- |
| - March | - $36,450 | - $38,980 |
| - April | - $65,560 | - $62,350 |
| - May | - $62,450 | - $64,960 |
| - June | - $61,340 | - $61,050 |
| - July | - $40,590 | - $38,990 |
| - August | - $42,650 | - $42,550 |
| - September | - $35,780 | - $34,750 |
| - Total | - $344,820 | - $343,630 |

- Using the information in this table, how would you find out in which month the builder actually spent the most? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Plot both the estimated and actual costs on a graph |  |
|  |  | Plot the actual cost on a graph |  |
|  |  | Work out the difference between the estimated and actual costs |  |

- The following graph is a visual representation of the difference in each month.

- By looking at this graph can you see if the overall project was overestimated or underestimated? Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | No, you cannot see this directly from the graph |  |
|  |  | Yes, you can see this from the graph |  |

- The following graph is a visual representation of the accumulated difference across the project.

- Overall, was the project overestimated or underestimated? 
Tick your response.

| Answer | Choice | Possible Answers |  |
| --- | --- | --- | --- |
|  |  | Overestimated |  |
|  |  | Underestimated |  |

Refer to the following scenario and house plan to respond to Q28. to Q30.

SCENARIO

You are a site supervisor of a small residential project, as outlined below:

The building is to be constructed using brick veneer.

The building has a floor area of 133 square metres including garage.

The concrete slab floor with garage floor is incorporated.

The building will be constructed using hand built wall frame and prefabricated roof trusses.

The building will have a cement tiled roof and powder coated aluminium windows in timber reveals.

The driveway and landscaping are to be provided.

Services are available directly in front of the site.

The site is almost flat and will only need a scrape with minimal excavation.

The contract period is 120 days.

The total job has been pre-costed at $136,500.

Note: You are not required to estimate the quantity required.

- Using the list of materials prepared, find the following information for four (4) materials of your choice:

| Answer | Material | Lead-in time | Delivery date | Order date | Delivery requirements/ special considerations |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Concrete | 4 weeks, 3 days | 08.01.2021 | 05.11.2020 | Delivery 6.30am Code to front gate is 2233 |  |
|  | Timber and roof trusses | 6 weeks | 22.01.2021 | 10.11.2020 | Delivery required at 7:00am |  |
|  | Bricks | 4 weeks 3 days | 08.01.2021 | 05.11.2020 | 7.30am Deliver to right side of driveway |  |
|  | Roof tiles | 6 Weeks , 2 days | 29.01.2021 | 16.11.2020 | 6:30am Deliver to left side of driveway |  |

- Describe the process of ordering the following materials for your project. Be sure to consider the things that need to be considered:

| Answer | Material | Ordering process | Considerations |  |
| --- | --- | --- | --- | --- |
|  | External cladding | Search for suppliers on line or through recommendations from others in the industry,. Discuss the availability for the product the client would like with the supplier. Agree on a price and delivery date , then forward a purchase order outlining the product, deliver date, the agreed price and any other special requirements | If the product need to be transported interstate or from overseas this may impact dependant on shipping variables. If the product becomes obsolete during the ordering process an alternate product will need to be discussed with the client |  |
|  | Wall frame | Search for suppliers on line or through recommendations from others in the industry. If this work is being carried out by a subcontractor, a quote will need to be supplied and agreed on before works can commence | Inclement weather could delay the delivery and installation |  |
|  | Windows | Search for suppliers and installers on line or through recommendations from others in the industry. Discuss the availability of the product the client would like with the supplier. Agree on a price and install date , then forward a purchase order outlining the product, deliver date, the agreed price and any other special requirements | If the product need to be transported interstate or from overseas this may impact dependant on shipping variables. If the product becomes obsolete during the ordering process an alternate product will need to be discussed with the client |  |

- While excavating one corner of the project, you find the soil below is unsuitable for supporting the foundation. Refer to the relevant Building Regulator and complete their standard builder variation request documentation to be presented to the client.

| Answer | As attached |  |
| --- | --- | --- |

CPCCBC4005A

Produce labour and material schedules for ordering

PRACTICAL ASSESSMENT INSTRUCTIONS - The following practical assessment will require the Participant to complete work related activities. - The Assessor will conduct observations of the Participant’s work to determine whether they display sufficient practical skills and knowledge. - Please fill in the details below – providing your name, signature and date of assessment. - The Participant’s signature acknowledges that the Assessor provided clear instructions and the Participant understood what was required to complete this assessment. - The Assessor may substitute a Practical Task with an alternate task of equal value. - Alternate tasks must be fully documented by the assessor in the Assessor Comments area.

| Participant name | Christine Muter |
| --- | --- |
| Participant signature |  |
| Date | 22/11/2021 |

| Assessor name |  |
| --- | --- |
| Assessor signature |  |
| Date | Click here to enter a date. |

| Task | Task outcome (Tick) |  |
| --- | --- | --- |
|  | Satisfactory | Not Yet Satisfactory |
| Task 1 (Occasion 1) |  |  |
| Task 1 (Occasion 2) |  |  |

Assessor Comments

CPCCBC4005A

Produce labour and material schedules for ordering

| Practical Task 1 (2X) |  |  |  |
| --- | --- | --- | --- |
| Description of task: On two (2) occasions, a suitable observer is to verify the participant’s ability to produce schedules of resource requirements so that orders can be placed for materials and labour for projects, and costs can be recorded and tracked as they are incurred. - Occasion 1: Residential project - Occasion 2: Commercial project The participant is to gather evidence of how they have completed each component of the Practical Task, which is to be submitted with this Practical Assessment sheet. Evidence to be submitted may include: - A copy of a material/labour schedule or supplier list for a project - A copy of a purchase order for purchasing materials or other resources - A cost report - Site condition reports or dilapidation reports - Contract documents - Call forward sheets - Variations The observer is to provide detailed comments on the tasks completed by the participant. The assessor is to verify the observer’s comments in the Assessor Comments section, and provide the Practical Assessment outcome on the front cover of this document. |  |  |  |
| Resources required: Contract documentation (including plans and specifications), computer. |  |  |  |
| Assessment of task |  |  |  |
| Name of participant: | Christine Muter |  |  |
| Name of observer: | John Gammon |  |  |
| Role of observer (Confirm suitability to sign) | Construction Manager |  |  |
| Email address of observer | John.gammon@tbs.com.au |  |  |
| Signature of observer: |  |  |  |
| Date: | 22/11/2021 |  |  |
| When completing the task, did the participant: |  | Tick if satisfactorily completed. Provide comments if left unticked. |  |
|  |  | 1st Occasion | 2nd Occasion |
| - Consider all contract conditions in the schedules, including: - All contractual requirements - Local government and regulatory bodies’ conditions of approval - Colour selections - Variations to contracts, raised by the client or builder |  |  | Commercial projects do not form part of TBS Business model |
| - Produce material and labour schedules, including: - Details of nominated suppliers and contractors in work schedules - Application of contract rates |  |  | Commercial projects do not form part of TBS Business mode |
| - Produce relevant overlay drawings. |  | This does not form part of TBS Business model | Commercial works do not form part of TBS Business model l |
| - Include contract details and instructions on orders. |  |  | Commercial works do not form part of TBS Business model |
| - Prepare site files, including: - All necessary site documents, including plans and specifications - Preparation of call forward sheets, detailing all orders |  | This does not form part of TBS Business model | Commercial works do not form part of TBS Business model |
| - Analyse project costs against estimates during construction. |  |  | Commercial works do not form part of TBS Business model |
| - Analyse approved variation costs. |  |  | Commercial works do not form part of TBS Business model |
| - Provide a final project cost analysis. |  | This is completed by the regional managers | Commercial works do not form part of TBS Business model |
| - Maintain data files of standard costs, including: - Approved variation cost increases - Changes to standard plans, specifications, and cost files |  | Notification to supervisors of variation approvals – yes | Commercial works do not form part of TBS Business model |
| - Effectively communicate using the following methods: - Verbally using language/concepts appropriate to cultural differences - Non-verbal communication |  |  | Commercial works do not form part of TBS Business model |
| The Participant’s performance was: Satisfactory Not Satisfactory |  |  |  |

observer Comments

Although not all of the above practical requirements can be met within Christine’s Position Description, Christine is exposed to variation submissions and their approval process on a daily basis. Her role within the Company also requires her to communicate with various certifiers, competing the relevant Building approval forms for building approval, researching and submitting the required documentation to obtain Bushfire Ratings, and understanding what type of works require certification and approval. Christine is skilled at submitting work orders to trades detailing the requirements of the work to be undertaken, the cost permitted as per the quote provided and any identified specific additional information that the trades will need in order to deliver or access the properties they have been appointed to work at. I believe Christine has a firm understanding of this module.