## Version history
DATE | VERSION
31 January 2021 | 1.0

## Actual
| MONTH 1 | MONTH 3 | MONTH 3 | MONTH 4 | MONTH 5 | TOTAL
LABOUR COSTS
Superannuation | 2360 | 2360 | 2360 | 2360 | 2360 | 11800
Payroll | 30500 | 30500 | 30500 | 30500 | 30500 | 152500
Leaves | 1640 | 1640 | 1640 | 1640 | 1640 | 8200
Training | 940 | 940 | 940 | 940 | 940 | 4700
Development | 1560 | 1560 | 1560 | 1560 | 1560 | 7800
TOTAL | 37000 | 37000 | 37000 | 37000 | 37000 | 185000
MATERIAL COSTS
Purchasing | 10600 | 12000 | 11500 | 9000 | 7500 | 50600
Transportation | 4500 | 4500 | 4500 | 4500 | 4500 | 22500
Storage | 1900 | 1000 | 2500 | 1900 | 1200 | 8500
Plant rental | 5500 | 5500 | 5500 | 5500 | 2500 | 24500
Equipment rental | 6000 | 6000 | 3000 | 6000 | 2000 | 23000
TOTAL | 28500 | 29000 | 27000 | 26900 | 17700 | 129100

## Estimated
ESTIMATED
LABOUR COSTS
Superannuation | 10000
Payroll | 150000
Leaves | 8000
Training | 3000
Development | 7500
TOTAL | 178500
MATERIAL COSTS
Purchasing | 50000
Transportation | 22000
Storage | 8350
Plant rental | 24000
Equipment rental | 21500
TOTAL | 125850

## Discrepancies
PROJECT | Simulation
DATE COMPLETED | 2025-03-17
COMPLETED BY | Abbie Heaslip
| DISCREPANCY | REASONS FOR DISCREPANCY | HOW TO GET BACK ON TRACK
LABOUR COSTS
Superannuation | -1800 | Underestimated employee remuneration levels | Review remuneration levels and adjust future estimates
Payroll | -2500 | Overestimated due to unexpected project delays | Reallocate staff or accelerate project phases to catch up
Leaves | -200 | Less than anticipated sick leave | Implement wellness programs to reduce sick leave
Training | -1700 | Costs increased due to specialized training needs | Identify more cost-effective training providers or methods
Development | -300 | Incremental costs for additional certifications | Pursue group discounts or subsidies for certifications
TOTAL | -6500
MATERIAL COSTS
Purchasing | -600 | Bulk order discount not applied as expected | Renegotiate with suppliers or seek alternative discounts
Transportation | -500 | Freight costs increased due to fuel price hike | Explore more efficient routes or consolidate shipments
Storage | -150 | Overestimated space requirements | Downsize storage space or renegotiate storage contracts
Plant rental | -500 | Less usage than anticipated | Adjust rental agreements according to actual usage
Equipment rental | -1500 | Unexpected maintenance and repair costs | Perform regular maintenance checks to prevent issues
TOTAL | -3250