Assessment Workbook 1

BSB51415 Diploma

of Project Management

The Project Life Cycle

Version 1.11 Produced 16 October 2018

Copyright © 2020 CSTC Pty Ltd. All rights reserved. No part of this publication may be reproduced or distributed in any form or by any means, or stored in a database or retrieval system other than pursuant to the terms of the Copyright Act 1968 (Commonwealth), without the prior written permission of 
CSTC Pty Ltd

Version control & document history

| Date | Summary of modifications made | Version |
| --- | --- | --- |
| 14 April 2016 | Version 1.0 produced following Training Package update | V1.0 |
| 22 June 2017 | Updated Table of Contents. | V1.1 |
| 16 October 2018 | Change to Practical Assessment | V1.11 |

# Table of Contents

This is an interactive table of contents. If you are viewing this document in Acrobat, clicking on a heading will transfer you to that page. If you have this document open in Word, you will need to hold down the Control key while clicking for this to work.

Table of Contents	3

Assessment Workbook Cover Sheet	4

Written Questions	5

Case Study	16

Instructions to Student	16

Introduction	17

Workbook Checklist	26

# Assessment Workbook Cover Sheet

| WORKBOOK: | Workbook 1 |  |  |
| --- | --- | --- | --- |
| TITLE: | The Project Life Cycle |  |  |
| FIRST AND SURNAME: | Cameron Smith |  |  |
| PHONE: | 0488124465 |  |  |
| EMAIL: | cam_smith21@hotmail.com |  |  |
| Please read the Candidate Declaration below and if you agree to the terms of the declaration sign and date in the space provided. |  |  |  |
| By submitting this work, I declare that: - I have been advised of the assessment requirements, have been made aware of my rights and responsibilities as an assessment candidate, and choose to be assessed at this time. - I am aware that there is a limit to the number of submissions that I can make for each assessment and I am submitting all documents required to complete this Assessment Workbook. - I have organised and named the files I am submitting according to the instructions provided and I am aware that my assessor will not assess work that cannot be clearly identified and may request the work be resubmitted according to the correct process. - This work is my own and contains no material written by another person except where due reference is made. I am aware that a false declaration may lead to the withdrawal of a qualification or statement of attainment. - I am aware that there is a policy of checking the validity of qualifications that I submit as evidence as well as the qualifications/evidence of parties who verify my performance or observable skills. I give my consent to contact these parties for verification purposes. |  |  |  |
| Name :Cam Smith |  | Signature: CS | Date: 12-05-20 |

# Written Questions

| - Below are the different stages of the lifecycle of a project. Match each lifecycle stage to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
|  | Stage | Description |
| C | Scoping | - It is during this phase that a project management plan is developed all comprehensive of individual plans for – cost, scope, time, quality, communication, risk and resources. Some of the important activities that mark this phase are -making WBS, development of schedule, milestone charts, GANTT charts, estimating and reserving resources, planning dates and modes of communication with stakeholders based on milestones, deadlines and important deliveries. |
| A | Planning | - It is in this phase that the project deliverable is developed and completed, adhering to the plan as developed in the previous phase. The project execution and project monitoring and Control are the 2 phases that mostly occur simultaneously. A lot of project management tasks during this phase capture project metrics through tasks like status meetings and project development updates, status reports, human resource development and performance reports. |
| B | Implementation | - A project is formally started, named and defined at a broad level during this phase. Project sponsors and other important stakeholders perform their due diligence on whether or not to undertake a project, or choose to undertake one project over another. Depending on the nature of the project, feasibility studies are conducted or as it may require. |
| E | Monitoring | - It includes a series of important tasks such as making the delivery, relieving resources, reward and recognition to the team members and formal termination of contractors in case they were employed on the project. |
| D | Closing | - This phase mostly deals with measuring the project performance and progression with respect to the project management plan. Scope verification and control to check and monitor for scope creep, change control to track and manage changes to project requirement, calculating key performance indicators for cost and time are to measure the degree of variation if any and in which case corrective measures are determined and suggested to keep project on track. |

- Consider a project that you are currently working on or you would most likely work on in the future. Provide an outline of typical project phases that would take place during the Implementation Stage of this project.

Given I work in the electrical/communications industry the typical implantation staging of any job is, Phase 1 Going over plans and assessing routes, Phase 2 Pathways (cable tray, basket , conduits) Phase 3 Cable Install (pull in cables) Phase 4 Terminations and Equipment Install Phase 5 Test and commission.

| - The following are various structures in which the Implementation Stage of the project can be carried out. Match each structure to its correct descripition. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Structure |  | Description |
| D | Sequential phase-to-phase relationship | - Projects intended to respond to high levels of change and ongoing stakeholder involvement. Also very iterative and incremental but differ in iterations being very rapid (2-4 weeks) and are fixed in time and cost. |
| E | Overlapping phase-to-phase relationship | - The project phases (more commonly known as iterations) repeat one or more project activities as the project team’s understanding of the product increases. |
| C | Predictive life cycle | - The project phases repeat one or more project activities as the project team’s understanding of the product increases. |
| B | Iterative/incremental life cycle | - In this structure, a new phase starts only when a previous phase is complete. The step-by-step nature of this approach reduces uncertainty, but may eliminate options for reducing the schedule. |
| A | Adaptive Life Cycle | - This is where a phase starts prior to the completion of a previous one. This can sometimes be applied as an example of the schedule compression technique called fast tracking. Overlapping phases may increase risk and can result in rework if a subsequent phase progresses before accurate information is available from the previous phase. |

| - Which of the following are activities that usually take place as part of the closing of a project? Select all that apply. |  |
| --- | --- |
|  | - Project evaluation |
|  | - Warrantee requirements |
|  | - Create communications log |
|  | - Develop project management plan |
|  | - Writing and delivery of project final report |
|  | - Finalisation of accounts and other financial documentation |
|  | - Delvelop project charter |
|  | - Handover of project deliverables |
|  | - Settling of financial liabilities |
|  | - Project evaluation |
|  | - Identify stakeholders |
|  | - Signing off by the project sponsor |
|  | - Finalise lessons learnt documentation and communicating it where needed |
|  | - Transition of responsibility or ownership of project deliverables or products |
|  | - Archiving of project documentation |

| - The following are different methodologies used to break project objectives into achievable project deliverables. Match each of the following to its correct description. Write the letter of your answer in the spaces provided. |  |  |
| --- | --- | --- |
| Methodology |  | Description |
| D | Project governance | - A document that formally authorises a project or a phase. It includes the initial requirements that satisfy the stakeholders’ needs and expectations. It provides the overall high level description of the strategies and goals of your project. |
| B | Project management information system | - An automated tool, such as scheduling software tool, a configuration management system, and information collection and distribution system or web interfaces to other outline automated systems. |
| A | Project charter | - A document covering all the details of the project down to a very detailed level. It can be presented in the form of a Gantt chart or any other document that displays project activities along a timeline. |
| E | Work Breakdown Structure | - It provides a management structure for the project manager and their team to deliver the project. It provides the support, processes and tools needed for the project to be delivered. |
| C | Project plan | - A document detailing the subdivision of project deliverables into smaller more manageable components. |

| - Below are different types of project governance models. Match each model to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Project governance model |  | Description |
| B | Programmatic Based | - In this model, project managers have a high level of authority to manage and control the project resources. The project manager in this structure has total authority over the project and can acquire resources needed to accomplish project objectives from within or outside the parent organization, subject only to the scope, quality, and budget constraints identified in the project. |
| C | Matrix Based | - A traditional structure in which program sector managers have formal authority over most resources. It is only suitable for projects within one program sector. |
| A | Project Based | - This model allows program units to focus on their specific technical competencies and allow projects to be staffed with specialists from throughout the organisation. |

| - List two (2) documentation that must be created to record strategies and goals for integration processes. In your own words, briefly describe each documentation. Do not exceed fifty (50) words for each discussion |  |
| --- | --- |
| Documentation | Discussion |
| Project Charter | Is a document designed for the stakeholders. Giving them the broad overal details of the project i.e cost, time, quality etc. |
| Project Plan | This is the PM's project bible. Detailed plan of the project, usually presented in timeline form such as a GANTT chart. The GANTT chart will break down milestone events and also individual trade requirements/dates |

| - Consider the communication media you would utilise in project management. - List three (3) communication media you would utilise in project management. - Discuss how each communication media is applied on various projects. |  |
| --- | --- |
| Communication media | Discussion |
| Verbal | May include the likes of a phone conference regarding the project, general site conversations etc |
| Non-Verbal | This may include but not limited to hand gestures |
| Written | Emails, written reports and other associated documents |

| - Discuss how each of the following communication methods below is applied on various projects. - Verbal communication - Non-verbal communication - Written communication In your discussion, include at least one (1) specific example or scenario on how each communication method is applied on various projects. |  |
| --- | --- |
| Communication Method | Discussion (with at least one (1) specific example or scenario for each communication method) |
| Verbal communication | Onsite meetings regarding issues/access, generally in the form of a onsite pre-start meeting. We also had builders brief meetings each night to discuss the next days plans. Also includes any project meetings |
| Non-verbal communication | Getting trades to mark-up on walls/floors etc where other services are clashing. I have marked up tray penetrations on walls for other trades to show exactly where our penetrations are going to be so there is no confusion. |
| Written communication | If in doubt or we required specific details I would get the builder to issue a Site Instruction with all the relevant details regarding the change in plans etc. This would also include amended plans, general site based emails etc |

| - List two (2) types of project management information systems (PMIS) and, in your own words, discuss how each is applied in project management. Do not exceed 50 words for each discussion. |  |
| --- | --- |
| Information systems | Application |
| Computer-based PMIS | These are the programs that you have on your computer that are designed to create your project requirements Microsoft Project, Project Scheduler, Primavera etc |
| Web-based PMIS | Utilises the internet to keep the project on time. Meaning that not all project team members are required to be onsite all of the time. Asana, Workzone, Proofhub are a few examples. |

| - The following are methods used to evaluate information systems and communication processes. Match each method to its correct description. Write the letters that correspond to your answers in the spaces provided. |  |  |
| --- | --- | --- |
| Method |  | Description |
| D | System quality | - A performance measure to evaluate the efficiency of an investment (such as in this case, resources used to facilitate project communication). It measures the return on an investment relative to the investment’s cost. |
| B | Information quality | - The information system is assessed in terms of accuracy of output, promptness of output, precision of output, reliability of output, arrival of output, output completions, and output format |
| A | ROI | - It is a useful tool for performing retrospective analyses of the characteristics of internal communication. With the help of this model we can obtain several interpretations of the characteristics of project communications which help improve the communication process and also the project management process. |
| C | Internal Communication Analysis Model | - The information system is assessed in terms of response time, accessibility, realization of user’s demands, correction of mistakes, model and data safety, system documentation and procedures, system flexibility and system compatibility. |

# Case Study

Instructions to Student

These case studies are hypothetical situations which will not require you to have access to a workplace, although your past and present workplace experiences may help with the responses you provide. You will be expected to encounter similar situations to these in future as you work in a project team environment.

In the real world you are likely to encounter the situation where you enter a project, taking over from another project manager. The documentation that is handed over to you is not necessarily up to scratch, and there could be serious issues with the project. This assessment captures that real life scenario.

The case studies are the first part of dealing with “multiple complex projects” required in all the units of this subject. The other assessment covering this requirement is the practical assessment. When you have completed the case studies you will be able to commence the practical assessment which covers the generic skills needed to function as an effective project team member. This assessment on the other hand covers the application of the underpinning knowledge and background theory.

Introduction

You have been appointed as a project management consultant to the project team at Awesome Landscapes Pty Ltd. Specifically, you are required to provide independent advice on seeing their current project throughout its entire lifecycle. You will be working in this project in every case study assessment throughout this course. The project involves the landscaping of a new eco-resort. The company has hired you on the basis of your ability to analyse project methodology, not on your knowledge of the nature of the landscaping work they perform. At this stage of the project the project charter and project plan have already been developed. You have been assigned to examine the project plan before the project launches in three months’ time. In particular you have been asked the following questions which you will need to provide answers for upon examination of the project charter and the project plan. The documents you need to complete the succeeding tasks can be accessed by accessing the following links: Project Charter version 1 (.pdf) Project Plan version 1 (.pdf) Project Gantt Chart (.mpp) Project Gantt Chart (.pdf) Project Network Diagram (username: cstclearner password: CstcPty@123) Note: These documents were generated in year 2016. For the purpose of this assessment, refer to ‘2016’ as the current year and ‘2017’ as the succeeding year.

| - List all personnel (name, title / designation, and company) who are required to sign off on the Project Plan before the project is endorsed for commencement. Discuss why each personnel you listed are required to sign off on the Project Plan. Do not exceed fifty (50) words for each discussion. |  |  |
| --- | --- | --- |
| Personnel | Title / Designation, Company | Discussion |
| Susan Wills | Massive Eco-Development Corp. PM | Susan is required to sign off on the project plan as she is the Project Sponsor and is required to sign off on all project contracts and other documentation |
| Stephen Lyons | Planning Manager, Council | Stephen is required to sign off on the project plan to make sure that all environmental requirements as stipulated by the council are adhered to throughout the project |
| Kate Chan | Timber Home Construction, PM | Kate is required to sign off on the project plan as she is the PM of the timber supplying company. |
| Kim Nguyen | Awesome Landscape, Director | Kim is required to sign off on the project plan due to being the director of the principal landscaping contractor |
| Sam Ng | Awesome Landscape, PM | Sam is the PM of lanscaping company. |

- Review the Project Plan. - Does the Project Plan show evidence that the project has been appropriately approved for commencement? - Does the Project Plan show evidence that it has been distributed to all stakeholders who are required to have a copy? Guidance: If it has been approved and distibuted, indicate which section(s) or page(s) in the Project Plan indicate so. If not, explain what needs to be done to have the project approved for commencement.

- Yes on page 6, all project steering committee members have signed off on the project.

- Yes on page 1, all project steering committee members have signed off that they have received a copy of the Project Plan

- How will the Project Outcomes be reported?

The project outcomes will be delivered in a final project meeting. In this meeting the following will be discussed and signed off, the project completion report, the final version of the project plan, the project archives checklist and the formal acceptance and closure.

- List all personnel (name, title/designation, company) who must have a copy of the Project Progress Reports. Discuss why each personnel you listed must have a copy of the Project Progress . Do not exceed fifty (50) words for each discussion.

| Personnel | Title / Designation, Company | Discussion |
| --- | --- | --- |
| Susan Wills | Massive Eco-Development Corp. PM | Susan requires a copy of the progress report as she is part of the sponsorship company and needs to be informed of progress of the build. |
| Robert Hinson | Massive Eco-Development Corp. PM | Same as above for Robert, he is also the main contact for any urgent informal correspondence on the project. |
| Kim Nguyen | Awesome Landscape, Director | Being director of the major landscaping contractor Kim needs to be aware of the staus of the project and how it is running |
| Sam Ng | Awesome Landscape, PM | Same as above for Sam, he also needs to be aware of how the other contractors on site are progressing, so if any are behind schedule he can assess his options early |
| Stephen Lyons | Planning Manager, Council | Stephen needs to be made aware of how the project is progressing so he can makes sure that all his inspections and site visits are being meet as per council requirements |
| Kate Chan | Timber Home Construction, PM | Same as Sam, Kate needs to be aware of any missed target dates or the project running behind schedule, so she can adjust her timber deliveries or milling dates |

| - At which stage of the project life cycle is the project? Assume the current date is 7 May 20xx, where 20xx is the current year. |  |
| --- | --- |
|  | - Scoping |
|  | - Planning |
|  | - Monitoring |
|  | - Implementation |
|  | - Closing |

- Discuss how Massive Eco-development Corporation is going to maintain effective integration between the three projects? Your discussion must be 100 – 200 words in length. Guidance: Why have the three projects been planned separately rather than being integrated into one single project? Discuss factors that ensure the effective running of the three projects running together as separate projects.

The project appears to have been broken down in three phases, it looks to me as though this is the case to help with council sign offs and also to help with the structure of the program. Given that the council requires 4 weeks notice to attend site to verify code compliance, I feel that this type of Project Phasing will be beneficial. I would say that the project has a sequential phase to phase relationship, so within the Phases of the project, you also have phases within that phase of construction. With a project that has such a task dependant relationship if you have an issue with one task it will have a knock on effect with the following tasks. But given the environmental status of this project this type of planning would be needed.

| - In your own words, discuss each of the following processes involved in the Closing Stage of the project. Do not exceed 150 words for each discussion. |  |
| --- | --- |
| Payment of Remaining Invoices | Means that all remaining payments to suppliers and contractors will be finalised before the closure of the project |
| Project Closure Meeting Documentation | a meeting will be held at the closure opf the project in this will show the results of the project, any lessons learnt and an audit report. It will also contain the project gantt chart indicating the project is complete, lessons learnt documentation will be included, a copy of the project completion report and also a final audit report on the project and particularly its costs will ne included, amongst other documents |
| Pre-meeting Audit | All the documentation that is covered in the project closure meeting will be evaluated by an independent auditor prior ti the final projct meeting |
| Final Project Meeting | All project steering committee members will attend the meeting, each member will be provided with a copy of the project documentation. Project report Final version of the project plan Project archives checklist Formal acceptance and closure The completion report, project plan and formal acceptance and closure documents must all be signed off by the committee. |
| Final Project Invoice | Once all documents have been signed off a Final invoice may be raised by Awesome for final contract payment |
| Project Archival | Once payment has been received the project documents may be archived in the appropriate manor. |

- How will the project be monitored?

The project will have weekly project meetings which will assess project progression and also as a prt pof these meetings if there are any issues they will get raised as a part of the sit down.

- Review the objectives of the project. - Do the objectives of the project align with the business objectives of Awesome Landscapes? Explain your reasoning. - Do the objectives of the project align with business objectives of project sponsor organisation? Explain your reasoning. Each discussion must be between 50 – 150 words.

- Yes, the objectives set out for the build are based apon being enviromentally conscious, disrupting and polluting the environment during the build to be kept to a minimum. Which aligns with Awesome lanscapes' vision statement of being as enviromentally friendly throughout the build as possible, restoring and using native plants to suit the local climate and habitat and to create an environment where future ongoing maintence will be kept to a minimum.

- Yes, Massive Eco-Development Corporation are a buisness that has created a name for themselves in the indusrty by developing and building eco friendly lodges and resorts. Given the location of their resorts, if there was an issue with the build or worse, enivornmental contamination to the build location, it would have a direct effect on the current build and also any future builds that may be in the pipelines.

- Sam has a gut feeling there will be some changes to the project once it commences. A rumour is spreading that there are going to be some additional chalets built requiring the construction of three more retaining walls than what appears in the project plan. He has specifically asked if he can approve and sign off on the extra construction himself knowing there is quite a big contingency budget to the project. Explain the procedure Sam would follow regarding the construction of the three additional retaining walls. Your discussion must not exceed 500 words. Guidance Answer Sam’s question by providing in your own words a specific procedure for the approval of the construction of three additional retaining walls. When mentioning any people in the procedure, list them by name and job title.

Although there is quite a big contingency budget, Sam would need to get the additional works signed off by Susan Wills( PM,Massive) & Stephen Lyons(Planning Manager, Council) and Kym Nguyen(Diector, Awesome) Once Sam had been formally notified of the additional retaining walls required for the new chalets, he would need to fill out an Appendix 38 Project Change Request form and submit it. Given that Awesome would already have a costings list from when they tendered the job, giving a quote for the additional works would be rather easy for Sam. As part of the Project Change Request, Sam would need to identify the type of change, any areas that would be impacted as a result of the change and give a timeframe for the works required, to show if there would be any impact to the completion date.

# Workbook Checklist

When you have completed this workbook, please ensure you have completed all parts of it: Written Questions Case Study IMPORTANT REMINDER Students must achieve a satisfactory result to ALL assessment tasks to be awarded COMPETENT for the unit relevant to this subject. To award the student competent in the units relevant to this subject, the student must successfully complete all the requirements listed above according to the prescribed benchmarks.

End of Document