## Safety Risk Assessment
No: # | APPLICATION | PROCESS | POTENTIAL HEALTH AND SAFETY HAZARDS (Where we could go wrong) | Initial Risk Rating |  |  | CONTROL MEASURES | Residual Risk Rating |  |  | HIRACHY OF CONTROL | RESPONSIBILITY | STATUS
|  |  | 1- 6 Acceptable 7 - 12 Acceptable with strict adherence to Control Measures 13 - 25 UNACCEPTABLE | P X | C = | T | 1- 6 Acceptable 7 - 12 Acceptable with strict adherence to Control Measures 13 - 25 UNACCEPTABLE | P X | C = | T
1 | SAFETY | Safety in Design (SiD) | Hazards or health related hazards not transferring to construction project risk assessment | 2 | 5 | 10 | Design and construction: SID workshop reviewing Buildability and safety in design to be completed. | 1 | 5 | 5 | ADMIN | Laing O'Rourke Des Eng. | Open
|  |  |  | 2 | 5 | 10 | Construction team to review SID register, action or RFI client for clarification | 1 | 5 | 5 | ADMIN | Laing O'Rourke Des Eng | Open
|  |  | Project delivery team unaware of design risks. | 2 | 5 | 10 | SID actions to be transferred to Project Risk Register and to be managed during construction through consultation with delivery team. | 1 | 5 | 5 | ADMIN | Laing O'Rourke Des Eng | Open
|  |  | Failure to communicate to supply chain | 2 | 5 | 10 | Sub contractors to advise of Buildability and SID actions in Sub contractor meetings. | 1 | 5 | 5 | ADMIN | Laing O'Rourke Des Eng | Open
|  |  | Changes in Design: • Design error or rectification (RFIs, TQs) • Unforeseen circumstances (latent conditions) • Revised construction methods • Material substitution (unavailability, or value management) • Subcontractor re-design • Construction detailing • Construction errors (non-conformances) | 3 | 5 | 15 | Design changes must be assessed for impacts on safety risks for all subsequent stages of the project lifecycle: construction, operation, maintenance and demolition. The level of assessment may be risk-based, and must be referred to the designer for assessment via RFI, TQ, NCR or other form of formal correspondence. For major changes, the assessment may entail consultation with other project stakeholders including the Client, maintainers, operators and Subcontractors. The assessment is to be concluded by formal response (e.g. RFI, TQ, NCR or other correspondence) from the designer. Where the assessment identifies a material impact to the original assessment, the SiD Register is to be updated. Where design changes alter construction methodologies, construction-phase documentation, including Project Risk Assessment and SWMS are to be reviewed in consultation with workers. Any changes to risk profiles are to be reviewed in accordance with the hierarchy of controls, consulted with workers and recorded. | 1 | 5 | 5 | ADMIN / ENG | Laing O'Rourke Eng | Open
2 | SAFETY | Site Security | Unauthorised entry to site | 2 | 5 | 10 | National Police Checks approval required to gain access to construction site. | 1 | 5 | 5 | ADMIN | Laing O'Rourke | Open
|  |  | Unauthorised entry to site | 2 | 5 | 10 | EIFY (Laing O'Rourke Systems) electronic site access system in place to ensure workforce capture. | 1 | 5 | 5 | ADMIN | Laing O'Rourke | Open
|  |  | Unauthorised entry to site / Personnel entering unauthorised Defence areas | 2 | 5 | 10 | Erect signage at entry points to Precincts stating:- Construction site, no unauthorised access, After hours contact number, Emergency contact numbers to be communicated. | 1 | 5 | 5 | ADMIN | Laing O'Rourke | Open
3 | SAFETY | Management of First Aid (Competency) | No First Aiders On Site | 2 | 5 | 10 | A qualified first aider is to be on site at all times when construction work is being undertaken. Site Supervisor are to be trained in first aid and CPR (First Aider ratio 1:25 for HRCW -Refer to Emergency Management Plan. | 1 | 5 | 5 | ADMIN | Laing O'Rourke/Subcontractors | Open
|  | Management of First Aid (COVID-19) | unnecessary exposure or management of exposure. | 2 | 5 | 10 | Development, implementation and monitoring of Pandemic Management Plan. First Aid Guidance document developed and made available to Supply chain and laminated within all First Aid rooms. | 1 | 5 | 5 | ADMIN | Laing O'Rourke/Subcontractors | Open
|  | Management of First Aid (Provisions) | Lack of Facilities, Equipment and Consumables | 2 | 5 | 10 | First aid facilities and equipment shall comply with all legislative requirements for the size of the work force (First Aider ratio 1:25 and first aid room required for 100+ workers) All Subcontractors shall be required to carry out a formal risk assessment to determine the First Aid Management strategies for their workgroups; this can be documented in their safety management plan. A current First Aid manual is to be kept on site. Phone numbers of the closest Hospital and medical centre posted in prominent location. – Notice board and First Aid shed. All First Aid Boxes on site shall be service regularly to ensure the amount of available consumables is adequate. | 1 | 5 | 5 | ADMIN | Laing O'Rourke/Subcontractors | Open
Note on I1: Dawson, Micheal:

## Risk Matrix
HSEQ RISK CLASSIFICATION MATRIX
Application: | Probability: |  | Consequence:
OHS | 5 = Almost Certain 4 = Probable 3 = Moderate 2 = Unlikely 1 = Rare |  | 5 = Multiple/Singular Fatality 4 = Nonfatal but permanent injury 3 = Injured no return to work (LTI) 2 = Injured return to work restricted duties(MTI) 1 = Injured immediate return to work (FAI)
Environment | 5 = Almost Certain 4 = Probable 3 = Moderate 2 = Unlikely 1 = Rare |  | 5 = Reputation 4 = Future work 3 = Wide Spread 2 = Local 1 = Insignificant
Quality | 5 = Almost Certain 4 = Probable 3 = Moderate 2 = Unlikely 1 = Rare |  | 5 = Failure 4 = Long Term defect 3 = Major cost 2 = Minor 1 = Acceptable
1- 6 Acceptable 7 - 12 Acceptable with strict adherence to Control Measures 13 - 25 UNACCEPTABLE
LIKELIHOOD CLASSIFICATION |  | Likelihood | Consequence
|  |  | 1 - Minor | 2 - Medium | 3 - Serious | 4 - Major | 5 - Catastrophic
|  | A - Almost Certain | Moderate | High | Critical | Critical | Critical | 2
|  | B - Likely | Moderate | High | High | Critical | Critical | 3
|  | C - Possible | Low | Moderate | High | Critical | Critical | 4
|  | D - Unlikely | Low | Low | Moderate | High | Critical | 5
|  | E - Rare | Low | Low | Moderate | High | High | 6
Do not alter. The template calculates the risk score from this sheet
Hierarchy of Control: Highest level of Control
|  | Elimination | Substitution | Engineering | Administration | PPE - Lowest Level of Control
|  | NOTE: | The above ‘Hierarchy of Controls’ must be considered and applied as part of the risk assessment process. Where ELIMINATION cannot be reasonably applied then, SUBSTITUTION, ENGINEERING, ADMINISTRATION and PPE can be considered as preferred controls in descending order.
CONSEQUENCE CATEGORIES AND DESCRIPTORS |  | ECONOMIC OPERATIONAL CATEGORIES