## Sheet1
Costings estimate
Site m² | 52000
Building m² | 5500
Estimate no. | Project name
10659 | BAC Wallenius Wilhelmsen
Date of estimate | Dates of project
| Start date: | 2022-01-19
| End date: | 2023-02-09
Estimate prepared by | Client name
Kandy-Lee Ashby | Brisbane Airport Corporation
Sitework | Total cost | Cost m²
SUPERVISION / LABOUR COSTS | 802844 | 145.9716
AUTHORITY FEES & INSURANCES | 221112.536 | 40.2023
CONSUMABLES & DOCUMENT CONTROL | 11823.6 | 2.1497
HOARDINGS, GANTRIES AND FENCING | 41219.58 | 7.4945
SITE ACCOMODATION | 24500.4 | 4.4546
TEMPORARY SERVICES | 12238.4 | 2.2252
CLEANING AND BINS | 24215 | 4.4027
SURVEYING & TRAFFIC MANAGEMENT | 41252.8 | 7.5005
SITE SECURITY | 495 | 0.09
SMALL TOOLS, EQUIPMENT & PLANT | 5210 | 0.94727
CRANAGE, HOISTS & SCAFFOLD | 3200 | 0.58182
Total site costs | 1188111.316
Building | Total cost | Cost m²
DEMOLITION | 1012 | 0.184
BULK EXCAVATION | 5883438.2571 | 1069.716
FOUNDATION PILES | 1214663.935 | 220.848
TERMITE PROTECTION | 2617.4 | 0.47589
CONCRETE & REINFORCEMENT | 2870606.7941 | 521.9285
CONCRETE PUMPING | 36490 | 6.6345
CONCRETE TILT PANEL | 394310 | 71.6927
MASONRY/BLOCKWORK | 93939.6665 | 17.0799
STRUCTURAL STEEL | 1849518.6498 | 336.2761
ROLLER DOORS AND SHUTTERS | 71200 | 12.9455
SCREENS AND AWNINGS | 82200 | 14.9455
FENCES & GATES | 202636 | 36.8429
TACTILES | 6944.4 | 1.2626
BICYCLE RACKS | 700 | 0.12727
LETTER BOXES | 350 | 0.063636
LOCKERS | 13000 | 2.3636
WHEELSTOPS | 3450 | 0.62727
BOLLARDS | 75350.1723 | 13.7
DOWNPIPE GUARDS | 11475 | 2.0864
CONVEX SAFETY MIRRORS | 900 | 0.16364
GUARD RAIL | 25575 | 4.65
SIGNAGE | 6700 | 1.2182
ALUMINIUM FRAMED WINDOWS AND DOORS | 63276.1 | 11.5047
WINDOW FURNISHINGS | 11875 | 2.1591
SHOWER SCREENS, MIRRORS AND ROBE DOORS | 930 | 0.16909
DOORS & FRAME SUPPLY & FIX | 41865 | 7.6118
SUNDRY HARDWARE FIX | 6583.37 | 1.197
JOINERY SUPPLY & FIX | 14843.6 | 2.6988
ROOFING | 1256298.97 | 228.418
ROOF SAFETY SYSTEM | 22519.41 | 4.0944
BIRD PROOFING | 11762.955 | 2.1387
SANITARY FIXTURES SUPPLY | 31950 | 5.8091
CEILINGS & PARTITIONS | 142206.8 | 25.8558
EXTERNAL CLADDING | 120747.6997 | 21.9541
TOILET PARTITIONS | 7600 | 1.3818
TILE SUPPLY & FIX | 51657.6782 | 9.3923
VINYL FLOOR FINISHES | 8036.8 | 1.4612
CARPET FLOOR FINISHES | 20552.7028 | 3.7369
ENTRY MATS | 2044.557 | 0.37174
EPOXY FLOORING | 27500 | 5
LINEMARKING | 1843.62 | 0.3352
HYDRAULIC SERVICES | 515100 | 93.6545
ELECTRICAL SERVICES | 787800 | 143.2364
MECHANICAL SERVICES | 202000 | 36.7273
FIRE SERVICES | 572771 | 104.1402
RETAINING WALLS | 601500 | 109.3636
GANTRY CRANE | 160000 | 29.0909
SPRAY BOOTHES | 240580 | 43.7418
KERBING | 96507.4932 | 17.5468
STORMWATER DRAINAGE | 482582.3639 | 87.7422
STORMWATER TREATMENT | 111780 | 20.3236
FINAL CLEAN | 12250 | 2.2273
PROVISIONAL SUMS | 100000 | 18.1818
Total building costs | 18574042.3945