MINUTES OF MEETING No. 2

| MEETING SUBJECT | New England Highway |
| --- | --- |
| DATE AND TIME | Monday 13th December |
| ATTENDEES | Ryan Buckley (RB), Dean Ellis (DE), Chantelle Neiland (CN), Emily Conlon (EC), Louise Brekich (LB), Morgan Hamilton (MH), Greg Hopkins (GH), Dan Bowdler (DB), Stef Pohl (SP), Brett Jenkins (BJ) |
| LOCATION | Helensvale Training Room |

| Item | Subject/Notes | Action By | Date Raised | Action Date |
| --- | --- | --- | --- | --- |
|  | Project Introduction |  |  |  |
|  | New England Highway Stanthorpe-Wallangarra Package 4 & 5 - High Risk Roads Safety Works (Stanthorpe-Wallangarra) - Two Project Packages; Package 4 and Package 5 - Contract Value $5,845,287.80 excl GST - Located between Glan Aplin, QLD - Scope; Road widening for center line treatment, drainage culverts, pavements, seals, and road furniture - Project No. J870-1 - Mobilise to Site 10th January 2022 | Note |  |  |
|  | Work Health and Safety |  |  |  |
|  | Work Health Safety Management Plan – submitted | DE | 06/12 | 10/12 |
|  | Emergency Response Plan – done, doesn’t need to be submitted | DE | 06/12 | 10/12 |
|  | Sever Wet Weather Plan – submitted | RB | 06/12 | 10/12 |
|  | COVID-19 Plan – done doesn’t need to be submitted | RB | 06/12 | 10/12 |
|  | Project Risk Assessment is done. DB to send to RB | DB | 06/12 | 10/12 |
|  | Site Induction. RB reviewed. MH & LB to review | DB | 06/12 | 10/12 |
|  | SWMS. DB to put in folder | DB | 06/12 | 10/12 |
|  | DBYD by RK | RK | 13/12 | 20/12 |
|  | Safety in Design Report. Do we have one. RB to check Contract docs or with TMR | RB | 13/12 | 20/12 |
|  | Dust register and monitoring. DB to provide additional info to RB | DB | 13/12 | 20/12 |
|  | CoR Mgmt Plan. DB to develop and submit to RB for approval | DB | 13/12 | 20/12 |
|  | Fatigue Management Plan. DB to develop and submit to RB for approval | DB | 13/12 | 20/12 |
|  | Project Management, Program and Controls |  |  |  |
|  | Create new Project Folders in SharePoint. RB to send invites once set up. – done | BT | 06/12 | 13/12 |
|  | Project Management Plan - done | RB | 06/12 | 13/12 |
|  | Program – done sent to TMR | RB | 06/12 | 13/12 |
|  | WorkPacks. BJ to start writing WorkPacks for submission to TMR - Earthworks plan – 7 days prior to starting works - Soil plan | BJ | 06/12 | 10/01 |
|  | Dilapidation assessment – to be complete on possession of site MH to check Spec 51 to see what the requirements is for buildings | MH | 13/12 | 10/01 |
|  | Phase Code selections for Budget updating - BJ is selecting Phase Codes - RB is completing the SEE Report upload template | BJ | 06/12 | 10/01 |
|  | IT requirements and set up – BT and CB discussed IT container. Might not need one as working from SharePoint and 4G modem. BJ to return all Three Chain equipment to Helensvale and work with IT to understand requirements | BJ | 13/12 | 10/01 |
|  | Project Form. EC to send to RB. RB to complete and return to set up in VP | EC/RB | 06/12 | 10/12 |
|  | TMR pre commencement workshop to be organised. Organised for Thursday 16/12 | RB | 13/12 | 16/12 |
|  | Site Facilities – Location plan and understand the requirements from TMR | RB | 13/12 | 16/12 |
|  | Quality |  |  |  |
|  | Project Quality Plan – submitted | RB/SP | 06/12 | 10/12 |
|  | Submission of ITPs. BJ reviewing ITPs from folder against specs. To be subited to TMR for approva | BJ/SP | 06/12 | 10/01 |
|  | Survey requirements. RB and CB to discuss what survey will be on project. Currently 1 surveyor – Mick Griffin | Note |  |  |
|  | QAntrol Pay Items and submission items. Discuss with TMR on Thursday | RB | 06/12 | 16/12 |
|  | Environmental |  |  |  |
|  | Submission of Construction Environmental Management Plan – Not yet submitted to be submitted tonight Water quality plan – base line monitoring when on site | MH | 06/12 | 13/12 |
|  | Submission of Erosion and Sediment Control Plans. SEEC provided a quote, which is over budget, MH to discuss or work out how to do it cheaper BJ to check for submission requirements of Soil Plan – submit with CEMP | MH/BK | 06/12 | 10/12 |
|  | Preclearing survey and ecologist onboarding. MH to check requirements for nest boxes to be installed before or after clearing. GH to call ecologists and check lead time Discuss nest boxes at TMR meeting. Check Spec 51 | MH/GH | 06/12 | 10/01 |
|  | Site Facility location and approvals. RB to check site locations in contract and send to MH to see if there need to be approved. Discuss with TMR at meeting | RB/MH | 06/12 | 16/12 |
|  | Water extraction points. GH to start discussions with land owners for water extraction points. Check budget allowance too | GH | 13/12 | 10/01 |
|  | Traffic Management |  |  |  |
|  | Traffic Management Plan – submitted BJ to complete the Subcontract Agreement for TMP and start getting TGS developed for submission to TMR | BJ | 06/12 | 10/12 |
|  | Submission of TGSs and timing for Program. BJ to check submission requirements – 2 weeks prior to starting | Note |  |  |
|  | Dates for VMS to be set up. BJ to discuss with LB for dates that VMS boards are to be installed. Get quotes and onboard To be set up 2 weeks prior to works starting | BJ | 06/12 | 10/01 |
|  | Staging Plans. BJ to start these |  |  |  |
|  | Community |  |  |  |
|  | Community Plan – submitted today | Note |  |  |
|  | LB to catch up with RB to discuss community requirements and timing for start date, door knocking and other comms matters. Complete after meeting with TMR | LB | 06/12 | 20/12 |
|  | Waiting for TMR letter box drop templates. Discuss with TMR at meeting | Note |  |  |
|  | Human Resources |  |  |  |
|  | Roster is 5 and 2, Monday to Friday | Note |  |  |
|  | Staff and wages requirements. DL spoke with Mark T. Only Vardy Meeting with Dave to close out accommodation | DL | 06/12 | 20/12 |
|  | Uplift for staff and wages agreements. RB to discuss with DL | RB/DL | 06/12 | 20/12 |
|  | Accommodation details. CN is reviewing, need DL to discuss with Mark | CN/DL | 06/12 | 20/12 |
|  | Training Plan requirements. Submitted | Note |  |  |
|  | Commercial and Procurement |  |  |  |
|  | Contract executed with Daena to get Steve to sign | RB | 13/12 | 20/12 |
|  | Bonds / LSL – draft Bonds have been submitted to TMR waiting acceptance | Note |  |  |
|  | Insurances – sent to TMR and saved in folder | Note |  |  |
|  | Subcontractor Onboarding Management Plan. RB to finalise and send around for use | RB | 06/12 | 20/12 |
|  | Procurement Register developed. RB to save register in folder Leanne starting next week to help with procurement | RB | 13/12 | 10/01 |
|  | Plant and Labour requirements. GH to review DJC and develop Labour and Plant Resourcing. RB to send excel sheet | RB/GH | 13/12 | 10/01 |
|  | Subcontract Agreements – in folders and can be used | Note |  |  |
|  | Quarry certificates – SC to get certificates as TMR approved. BJ to submit to TMR once received | SC | 13/12 | 10/01 |
|  | Other Business |  |  |  |