## COVER, SUPPLIER, MASTER CODES
DEFECTS SCHEDULE
Project Name: |  | HSC Townsville |  | THIS WILL APPEAR AS HEADER INFORMATION ON EACH PAGE
Project Number: |  | B20-0017 |  | THIS WILL APPEAR AS HEADER INFORMATION ON EACH PAGE
Project Address: |  | Tenancy 1-4, 101 Sturt Street, Townsville, QLD, AUS, 4810.
Issue Number: |  | A - FOR ACTION |  | REVISION NUMBER AND ISSUE TYPE TO BE CONSECUTIVELY A-Z THROUGH ALL STAGES
Date: |  | 03/11/2020
DOCUMENT TRANSMITTAL |  |  | GENERAL NOTES
DATE | REVISION | ISSUE TYPE | PLEASE ACKNOWLEDGE
03/11/2020 | A | FOR ACTION | 1. RECTIFICATION OF DEFECTS TO BE CORRECTED AS SOON AS POSSIBLE.
DEFECTS ACTION REGISTER
CONTACT DETAILS
PERSONS ADDRESSED TO ACTION |  | CLIENT Qbuild NQ Kylie Pomerenke, Kedar Chapagain
BUILDER Paynters Construction Matthew Shea, Andrew Law, Michael Carter
SUPPLIER Innerspace QLD Rachel Hatch, Simon Baillie, Mel Papastergou
DESIGNER Incorp Advisory Ellie Ross
-

## DEFECTS SCHEDULE
DEFECTS SCHEDULE |  |  | B20-0017 | HSC Townsville |  |  | UPDATE JOB NUMBER/PROJECT NAME ON COVER PAGE
AMENDMENTS HIGHLIGHTED | [6 empty] | TYPE: | DEFECT | INCOMPLETE WORKS | ADDITIONAL WORKS
ITEM NO. | TYPE/IMAGE | DESCRIPTION | REPORTED | ACTION BY | COMMENT/COMPLETED | CLOSED
GENERAL ITEMS
1.1 | DEFECT | Item: General Clean to Fitout Description: Final clean to be completed to all walls, ceiling, flooring, glazing (including framing), doors (including framing), joinery, and furniture. | 2020-10-30 | BUILDER
1.2 | DEFECT | Item: Doors Description: Some of the door are not closing properly after entering/exiting. Please ensure that the tension on the closers is appropriately adjusted. All viewing panels need to be cleaned. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.3 | INCOMPLETE WORKS | Item: Doors Description: Viewing panels in doors need to be cleaned. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.4 | INCOMPLETE WORKS | Item: Signage Description: Signage and Graphics to finish being installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.5 | INCOMPLETE WORKS | Item: AV Description: Works and electrical connection to be completed. | 2020-10-30 | BUILDER/CLIENT | Complete 4/11/20 | 2020-11-04
1.6 | INCOMPLETE WORKS | Item: Wall Finishes Description: Final whiteboards and acoustic panels to be installed across fitout. Film to be removed from whiteboard once construction works are complete. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.7 | INCOMPLETE WORKS | Item: Joinery Description: Final joinery items to be installed. | 2020-10-30 | BUILDER | Planter box Thurs 12/11/20
1.8 | DEFECT | Item: Joinery Description: Joinery handles are missing from joinery cupboards. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.9 | INCOMPLETE WORKS | Item: Furniture Description: Furniture placement is to be finalised once construction works are complete. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.10 | INCOMPLETE WORKS | Item: Blinds Description: Blinds around perimeter of building to be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.11 | INCOMPLETE WORKS | Item: Ceiling Description: Ceiling tiles to be placed in grid throughout tenancy once construction works are complete. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
1.12 | ADDITIONAL WORKS | Item: Ceiling Description: Contractor to confirm that ceiling baffles have been laid in ceiling for acoustic value over P2 walls. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.01 ENTRY/EXIT
2.1 | INCOMPLETE WORKS | Item: Joinery Description: Joinery J01 still to be installed. Associated AV connection, signage, and plants to be installed with this. | 2020-10-30 | BUILDER/CLIENT | Plants outstanding Thurs 12/11/20
2.2 | DEFECT | Item: Front Entry Door Description: Brush seal appears to be missing from doors leaving airgap in side of door. Client could request that the building owner instates this item. | 2020-10-30 | CLIENT | B&N Glass to complete this week
2.3 | INCOMPLETE WORKS | Item: Signage Description: Entry signage on glazing to be complete. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.02 CONCIERGE
3.3 | INCOMPLETE WORKS | Item: Joinery Description: Missing items from joinery J06 to to be installed. This includes perspex, graphic film, monitor arms, cable trays, and signage. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.03 CONCIERGE STORE
4.1 | INCOMPLETE WORKS | Item: Joinery Description: Missing items from joinery J05 to be installed. This includes perspex, graphic film, monitor arms, cable trays, signage, cable hole for power reticulation. Power and data to unit also looks to still be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
4.2 | INCOMPLETE WORKS | Item: AV Description: CCTV and MATV monitors above unit to be installed from ceiling mount. | 2020-10-30 | BUILDER/CLIENT | Complete 9/11/20 | 2020-11-04
GF.06 INFORMATION/BULLETIN BOARD
5.1 | INCOMPLETE WORKS | Item: Joinery Description: Missing items from joinery J02 to be installed. This includes whiteboard, acoustic panel, and signage. Power and data to unit also looks to still be installed. | 2020-10-30 | BUILDER | Incomplete 4/11/20
5.2 | DEFECT | Item: Wall Description: Damage to the wall from installation of joinery to be repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
5.3 | INCOMPLETE WORKS | Item: Electrical Wheelchair Charge Description: Power to be installed on wall as pre electrical drawings. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
5.4 | DEFECT | Item: Ceiling Description: Damage to the ceiling bulkhead from installation of joinery to be repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 9/11/20 (Remove spider webs) | 2020-11-09
GF.11 UTILITY
6.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
6.2 | DEFECT | Item: Joinery Description: Overhead cupboard panel is missing. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
6.3 | INCOMPLETE WORKS | Item: Lighting Description: LED light to be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
6.4 | INCOMPLETE WORKS | Item: Joinery Description: Locks be installed to below bench cupboards in front of house. | 2020-10-30 | BUILDER | Moduline to complete Thurs 12/11/20
GF.12 SERVICE COUNTERS (ALL GENERAL)
7.1 | INCOMPLETE WORKS | Item: Joinery Description: Missing items from joinery J03, J04, and J08 to be installed. This includes perspex, graphic film, monitor arms, cable trays, signage, cable hole for power reticulation. Power and data to unit also looks to still be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
7.2 | INCOMPLETE WORKS | Item: Flooring Description: Carpet to perimeter of room near J08 needs to be installed. | 2020-10-30 | BUILDER | Complete 12/11/20 | ?
GF.07/GF.13 WAITING
8.1 | INCOMPLETE WORKS | Item: Lighting Description: Pendant lights to be installed over waiting area couches. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.16 INTERVIEW ROOM
9.1 | DEFECT | Item: Furniture Description: Furniture to be repositioned against indicated wall. Monitor arms to be moved down workstation to assist with chair access for C5. | 2020-10-30 | BUILDER/SUPPLIER | Complete 4/11/20 | 2020-11-04
9.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.17 UTILITY
10.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on wall to be cleaned/repaired/patched/painted as required. In particular there is marks under overhead cupboards and white paint marks on opposite wall at ceiling level. | 2020-10-30 | BUILDER | To be cleaned - NOT COMPLETE
10.2 | DEFECT | Item: Graphics Description: 'Staff Only' sign installed on the wrong side of door. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
10.3 | INCOMPLETE WORKS | Item: Lighting Description: LED light to be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
10.4 | INCOMPLETE WORKS | Item: Joinery Description: Locks be installed to below bench cupboards in front of house. | 2020-10-30 | BUILDER | Thursday 12/11/20
GF.18 INTERVIEW ROOM
11.1 | DEFECT | Item: Furniture Description: Furniture to be repositioned against indicated wall. Monitor arms to be moved down workstation to assist with chair access for C5. | 2020-10-30 | BUILDER/SUPPLIER | Complete 4/11/20 | 2020-11-04
11.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.19 INTERVIEW ROOM
12.1 | DEFECT | Item: Furniture Description: Furniture to be repositioned against indicated wall. Monitor arms to be moved down workstation to assist with chair access for C5. | 2020-10-30 | BUILDER/SUPPLIER | Complete 4/11/20 | 2020-11-04
12.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
12.3 | DEFECT | Item: Ceiling Description: Ceiling tile damaged in ceiling to be resolved. | 2020-10-30 | BUILDER | INCOMPLETE
GF.20 INTERVIEW ROOM
13.1 | DEFECT | Item: Furniture Description: Furniture to be repositioned against indicated wall. Monitor arms to be moved down workstation to assist with chair access for C5. | 2020-10-30 | BUILDER/SUPPLIER | Complete 4/11/20 | 2020-11-04
13.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | INCOMPLETE PIN BOARD GAP
13.3 | DEFECT | Item: Ceiling Description: Ceiling tile damaged in ceiling to be resolved. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
GF.21 OFFICE
14.1 | DEFECT | Item: Furniture Description: Furniture to be repositioned against indicated wall. Monitor arms to be moved down workstation to assist with chair access for C5. | 2020-10-30 | BUILDER/SUPPLIER | Complete 4/11/20 | 2020-11-04
14.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
14.3 | DEFECT | Item: Walls Description: GPO/Data is not at indicated height at joinery. | 2020-10-30 | BUILDER | Joinery height changed after rough-in
14.4 | DEFECT | Item: Ceiling Description: Ceiling tile damaged in ceiling to be resolved. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
GF.22 CHARGE/STORE AND GENERAL CORRIDOR
15.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on corridor walls to be cleaned/repaired/ patched/painted as required. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
15.2 | INCOMPLETE WORKS | Item: Flooring Description: Expansion join to be cleaned and polished. | 2020-10-30 | BUILDER | INCOMPLETE
GF.23/GF.24 MEETING
16.1 | INCOMPLETE WORKS | Item: Operable Wall Description: Installation to be finalised. Doors to go onto cupboard. | 2020-10-30 | BUILDER | Complete | 2020-11-09
16.2 | ADDITIONAL WORKS | Item: Doors Description: Door stop to replaced with restricted door opener/closer as per recent discussions/discussions on site. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
16.3 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. In particular there is holes next to acoustic panels. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
16.4 | INCOMPLETE WORKS | Item: Flooring Description: Expansion join to be cleaned and polished. | 2020-10-30 | BUILDER | INCOMPLETE
GF.25 COMMS
17.1 | INCOMPLETE WORKS | Item: Door Description: Vent in door to be installed. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
17.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. In particular there is holes next to acoustic panels. | 2020-10-30 | BUILDER | INCOMPLETE
GF.27/GF.28 QUIET ROOM
18.1 | INCOMPLETE WORKS | Item: Lighting Description: Wall light to be installed on acoustic panel. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
18.2 | INCOMPLETE WORKS | Item: Flooring Description: Expansion join to be cleaned and polished. | 2020-10-30 | BUILDER | INCOMPLETE 9/11/20
GF.29 UTILITY/LOCKERS
19.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. In particular there is holes next to acoustic panels. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
19.2 | INCOMPLETE WORKS | Item: Lighting Description: LED light to be installed. | 2020-10-30 |  | Complete 4/11/20 | 2020-11-04
GF.30 OFFICE
20.1 | DEFECT | Item: Furniture Description: Monitor arms to be moved down workstation to assist with chair access for C5. | 2020-10-30 | BUILDER/SUPPLIER | Complete 4/11/20 | 2020-11-04
20.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.31 WORKSTATION AREA
21.1 | ADDITIONAL WORKS | Item: Furniture Description: Due to leveling of floor storage may benefit from being fixed to wall or adjusted to align so there is better balance. | 2020-10-30 | BUILDER/SUPPLIER | NOT PAYNTERS
GF.32 WAITING/BACK OF HOUSE ENTRY
22.1 | DEFECT | Item: Ceiling Description: Ceiling tile damaged in ceiling to be resolved. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
GF.34 KITCHENETTE
23.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
23.2 | INCOMPLETE WORKS | Item: Fittings/Fixtures Description: Plumbing and whitegoods to be delivered and installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
23.3 | DEFECT | Item: Joinery Description: J14 Bulkheads has sticky residue to be cleaned. The bulkhead edging appears to be chipped/jags to the edge. Could this be adjusted for neater finish e.g. silicon? | 2020-10-30 | BUILDER | INCOMPLETE
23.4 | INCOMPLETE WORKS | Item: Lighting Description: LED light to be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.35 INNOVATION AND COMMUNITY RESILIENCE HUB
24.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
24.2 | INCOMPLETE WORKS | Item: Flooring Description: Carpet to perimeter of room near GF.34 wall needs to be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
24.2 | DEFECT | Item: Joinery Description: J15 gables to end of joinery units appear to be missing/not to floor. | 2020-10-30 | BUILDER | ? Unsure
24.3 | DEFECT | Item: Walls Description: Finish to perimeter glazing junction between GF.35 and GF.32 needs to be finished neater at floor level. | 2020-10-30 | BUILDER | To add skirting
GF.36 COLLABORATION/BREAKOUT
25.1 | DEFECT | Item: Ceiling Description: Ceiling tile damaged in ceiling to be resolved. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
25.2 | INCOMPLETE WORKS | Item: Lighting Description: Acoustic pendants to be installed over furniture. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
25.3 | DEFECT | Item: Door Description: Sliding door and its door stop to be completed. There is also damage to the bottom of the sliding door to be repaired/patched/painted. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
25.4 | INCOMPLETE WORKS | Item: Flooring Description: Expansion join to be cleaned and polished. | 2020-10-30 | BUILDER | INCOMPLETE
GF.38 KITCHEN BREAKOUT
26.1 | INCOMPLETE WORKS | Item: Fittings/Fixtures Description: Plumbing and whitegoods to be delivered and installed. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
26.2 | DEFECT | Item: Joinery Description: J17 screw holes to be capped where cupboards adjoin to the overhead bulkhead. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
26.3 | INCOMPLETE WORKS | Item: Joinery Description: Shelves above fridge to be installed in the cupboard. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
26.4 | DEFECT | Item: Joinery Description: Timber feature wall above J18 is not sitting flush and aligned at the joins. | 2020-10-30 | BUILDER | INCOMPLETE
26.5 | DEFECT | Item: Walls Description: Acoustic panels appear to be frayed due to blunt cut. Edges to be tidied with clean blade or tucked in for neater finish. | 2020-10-30 | BUILDER | INCOMPLETE
26.6 | DEFECT | Item: Door Description: Damage to the bottom of the door to be repaired/patched/painted, or replaced is split in door is not fixable. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
26.7 | INCOMPLETE WORKS | Item: Flooring Description: Expansion join to be cleaned and polished. | 2020-10-30 | BUILDER | INCOMPLETE
GF.39 UTILITY
27.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.40 WORKSTATION AREA
28.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
28.2 | DEFECT | Item: Flooring Description: Carpet to perimeter of room near GF.37 wall needs to be glued down as it is lifting. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
28.2 | INCOMPLETE WORKS | Item: Lighting Description: Acoustic pendants to be installed over furniture. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.43 UTILITY
29.1 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.44 LOCKERS
30.1 | DEFECT | Item: Furniture Description: Appears to be a dent to front of locker. Not sure when this occurred e.g. pre/post delivery. | 2020-10-30 | BUILDER/SUPPLIER/CLIENT | NOT PAYNTERS
30.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.45 LOCKERS AND GENERAL CORRIDOR
31.1 | DEFECT | Item: Column Description: Damage/marks/dirt on column to be cleaned/repaired/patched/ painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
31.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
31.3 | DEFECT | Item: Corridor Walls Description: Damage to corridor walls to be patched and painted. Door and glazing frames to adjacent FOH meeting room to be cleaned including any masking tape or pencil marks at ceiling level. Paint on door seals to be removed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.47 UTILITIES/STORE
32.1 | DEFECT | Item: Joinery Description: Gables to side of J24 joinery not floor. | 2020-10-30 | BUILDER | CAN'T ?
32.2 | INCOMPLETE WORKS | Item: Joinery Description: Joinery shop drawings show a bulkhead over J24 which has not been installed. | 2020-10-30 | BUILDER | NOT ON AREA DRAWING
33.3 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.48 WELLNESS ROOM
33.1 | DEFECT | Item: Joinery Description: J23 vent for bar fridge to be installed in joinery. | 2020-10-30 | BUILDER | WHERE?
33.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
33.3 | DEFECT | Item: Door Description: Paint on door frames to be cleaned. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
GF.49 STORE/CLEANERS ROOM
34.1 | DEFECT | Item: Flooring Description: Scuff marks on floor to be cleaned. | 2020-10-30 | BUILDER | TO BE COMPLETED
34.2 | DEFECT | Item: Flooring Description: Damage to plasterboard on flooring join to be rectified. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
34.3 | INCOMPLETE WORKS | Item: Fittings Description: Sink and taps to be installed. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
34.4 | DEFECT | Item: Door Description: Paint on door frames to be cleaned. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
GF.50 CASUAL MEETING AND COLLAB AREA
35.1 | INCOMPLETE WORKS | Item: Flooring Description: Carpet to be cleaned. Lots of construction residue. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
35.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
35.3 | DEFECT | Item: Door Description: Appears to be large gouge in timber door. Can this be filled and painted? | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
35.4 | DEFECT | Item: Collaborative Area Adjacent Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.51 MEETING
36.1 | INCOMPLETE WORKS | Item: Joinery Description: J13 surface to be cleaned. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
36.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.52 MEETING
37.1 | INCOMPLETE WORKS | Item: Joinery Description: J13 surface to be cleaned. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
37.2 | DEFECT | Item: Ceiling Description: Marks on ceiling tile to be cleaned. | 2020-10-30 | BUILDER | INCOMPLETE
37.3 | DEFECT | Item: Door Description: Appears to be large gouge in timber door. Can this be filled and painted? | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
37.4 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
GF.53 MEETING
38.1 | INCOMPLETE WORKS | Item: Joinery Description: J13 surface to be cleaned. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
38.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
38.3 | DEFECT | Item: Ceiling Description: Marks on ceiling tile to be cleaned. | 2020-10-30 | BUILDER | INCOMPLETE
GF.54 MEETING
39.1 | INCOMPLETE WORKS | Item: Joinery Description: J13 surface to be cleaned. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
39.2 | DEFECT | Item: Walls Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 4/11/20 | 2020-11-04
39.3 | DEFECT | Item: Ceiling Description: Marks on ceiling tile to be cleaned. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
39.4 | DEFECT | Item: Door Description: Appears to be large gouge in timber door. Can this be filled and painted? | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09
39.5 | DEFECT | Item: Corridor between Meeting GF.54 and GF.21 Description: Damage/marks/dirt on walls to be cleaned/repaired/patched/painted as required. | 2020-10-30 | BUILDER | Complete 9/11/20 | 2020-11-09