## FF&E
V 1.0
[10 empty] | PROJECT NUMBER/NAME: | 48402 - CURRIMUNDI HOTEL ACCOMODATION REFURBISHMENT |  |  |  |  | DOCUMENT VERSION: | V 1.0 | [17 empty] | QUOTE STATUS KEY | PAYMENT STATUS KEY | DISPATCH STATUS KEY
[10 empty] | SITE ADDRESS: | 32 BUDERIM STREET, CURRIMUNDI QLD 4551 |  |  |  |  | LAST MODIFIED: | 24.04.24 | [9 empty] | PPAR | [7 empty] | UNSENT | NOT RECEIVED | NOT ORDERED
|  |  |  | PROJECT FF&E PROCUREMENT SPREADSHEET | [5 empty] | CLIENT: | AVC / QVC | [15 empty] | CCPF | [7 empty] | AWAITING RESPONSE | RECEIVED | ORDERED
[10 empty] | SITE CONTACT: | [24 empty] | NO RESPONSE | IN PROGRESS | ON-HOLD
[10 empty] | PROJECT COMMENCEMENT: | [24 empty] | REJECTED TO QUOTE | PARTIALLY PAID | IN TRANSIT
[10 empty] | PROJECT COMPLETION: | [24 empty] | RECEIVED | PAID ON ACCOUNT | AWAITING COLLECTION
[10 empty] | STAGED WORKS: | [24 empty] | ACCEPTED | PAID | DELIVERED
[35 empty] | [CLEAR] | [CLEAR] | [CLEAR]
| SUMMARY |  |  | CATEGORY / NOTES | ITEM / DESCRIPTION |  | IMAGE | QTY / | UOM | SUPPLIER DETAILS |  | QUOTE | [7 empty] | PURCHASE | [5 empty] | INVOICE | [7 empty] | NOTES
| QUOTE STATUS | PAYMENT STATUS | DISPATCH STATUS | [8 empty] | QUOTE DETAILS |  |  |  | ESTIMATED COSTINGS |  |  |  | BUDGET ALLOCATION |  | PURCHASE DETAILS |  | DISPATCH DETAILS |  | INVOICE DETAILS |  |  |  | ACTUAL COSTINGS
HOW TO USE THIS TEMPLATE (COPY THE BELOW ROWS WHEN CREATING NEW LINES)
CATEGORY
| UNSENT | NOT RECEIVED | NOT ORDERED |  | NAME: |  |  |  |  | NAME: |  | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
ELECTRICAL FIXTURES & FITTINGS
LIGHTING
| UNSENT | NOT RECEIVED | NOT ORDERED | WL.1: Wall Light, Bedroom / Headboard Lights. | NAME: | Minimalist Sphere Wall Light, Medium, 120mm |  | 53 | PIECE | NAME: | Lighting Collective: Luxury Lighting | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 134.1 | GST | 710.73 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | *Pricing obtained online (suppliers website) 24.04.24, pricing excludes trade discount (confirmed with offical quotation).
[5 empty] | ID/SKU: |  |  |  |  | PHONE: | (02) 6685 5744 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 7107.3 | TOTAL COST (incl GST) | 7818.03 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://lightingcollective.com.au/products/minimalist-sphere-wall-light?variant=39260564521073 |  |  |  | EMAIL: | info@lightingcollective.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 7818.03
| ACCEPTED | PAID | DELIVERED | WL.1: Wall Light, Bedroom / Headboard Lights. | NAME: | Minimalist Sphere Wall Light, Medium, 120mm |  | 53 | PIECE | NAME: | The Lighting Outlet | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 118.99 | GST | 630.647 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: | 7 days | RECEIVED: | 09.07.24 | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | Additional light needed for family room
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 6306.47 | TOTAL COST (incl GST) | 6937.117 | EST. UNIT: |  | PO #: | 2210 | EXPECTED: | 16.07.24 | FORM: |  | INV #: | 8200134 | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://thelightingoutlet.com.au/products/orb-flush-mirror-wall-light-medium-in-white-chrome-or-dark-bronze |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 6937.117
| UNSENT | NOT RECEIVED | NOT ORDERED | WL.1: Wall Light, Bedroom / Headboard Lights. | NAME: | Minimalist Sphere Wall Light, Medium, 120mm |  | 53 | PIECE | NAME: | Zest Lighting | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 127.5 | GST | 675.75 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | *Pricing obtained online (suppliers website) 24.04.24, pricing excludes trade discount (confirmed with offical quotation).
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 6757.5 | TOTAL COST (incl GST) | 7433.25 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://www.zestlighting.com.au/orb-white-round-glass-mirror-wall-lamp/?srsltid=AfmBOorx1VyuwnSedsCYuR_6AKcIDxqBbzpNyzrDmKRra5syqk8WjLoEg4U |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 7433.25
PLUMBING FIXTURES & FITTINGS
SHOWER FIXTURES AND FITTINGS
| UNSENT | NOT RECEIVED | NOT ORDERED | *SHOWER SCREEN* | NAME: |  |  | 1 | PIECE | NAME: | Bunnings Warehouse | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  |  | PHONE: | (07) 3516 8999 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: | BuilderServiceQld@bunnings.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
FLOOR, WALL AND CEILING FINISHES
TILES
| ACCEPTED | NOT RECEIVED | ORDERED | FT.1: Floor Tile, Bedroom / Living Room. | NAME: | Godfrey Hirst Oceanic Planks - Eskine 250 x 1000mm |  | 555 | M2 | NAME: | Future Floors QLD, Lewis Bowley | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 42 | GST | 2381 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: | 940 |  |  |  | PHONE: | 07 3335 1333 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 23310 | TOTAL COST (incl GST) | 26191 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://www.ghcommercial.com/products/oceanic-planks?colour=erskine |  |  |  | EMAIL: | lewis@futurefloorsqld.com | VALID UNTIL: |  |  |  | DELIVERY (ex GST) | 500 |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 26191
| AWAITING RESPONSE | NOT RECEIVED | NOT ORDERED | FT.1: Floor Tile, Bedroom / Living Room. | NAME: | Godfrey Hirst Oceanic Planks - Eskine 250 x 1000mm |  | 525 | M2 | NAME: | Aflor Commercial | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: | 940 |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://www.ghcommercial.com/products/oceanic-planks?colour=erskine |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
| RECEIVED | NOT RECEIVED | NOT ORDERED | FT.1: Floor Tile, Bedroom / Living Room. | NAME: | Godfrey Hirst Oceanic Planks - Eskine 250 x 1000mm |  | 525 | M2 | NAME: | Right Floors | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: | 940 |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://www.ghcommercial.com/products/oceanic-planks?colour=erskine |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
| AWAITING RESPONSE | NOT RECEIVED | NOT ORDERED | FT.1: Floor Tile, Bedroom / Living Room. | NAME: | Godfrey Hirst Oceanic Planks - Eskine 250 x 1000mm |  | 525 | M2 | NAME: | Carpet Court | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: | 940 |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://www.ghcommercial.com/products/oceanic-planks?colour=erskine |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
| ACCEPTED | NOT RECEIVED | DELIVERED | WT.1: Wall Tile, Bathroom Splashbacks | NAME: | Resort White Matt Porcelain Mosaic Tile | #VALUE! | 1 | M2 | NAME: | National Tiles, Christian Aquilina | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 382.72 | GST | 47.272 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | Quantity 9.36 m2 (includes wastage)
[5 empty] | ID/SKU: | NT17-1001MT |  |  |  | PHONE: | 0449 808 141 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 382.72 | TOTAL COST (incl GST) | 519.992 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://www.nationaltiles.com.au/resort-white-matt-porcelain-mosaic-tile?gad_source=1&gclid=CjwKCAjwm_SzBhAsEiwAXE2Cvzi_naGf8wR0lzbIZO7BpTJKfrr62U3XZw1SSO9SHRA9QdhlQI_LrRoC2IUQAvD_BwE |  |  |  | EMAIL: | caquilina@nationaltiles.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) | 90 |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 519.992
STEEL WORKS
| RECEIVED | NOT RECEIVED | NOT ORDERED | Steel structural supports for new floating shelves. • 106 x steel tube brackets, 250mm x 210mm (20mm x 20mm). • Predrilled with 5mm clearance holes on front and side. | NAME: |  |  | 106 |  | NAME: | A1 Stainless Streel | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 65.0943 | GST | 690 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  |  | PHONE: | 0438 007 040 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 6899.9999 | TOTAL COST (incl GST) | 7589.9999 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: | info@a1customstainless.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 7589.9999
| ACCEPTED | NOT RECEIVED | ORDERED | Steel structural supports for new floating shelves. • 106 x steel tube brackets, 250mm x 210mm (20mm x 20mm). • Predrilled with 5mm clearance holes on front and side. | NAME: |  |  | 106 |  | NAME: | Andrew, Concept Steel | SENT: | 11.07.24 | VERSION #: |  | UNIT COST (ex GST) |  | GST | 424 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: | 12.07.24 | QUOTE #: |  | SUBTOTAL (ex GST) | 4240 | TOTAL COST (incl GST) | 4664 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 4664
BENCHTOP
| ACCEPTED | NOT RECEIVED | ORDERED | Vanity Bench Tops 612x430 | NAME: | Polytec Smooth Marmo Di Torre |  | 25 |  | NAME: | Multiform | SENT: | 17.07.24 | VERSION #: |  | UNIT COST (ex GST) | 128.5231 | GST | 323.6077 | EST. QTY/UOM: |  | DATE SENT: | 22.07.24 | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: | 17.07.24 | QUOTE #: |  | SUBTOTAL (ex GST) | 3213.0767 | TOTAL COST (incl GST) | 3559.6844 | EST. UNIT: |  | PO #: | 2268 | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) | 23 |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 3559.6844
| ACCEPTED | NOT RECEIVED | ORDERED | Vanity Bench Tops, Family room 1800x430 | NAME: | Polytec Smooth Marmo Di Torre |  | 1 |  | NAME: |  | SENT: | 17.07.24 | VERSION #: |  | UNIT COST (ex GST) | 128.5231 | GST | 15.1523 | EST. QTY/UOM: |  | DATE SENT: | 22.07.24 | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: | 17.07.24 | QUOTE #: |  | SUBTOTAL (ex GST) | 128.5231 | TOTAL COST (incl GST) | 166.6754 | EST. UNIT: |  | PO #: | 2268 | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) | 23 |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 166.6754
AMENITY JOINERY BUNDLES
| RECEIVED | NOT RECEIVED | NOT ORDERED | Unit Amenities Mirror, vanity unit, mixer, basin, additional mixer , mirror and basin for family room | NAME: |  |  | 1 |  | NAME: | Reece | SENT: | 27.05.24 | VERSION #: | A | UNIT COST (ex GST) | 49793.1 | GST | 4979.31 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | Need an additional mirror Alternative: asking for alternaive mixer and basin
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: | 02.07.24 | QUOTE #: | 400814948 | SUBTOTAL (ex GST) | 49793.1 | TOTAL COST (incl GST) | 54772.41 | EST. UNIT: | 36400 | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 54772.41
| ACCEPTED | PAID | ORDERED | Unit Amenities Mirror, mixer, basin, additional mixer, mirror and basin for family room 1 / 2 orders | NAME: | Silicone Arch Mirror 600 x 900, Otti Artis 88 Slate Blue Basin, Bria sink Mixer |  | 1 |  | NAME: | BSW Tristan | SENT: | 19.07.24 | VERSION #: | B | UNIT COST (ex GST) |  | GST | 1091.067 | EST. QTY/UOM: |  | DATE SENT: | 22.07.24 | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | waiting on final quote for alterations
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: | 24.07.24 | QUOTE #: | 128629 | SUBTOTAL (ex GST) | 10910.67 | TOTAL COST (incl GST) | 12001.737 | EST. UNIT: |  | PO #: | 2265 | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 12001.737
| ACCEPTED | PAID | ORDERED | Unit Amenities base vanity carcuss 2 / 2 orders | NAME: |  |  | 1 |  | NAME: | BSW Tristan | SENT: | 27.05.24 | VERSION #: | B | UNIT COST (ex GST) |  | GST | 1903.134 | EST. QTY/UOM: |  | DATE SENT: | 22.07.24 | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | waiting on final quote for alterations
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: | 02.07.24 | QUOTE #: | 125156 | SUBTOTAL (ex GST) | 19031.34 | TOTAL COST (incl GST) | 20934.474 | EST. UNIT: |  | PO #: | 2264 | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 20934.474
| RECEIVED | NOT RECEIVED | NOT ORDERED | Unit Amenities Mirror, vanity unit, mixer, basin, additional mixer , mirror and basin for family room | NAME: |  |  | 1 |  | NAME: | Blue Space | SENT: | 27.05.24 | VERSION #: | A | UNIT COST (ex GST) | 49134.73 | GST | 4913.473 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | Does not include benctops. Need aditional mirror, mixer, and basin
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: | 02.07.24 | QUOTE #: | D35933 | SUBTOTAL (ex GST) | 49134.73 | TOTAL COST (incl GST) | 54048.203 | EST. UNIT: | 36400 | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 54048.203
CURTAINS
| ACCEPTED | PARTIALLY PAID | ORDERED | CRT.1: Curtains, Bedrooms / Living Room | NAME: | Nettex Galaxy, Colour Earth |  | 25 | PIECE | NAME: | Zen Curtains | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 700 | GST | 1750 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | *Pricing carried-across from # 45376: Everton Park Hotel Accomodation Refurbishment - 2200 x 2245mm curtain set (Family Room sliding doors).
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 17500 | TOTAL COST (incl GST) | 19250 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 19250
| ACCEPTED | PARTIALLY PAID | ORDERED | CRT.1: Curtains, Unit 23, 24. AC in window | NAME: | Nettex Galaxy, Colour Earth |  | 2 | PIECE | NAME: | Zen Curtains | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 700 | GST | 140 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0 | *Pricing carried-across from # 45376: Everton Park Hotel Accomodation Refurbishment - 2200 x 2245mm curtain set (Family Room sliding doors).
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 1400 | TOTAL COST (incl GST) | 1540 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 1540
HVAC
| ACCEPTED | NOT RECEIVED | ORDERED | AC UNIT | NAME: | Mitsubishi Heavy Industries 2.0kW Avanti Air Conditioner Split Reverse Cycle Set | #VALUE! | 10 |  | NAME: | Bunnings Warehouse | SENT: | 02.27.24 | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: | 508251 |  |  |  | PHONE: | (07) 3516 8999 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: | https://www.bunnings.com.au/mitsubishi-heavy-industries-2-0kw-avanti-air-conditioner-split-reverse-cycle-set_p0508251? |  |  |  | EMAIL: | BuilderServiceQld@bunnings.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
TOOLS
| ACCEPTED | NOT RECEIVED | ORDERED | Teeth Grinding | NAME: | Wild Zebra Grey 30/40 Grit Redi Lock Style Diamond Grinding Shoe (Soft Bond) × 6 |  | 6 |  | NAME: | All Preparation Equipment | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 25.99 | EST. QTY/UOM: |  | DATE SENT: |  | LEAD TIME: |  | RECEIVED: |  | DUE DATE: |  | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 234 | TOTAL COST (incl GST) | 285.89 | EST. UNIT: |  | PO #: |  | EXPECTED: |  | FORM: |  | INV #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) | 25.9 |  |  | EST. TOTAL: | 0 |  |  | ACTUAL: |  | SUBMITTED: |  |  |  | DELIVERY (ex GST) |  | VARIANCE | 285.89

## SUBCONTRACTOR
V 1.0
[10 empty] | PROJECT NAME/NUMBER: | JXXXX - YYYYY - JOB NAME - JOB DESCRIPTION | [21 empty] | QUOTE STATUS KEY | PAYMENT STATUS KEY | ATTENDANCE STATUS KEY
[10 empty] | SITE ADDRESS: | [15 empty] | PPAR | [6 empty] | UNSENT | NOT RECEIVED | NOT CONTRACTED
|  |  |  | PROJECT SUBCONTRACTOR PROCUREMENT SPREADSHEET | [5 empty] | CLIENT: | [15 empty] | CCPF | [6 empty] | AWAITING RESPONSE | RECEIVED | CONTRACTED
[10 empty] | SITE CONTACT: | [22 empty] | NO RESPONSE | IN PROGRESS | ACTIVE
[10 empty] | PROJECT COMMENCEMENT: | [22 empty] | REJECTED TO QUOTE | PARTIALLY PAID | ON-HOLD
[10 empty] | PROJECT COMPLETION: | [22 empty] | RECEIVED | PAID | COMPLETED
[10 empty] | STAGED WORKS: | [22 empty] | ACCEPTED | [CLEAR] | [CLEAR]
[CLEAR]
| SUMMARY |  |  | CATEGORY | SUBCONTRACTOR DESCRIPTION |  | QTY / | UOM | SUBCONTRACTOR DETAILS |  | QUOTE | [7 empty] | PURCHASE | [5 empty] | INVOICE | [6 empty] | NOTES
| QUOTE STATUS | PAYMENT STATUS | ATTENDANCE STATUS | [7 empty] | QUOTE DETAILS |  |  |  | ESTIMATED COSTINGS |  |  |  | BUDGET ALLOCATION |  | PURCHASE DETAILS |  | ATTENDANCE DETAILS |  | INVOICE DETAILS |  |  | ACTUAL COSTINGS
HOW TO USE THIS TEMPLATE (COPY THE BELOW ROWS WHEN CREATING NEW LINES)
CATEGORY
| UNSENT | NOT RECEIVED | NOT CONTRACTED |  | NAME: |  |  |  | NAME: |  | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: |  | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
PLUMBING
| RECEIVED | NOT RECEIVED | NOT CONTRACTED | Plumbing Works | NAME: | AK Gas & Plumbing, Cameron Anderson |  |  | NAME: | AK Gas & Plumbing, Cameron Anderson | SENT: |  | VERSION #: | B | UNIT COST (ex GST) |  | GST | 2714.73 | EST. QTY/UOM: | 1 | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 1300 007 769 / 0400 829 858 | RECEIVED: |  | QUOTE #: | 18022 | SUBTOTAL (ex GST) | 27147.3 | TOTAL COST (incl GST) | 29862.03 | EST. UNIT: | 32525 | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | works@akgp.com.au / cameron@akgp.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 32525 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 29862.03
| ACCEPTED | NOT RECEIVED | ACTIVE | Plumbing Works | NAME: | Synergy Trades Group |  |  | NAME: | Synergy Trades Group | SENT: |  | VERSION #: | A | UNIT COST (ex GST) |  | GST | 1648 | EST. QTY/UOM: | 1 | DATE SENT: | 25.07.24 | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 07 5458 5329 | RECEIVED: | 22.07.24 | QUOTE #: | 69076 | SUBTOTAL (ex GST) | 16480 | TOTAL COST (incl GST) | 18128 | EST. UNIT: | 32525 | PO #: | 2286 | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | office@synergytrades.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 32525 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 18128
| UNSENT | NOT RECEIVED | NOT CONTRACTED | Guttering / Downpipes | NAME: | KPE Building |  |  | NAME: | Kenton | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 1727.2727 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 17272.727 | TOTAL COST (incl GST) | 18999.9997 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | kpebuilding@bigpond.com | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 18999.9997
ELECTRICAL
| RECEIVED | NOT RECEIVED | NOT CONTRACTED | Electrical Works | NAME: | AK Gas & Plumbing, Cameron Anderson |  |  | NAME: | AK Gas & Plumbing, Cameron Anderson | SENT: |  | VERSION #: | B | UNIT COST (ex GST) |  | GST | 5423.139 | EST. QTY/UOM: | 1 | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 1300 007 769 / 0400 829 858 | RECEIVED: | 18.07.24 | QUOTE #: | 18021 | SUBTOTAL (ex GST) | 54231.39 | TOTAL COST (incl GST) | 59654.529 | EST. UNIT: | 41080 | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | works@akgp.com.au / cameron@akgp.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 41080 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 59654.529
| ACCEPTED | NOT RECEIVED | ACTIVE | Electrical Works | NAME: | Synergy Trades Group |  |  | NAME: | Synergy Trades Group | SENT: |  | VERSION #: | A | UNIT COST (ex GST) |  | GST | 4839 | EST. QTY/UOM: | 1 | DATE SENT: | 25.07.24 | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 07 5458 5329 | RECEIVED: | 22.07.24 | QUOTE #: | 69246 | SUBTOTAL (ex GST) | 48390 | TOTAL COST (incl GST) | 53229 | EST. UNIT: | 41080 | PO #: | 2285 | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | office@synergytrades.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 41080 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 53229
| UNSENT | NOT RECEIVED | NOT CONTRACTED | AC Unit Installs | NAME: | AK Gas & Plumbing, Cameron Anderson |  |  | NAME: | AK Gas & Plumbing, Cameron Anderson | SENT: |  | VERSION #: | B | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 1300 007 769 / 0400 829 858 | RECEIVED: | 30.07.24 | QUOTE #: | 18334 | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | works@akgp.com.au / cameron@akgp.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
HOT WATER SYSTEMS PLUMBING AND ELECTRICAL
| ACCEPTED | NOT RECEIVED | ACTIVE | HWS disconnect and reconnect | NAME: | Synergy Trades Group |  |  | NAME: | Synergy Trades Group | SENT: |  | VERSION #: | A | UNIT COST (ex GST) |  | GST | 794 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 07 5458 5329 | RECEIVED: | 24.07.24 | QUOTE #: | 69275 | SUBTOTAL (ex GST) | 7940 | TOTAL COST (incl GST) | 8734 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | office@synergytrades.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 8734
PAINTING
| AWAITING RESPONSE | NOT RECEIVED | NOT CONTRACTED | Painting Works Internal | NAME: | Wilko Painting |  |  | NAME: | Isaac Jover, Wilko Painting | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 1300 945 564 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | admin@wilkopainting.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
| REJECTED TO QUOTE | NOT RECEIVED | NOT CONTRACTED | Painting Works Internal | NAME: | Luxe Finishes |  |  | NAME: | Ben Mead, Luxe Finishes | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 0422 509 079 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | ben@luxefinishesau.com | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
| ACCEPTED | NOT RECEIVED | ACTIVE | Painting Works External | NAME: | Wilko Painting |  |  | NAME: | Isaac Jover, Wilko Painting | SENT: | 03.07.24 | VERSION #: | B | UNIT COST (ex GST) |  | GST | 8685 | EST. QTY/UOM: |  | DATE SENT: | 26.07.24 | START: | 05.08.24 | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 1300 945 564 | RECEIVED: | 19.07.24 | QUOTE #: | 870 | SUBTOTAL (ex GST) | 86850 | TOTAL COST (incl GST) | 95535 | EST. UNIT: |  | PO #: | 2288 | END: | 06.10.24 | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | admin@wilkopainting.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: |  | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 95535
| REJECTED TO QUOTE | NOT RECEIVED | NOT CONTRACTED | Painting Works External | NAME: | Luxe Finishes |  |  | NAME: | Ben Mead, Luxe Finishes | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 0422 509 079 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | ben@luxefinishesau.com | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
SHOWER SCREEN
| RECEIVED | NOT RECEIVED | NOT CONTRACTED | Shower 1, unit 26 Supply and Install 1 x 10mm clear frameless glass bath panel Approximately 1600mm high x 700mm wide Installed with polished chrome fixing brackets | NAME: |  | 1 |  | NAME: | Hills Robes & Screens | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 595.45 | GST | 59.545 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | (07) 5491 7567 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 595.45 | TOTAL COST (incl GST) | 654.995 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | jacki@hillswardrobes.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 654.995
| RECEIVED | NOT RECEIVED | NOT CONTRACTED | Shower 2, unit 8 Supply and install 1 x 10mm clear frameless glass shower screen Approximately 1800mm high x 485mm x 665mm door x 165mm (splayed/quadrant) Installed with polished chrome fittings | NAME: |  | 1 |  | NAME: | Hills Robes & Screens | SENT: |  | VERSION #: |  | UNIT COST (ex GST) | 1381.818 | GST | 138.1818 | EST. QTY/UOM: |  | DATE SENT: |  | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | (07) 5491 7567 | RECEIVED: |  | QUOTE #: |  | SUBTOTAL (ex GST) | 1381.818 | TOTAL COST (incl GST) | 1519.9998 | EST. UNIT: |  | PO #: |  | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | jacki@hillswardrobes.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 1519.9998
JOINERY
| ACCEPTED | NOT RECEIVED | ACTIVE | Vanity Benchtops | NAME: | Polytec Smooth Marmo Di Torre Smooth, Square Edge | 26 |  | NAME: | Multiform, Damien Cross | SENT: |  | VERSION #: |  | UNIT COST (ex GST) |  | GST | 341.63 | EST. QTY/UOM: |  | DATE SENT: | 24.07.24 | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 07 3271 5311 | RECEIVED: | 17.07.24 | QUOTE #: | TQ23833 | SUBTOTAL (ex GST) | 3416.3 | TOTAL COST (incl GST) | 3757.93 | EST. UNIT: |  | PO #: | 2268 | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | benchtops@mfj.com.au | VALID UNTIL: |  |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 3757.93

## HIRE SCHEDULE
V 1.0
[10 empty] | PROJECT NAME/NUMBER: | JXXXX - YYYYY - JOB NAME - JOB DESCRIPTION | [19 empty] | QUOTE STATUS KEY | PAYMENT STATUS KEY | HIRE STATUS KEY
[10 empty] | SITE ADDRESS: | [13 empty] | PPAR | [6 empty] | UNSENT | NOT RECEIVED | NOT HIRED
|  |  |  | PROJECT HIRE PROCUREMENT SPREADSHEET | [5 empty] | CLIENT: | [13 empty] | CCPF | [6 empty] | AWAITING RESPONSE | RECEIVED | SCHEDULED
[10 empty] | SITE CONTACT: | [20 empty] | NO RESPONSE | IN PROGRESS | AWAITING COLLECTION
[10 empty] | PROJECT COMMENCEMENT: | [20 empty] | REJECTED TO QUOTE | PARTIALLY PAID | ON-HOLD
[10 empty] | PROJECT COMPLETION: | [20 empty] | RECEIVED | PAID ON ACCOUNT | ON-HIRE
[10 empty] | STAGED WORKS: | [20 empty] | ACCEPTED | PAID | RETURNED
[31 empty] | [CLEAR] | [CLEAR] | [CLEAR]
| SUMMARY |  |  | CATEGORY / NOTES | ITEM / DESCRIPTION |  | QTY / | UOM | SUPPLIER DETAILS |  | QUOTE | [6 empty] | PURCHASE |  |  |  |  | INVOICE | [6 empty] | NOTES
| QUOTE STATUS | PAYMENT STATUS | HIRE STATUS | [7 empty] | QUOTE DETAILS |  |  | ESTIMATED COSTINGS |  |  |  | BUDGET ALLOCATION |  | PURCHASE DETAILS | HIRE DETAILS |  | INVOICE DETAILS |  |  | ACTUAL COSTINGS
HOW TO USE THIS TEMPLATE (COPY THE BELOW ROWS WHEN CREATING NEW LINES)
CATEGORY
| UNSENT | NOT RECEIVED | NOT HIRED |  | NAME: |  |  |  | NAME: |  | SENT: |  | VERSION #: | UNIT COST (ex GST) |  | GST | 0 | EST. QTY/UOM: |  | DATE SENT: | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0 | EST. UNIT: |  | PO #: | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: |  | VALID UNTIL: |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 0
STORAGE CONTAINER
| RECEIVED | NOT RECEIVED | NOT HIRED | $25/week, with a $400 delivery / pickup | NAME: | 20 FT Container | 9 | weeks | NAME: | Sunshine Coast Containers | SENT: | 19.07.24 | VERSION #: | UNIT COST (ex GST) | 25 | GST | 62.5 | EST. QTY/UOM: |  | DATE SENT: | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: |  | RECEIVED: | 19.07.24 | QUOTE #: | SUBTOTAL (ex GST) | 225 | TOTAL COST (incl GST) | 687.5 | EST. UNIT: |  | PO #: | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: |  | VALID UNTIL: |  |  | DELIVERY (ex GST) | 400 |  |  | EST. TOTAL: | 0 |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 687.5
| ACCEPTED | NOT RECEIVED | SCHEDULED | $99/month, with a $300 delivery / pickup | NAME: | 20 FT Container | 3 | months | NAME: | Bionic Group | SENT: | 19.07.24 | VERSION #: | UNIT COST (ex GST) | 99 | GST | 59.7 | EST. QTY/UOM: |  | DATE SENT: | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: |  | RECEIVED: | 19.07.24 | QUOTE #: | SUBTOTAL (ex GST) | 297 | TOTAL COST (incl GST) | 656.7 | EST. UNIT: |  | PO #: | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: |  | VALID UNTIL: |  |  | DELIVERY (ex GST) | 300 |  |  | EST. TOTAL: | 0 |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 656.7
| RECEIVED | NOT RECEIVED | NOT HIRED | $163/per month, $730 delivery, $730 pickup | NAME: | 20 FT Container | 3 | months | NAME: | Royal Wolf | SENT: | 19.07.24 | VERSION #: | UNIT COST (ex GST) | 163 | GST | 194.9 | EST. QTY/UOM: |  | DATE SENT: | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: |  | RECEIVED: | 19.07.24 | QUOTE #: | SUBTOTAL (ex GST) | 489 | TOTAL COST (incl GST) | 2143.9 | EST. UNIT: |  | PO #: | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: |  | VALID UNTIL: |  |  | DELIVERY (ex GST) | 1460 |  |  | EST. TOTAL: | 0 |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 2143.9
SKIP BINS
| RECEIVED | NOT RECEIVED | NOT HIRED |  | NAME: | 12M3 Skip Bin | 1 |  | NAME: | Kartaway | SENT: | 19.07.24 | VERSION #: | UNIT COST (ex GST) | 1500 | GST | 161.25 | EST. QTY/UOM: |  | DATE SENT: | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: |  | RECEIVED: |  | QUOTE #: | SUBTOTAL (ex GST) | 1500 | TOTAL COST (incl GST) | 1773.75 | EST. UNIT: |  | PO #: | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: |  | VALID UNTIL: |  |  | DELIVERY (ex GST) | 112.5 |  |  | EST. TOTAL: | 0 |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 1773.75
| ACCEPTED | IN PROGRESS | SCHEDULED |  | NAME: | 12M3 Skip Bin | 2 |  | NAME: | Suncoast Skips | SENT: | 19.07.24 | VERSION #: | UNIT COST (ex GST) | 1505 | GST | 301 | EST. QTY/UOM: |  | DATE SENT: | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | 0472 906 007 | RECEIVED: |  | QUOTE #: | SUBTOTAL (ex GST) | 3010 | TOTAL COST (incl GST) | 3311 | EST. UNIT: |  | PO #: | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | info@suncoastskips.com.au | VALID UNTIL: |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 3311
TEMP FENCING
| ACCEPTED | NOT RECEIVED | SCHEDULED | $250 in clused delivery, install and removal | NAME: | 25 Temp fence panels with base and clips | 1 |  | NAME: | (Macca) Dan McKenzie, ATF Sunshine Coast & Total Site Setup | SENT: | 19.07.24 | VERSION #: | UNIT COST (ex GST) |  | GST | 91 | EST. QTY/UOM: |  | DATE SENT: | START: |  | RECEIVED: |  | DUE DATE: | UNIT COST (ex GST) |  | GST | 0
[5 empty] | ID/SKU: |  |  |  | PHONE: | (07) 5494 8010 | RECEIVED: | 22.07.24 | QUOTE #: | SUBTOTAL (ex GST) | 910 | TOTAL COST (incl GST) | 1001 | EST. UNIT: |  | PO #: | END: |  | FORM: |  | INV #: | SUBTOTAL (ex GST) | 0 | TOTAL COST (incl GST) | 0
[5 empty] | LINK: |  |  |  | EMAIL: | info@atfsunshinecoast.com.au | VALID UNTIL: |  |  | DELIVERY (ex GST) |  |  |  | EST. TOTAL: | 0 |  | TOTAL: | 1 day/s | SUBMITTED: |  |  | DELIVERY (ex GST) |  | VARIANCE | 1001

## CARPET T.O.
| CARPET AREA | ADDITIONAL | TOTAL
Unit 1 | 18 |  | 18
Unit 2 | 18 |  | 18
Unit 3 | 18 |  | 18
Unit 4 | 18 |  | 18 | BLOCK 1
Unit 5 | 18 |  | 18 | BLOCK 2
Unit 6 | 18 |  | 18 | BLOCK 3
Unit 7 | 18 |  | 18
Unit 8 | 18 |  | 18
Unit 9 | 18 |  | 18
Unit 10 | 18 |  | 18
Unit 11 | 18 |  | 18
Unit 11A | 18 |  | 18
Unit 12 | 18 |  | 18
Unit 13 | 18 |  | 18
Unit 14 | 18 |  | 18
Unit 15 | 18 |  | 18
Unit 16 | 18 |  | 18
Unit 17 | 18 |  | 18
Unit 18 | 18 |  | 18
Unit 19 | 18 |  | 18
Unit 20 | 18 |  | 18
Unit 21 | 18 |  | 18
Unit 22 | 18 |  | 18
Unit 23 | 18 |  | 18
Unit 24 | 18 |  | 18
Unit 25 | 18 |  | 18
Unit 26 | 36 |  | 36
|  | Total | 504
|  | Total With Wastage (10%) | 554.4

## S.BACK T.O.
| TILING AREA |  | TOTAL
Unit 1 | 0.25 |  | 0.25
Unit 2 | 0.25 |  | 0.25
Unit 3 | 0.25 |  | 0.25
Unit 4 | 0.25 |  | 0.25 | BLOCK 1
Unit 5 | 0.25 |  | 0.25 | BLOCK 2
Unit 6 | 0.25 |  | 0.25 | BLOCK 3
Unit 7 | 0.25 |  | 0.25
Unit 8 | 0.25 |  | 0.25
Unit 9 | 0.25 |  | 0.25
Unit 10 | 0.25 |  | 0.25
Unit 11 | 0.25 |  | 0.25
Unit 11A | 0.25 |  | 0.25
Unit 12 | 0.25 |  | 0.25
Unit 13 | 0.25 |  | 0.25
Unit 14 | 0.25 |  | 0.25
Unit 15 | 0.25 |  | 0.25
Unit 16 | 0.25 |  | 0.25
Unit 17 | 0.25 |  | 0.25
Unit 18 | 0.25 |  | 0.25
Unit 19 | 0.25 |  | 0.25
Unit 20 | 0.25 |  | 0.25
Unit 21 | 0.25 |  | 0.25
Unit 22 | 0.25 |  | 0.25
Unit 23 | 0.25 |  | 0.25
Unit 24 | 0.25 |  | 0.25
Unit 25 | 0.25 |  | 0.25
Unit 26 | 0.55 |  | 0.55
|  | Total | 7.05
|  | Total With Wastage (10%) | 7.755

## RnM.1
ITEM | ROOM 1 | ROOM 2 | ROOM 3 | ROOM 4 | ROOM 5 | ROOM 6 | ROOM 7 | ROOM 8 | ROOM 9 | ROOM 10 | ROOM 11 | ROOM 11a | ROOM 12 | ROOM 14 | ROOM 15 | ROOM 16 | ROOM 17 | ROOM 18 | ROOM 19 | ROOM 20 | ROOM 21 | ROOM 22 | ROOM 23 | ROOM 24 | ROOM 25 | Room 26
Entry tiles Remove | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570 | 570
New Shower Head $175 supply | 250 | 250 | 250 | No | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | No | 250 | 250 | 250 | 250 | 250 | 250 | 250 | No
New Shower Taps $125 supply | No | No | No | No | 225 | No | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | No
New Shower Shelf | No | No | Yes | No | 100 | No | 100 | 100 | 100 | 100 | No | No | 100 | No | 100 | No | 100 | No | No | No | 100 | 100 | 100 | 100 | 100 | No
New Toilet Roll Holder $35 supply | 50 | No | No | No | No | 50 |  | 50 | 50 |  | 50 | 50 | 50 | 50 |  | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 |  | 50
Hand Towel Holder - change to hook/relocate | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | No
Move Towel Holder | 15 | 15 | No | No | No | No |  | 15 | 15 |  | 15 | 15 | 15 | 15 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |  | No
New Shower Handle | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | No
HWC Reskin Joinery (included in quote) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No |  | No
NO HWC - New Joinery (included in quote) | No | No | No | No | No | No | No | No | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes |  | Yes
New TV | Yes | No | Yes | No | No | Yes |  | Yes |  |  | No | Yes | No | No |  | Yes | Yes | Yes | No | No | Yes | Yes | Yes | Yes |  | Yes
New Fridge | No | Yes | No | No | Yes | No |  | Yes | No |  | No | Yes | Yes | No |  | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No |  | No
New Iron | No | No | Yes | No | No | No |  | No | No |  | Yes | No | No | No |  | No | No | No | No | No | No | No | No | Yes |  | Yes
New Kettle | No | No | No | Yes | No | Yes |  | No | Yes |  | Yes | Yes | Yes | No |  | No | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes |  | Yes
New Microwave | No | Yes | No | No | No | No |  | No | No |  | No | No | No | No |  | Yes | Yes | Yes | No | No | Yes | No | No | Yes |  | Yes
New Entry Door Seal | No | No | 45 | No | No | No |  | No | No |  | No | 45 | No | 45 |  | No | No | No | 45 | No | No | 45 | No | No |  | No
New Door Chain | No | No | No | 20 | 20 | No |  | No | No |  | No | No | 20 | No |  | No | No | No | No | No | No | 20 | No | No |  | No
Replace old HVAC with new system | 2500 | 2500 | No | No | No | No | No | 2500 | 2500 | 2500 | 2500 | No | No | No | 2500 | 2500 | 2500 | No | No | No | No | No | No | No | 2500 | No
Outdoor Furniture | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes
Bathroom Splashback | No | No | 350 | No | No | No | 350 | No | No | 350 | No | No | No | No | 350 | No | 350 | No | No | No | No | No | No | No | 350 | No
New Outlets/Light Switch |  |  |  | 50 | 50 | 50 | 50 | No | No | 50 | 50 | 50 | No | 50 | 50 | No | No | No | No | No | 50 | 50 | No | No | 50 | No
New Lights | [6 empty] | 280 |  |  | 280 | 280 | 280 | 280 | 280 | 280 | 280 | No | No | No | No | No | No | No | No | 280 | No
Window Film | [5 empty] | 320 | 320 | No | No | 320 | No | No | No | No | 320 | No | No | No | No | No | No | No | No | No | 320 | No
Shower Screen | [7 empty] | 1800 | No |  | No | No | No | No |  | No | No | No | No | No | No | No | No | No |  | 1800
Queen Room ONLY | [8 empty] | Yes |  | Yes | Yes | No | No |  | No | No | No | No | No | No | No | Yes | Yes |  | No
New Door | [15 empty] | No | No | No | No | No | No | 850 | No | No |  | No
Blind under split system | [15 empty] | No | No | No | No | No | No | No | 150 | 150 | 150 | No
Custom Vanity included in quote | [15 empty] | No | No | No | No | No | No | No | No | No | No | Yes
HWC Cupbaord Lock | [25 empty] | 45
ROOM NOTES |  |  |  | Shower leaks |  |  |  |  | 150 |  | Option to close in old door. | [9 empty] | Needs Pest control |  |  |  |  | Family Room
LIGHT NOTES |  |  |  | Remove mirror, hang TV |  |  | Remove mirror, hang TV | Remove mirror, hang TV |  |  | 1x square 2x different round lights. Remove mirror, hang TV. Adjoining Doors with 11A | 2x round 1x square. Remove mirror, hang TV. Adjoining Doors with 11 | 2x Round 1x Square | Light bulb not light | Remove mirror, hang TV | 2x square lights 1x round. Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV Door to other room
| 3445 | 3395 | 1275 | 700 | 1275 | 1300 | 2205 | 5570 | 3920 | 4705 | 4000 | 1545 | 1570 | 1545 | 4705 | 3950 | 4120 | 920 | 1215 | 1170 | 1320 | 2235 | 1420 | 1420 | 4855 | 2465
TOTAL | 66245

## RnM.2
ITEM | ROOM 1 | ROOM 2 | ROOM 3 | ROOM 4 | ROOM 5 | ROOM 6 | ROOM 7 | ROOM 8 | ROOM 9 | ROOM 10 | ROOM 11 | ROOM 11a | ROOM 12 | ROOM 14 | ROOM 15 | ROOM 16 | ROOM 17 | ROOM 18 | ROOM 19 | ROOM 20 | ROOM 21 | ROOM 22 | ROOM 23 | ROOM 24 | ROOM 25 | Room 26
Entry tiles Remove | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 26
New Shower Head supply | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | 23 | 175 |  | 4025
New Shower Taps supply | No | No | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | 20 | 125 |  | 2500
New Shower Shelf | No | No | Yes | No | Yes | No | Yes | Yes | Yes | Yes | No | No | Yes | No | Yes | No | Yes | No | No | No | Yes | Yes | Yes | Yes | Yes | No | 14
New Toilet Roll Holder supply | Yes | No | No | No | No | Yes | No | Yes | Yes | No | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | 18 |  |  | 6525
Hand Towel Holder - change to hook/relocate | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | 25
Move Towel Holder | Yes | Yes | No | No | No | No | No | Yes | Yes | No | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | 17
New Shower Handle | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | 25
HWC Reskin Joinery (included in quote) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | 11
NO HWC - New Joinery (included in quote) | No | No | No | No | No | No | No | No | No | No | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | No | Yes | 13
New TV | Yes | No | Yes | No | No | Yes | No | Yes | No | No | No | Yes | No | No | No | Yes | Yes | Yes | No | No | Yes | Yes | Yes | Yes | No | Yes | 13
New Fridge | No | Yes | No | No | Yes | No | No | Yes | No | No | No | Yes | Yes | No | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | 12
New Iron | No | No | Yes | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | Yes | 4
New Kettle | No | No | No | Yes | No | Yes | No | No | Yes | No | Yes | Yes | Yes | No | No | No | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | No | Yes | 14
New Microwave | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | No | No | Yes | No | No | Yes | No | Yes | 7
New Entry Door Seal | No | No | Yes | No | No | No | No | No | No | No | No | Yes | No | Yes | No | No | No | No | Yes | No | No | Yes | No | No | No | No | 5
New Door Chain | No | No | No | Yes | Yes | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | Yes | No | No | No | No | 4
Replace old HVAC with new system | Yes | Yes | No | No | No | No | No | Yes | Yes | No | Yes | No | No | No | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | 8 | 2500 | 700 | 5600
Outdoor Furniture | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | 11
Bathroom Splashback - all units to now have S.B | No | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | Yes | No | Yes | No | No | No | No | No | No | No | Yes | No | 6
New Outlets/Light Switch | No | No | No | Yes | Yes | Yes | Yes | No | No | Yes | Yes | Yes | No | Yes | Yes | No | No | No | No | No | Yes | Yes | No | No | Yes | No | 12 | 50 |  | 600
New Lights | No | No | No | No | No | No | Yes | No | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | Yes | No | 9 | 280 |  | 2520
Window Film | No | No | No | No | No | Yes | Yes | No | No | Yes | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | Yes | No | 5
Shower Screen | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | 2
Queen Room ONLY | No | No | No | No | No | No | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | 5 |  |  | 8720
New Door | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | 1
Blind under split system | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | No | 3
Custom Vanity included in quote | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | 1
HWC Cupbaord Lock | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | 1
ROOM NOTES |  |  |  | Shower leaks | [6 empty] | Option to close in old door. | [9 empty] | Needs Pest control |  |  |  |  | Family Room
LIGHT NOTES |  |  |  | Remove mirror, hang TV |  |  | Remove mirror, hang TV | Remove mirror, hang TV |  |  | 1x square 2x different round lights. Remove mirror, hang TV. Adjoining Doors with 11A | 2x round 1x square. Remove mirror, hang TV. Adjoining Doors with 11 | 2x Round 1x Square | Light bulb not light | Remove mirror, hang TV | 2x square lights 1x round. Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV | Remove mirror, hang TV Door to other room

## Sheet2
vanity off shelf | 19500
sink and mixer | 8320 |  | 320 for both |  | 4703.4 | 2340 | 7043.4
mirrors | 8580 | [5 empty] | 3758.18
[5 empty] | 16900 |  | 10801.58
6098.42
[5 empty] | remaing for vanity |  | 25598.42
total | 36400
[5 empty] | Multiform benchtops | 3341.3
3341.3
6682.6
[5 empty] | remainging for cab | 18915.82
Total for Mixer, basin & mirror | 10910.67
Total for vanity base units | 18922.25
29832.92
Total for multiform vanity benchtops | 131.3962 | 3416.3
Total | 33249.22
| Accommodation | R&M |  |  | SYNERGY | AK
Budgeted Electrical | 6000 | 10120 | 24960 | 41080 | 48390 | 54231.39
Budgeted Plumbing | 26000 | 6525 |  | 32525 | 14981.82 | 27147.3
|  |  | total | 73605 | 63371.82 | 81378.69
7218.18
70590

## Accomodation
|  | Date In | Date Out | Total Nights | Total Price | Price per day | Accomodation | Distance to work site | Notes
1 | https://www.airbnb.com.au/rooms/1117726636964082191?adults=6&location=Currimundi%2C%20Queensland%2C%20Australia&search_mode=regular_search&check_in=2024-07-29&check_out=2024-10-04&source_impression_id=p3_1719878787_P3LoZlr0WWTbUdm4&previous_page_section_name=1001&federated_search_id=f8b0fe5a-4e82-4f43-a7e8-bc670b2a4957 | Monday 29.07.24 | Friday 04.10.24 | 67 | 15910.99 | 237.4775 | 4 bedroom / 6 bed / 2 bath / 8 guests / laundry/ off street parking | approx 10 minute drive | Full works period
1.1 | https://www.airbnb.com.au/rooms/1117726636964082191?adults=6&search_mode=regular_search&check_in=2024-07-29&check_out=2024-08-09&source_impression_id=p3_1719879105_P3cAwSCYvX4fnEqL&previous_page_section_name=1000&federated_search_id=7242c6bf-6175-4182-a1dd-baae90128077 | Monday 29.07.24 | Friday 09.08.24 | 11 | 2703.39 | 245.7627 |  |  | first fortnight
1.2 | https://www.airbnb.com.au/rooms/1117726636964082191?adults=6&search_mode=regular_search&check_in=2024-07-29&check_out=2024-08-09&source_impression_id=p3_1719879105_P3cAwSCYvX4fnEqL&previous_page_section_name=1000&federated_search_id=7242c6bf-6175-4182-a1dd-baae90128077 | Monday 12.08.24 | Friday 23.08.24 | 11 | 2703.39 | 245.7627 |  |  | second fortnight
2 | https://www.airbnb.com.au/rooms/812118503746636621?adults=6&search_mode=regular_search&check_in=2024-07-29&check_out=2024-08-09&source_impression_id=p3_1719882687_P3DO58AO-nS4m5Q-&previous_page_section_name=1000&federated_search_id=85115ff7-d081-4cb5-af73-c1b236602b59 | Monday 29.07.24 | Friday 09.08.24 | 11 | 2941.38 | 267.3982