Project Schedule Template

Stage: 1

| Milestones to be completed | Bulk Earthworks – Site Cut (23/05/2024 - 20/08/2024) - Milestone 1: Clear Site of Vegetation – Complete by 06/06/2024 - Milestone 2: Excavation of Foundation Material & Footings – Complete by 18/07/2024 - Milestone 3: Soil Testing & Analysis Completion – Complete by 01/07/2024 - Milestone 4: Material Export Commences – Ongoing until 20/08/2024 Civil Works – Stormwater Drainage (29/05/2024 - 06/06/2024) - Milestone 1: Stormwater Pipework Installation – Complete by 06/06/2024 - Milestone 2: Field Inlet Pit and Manhole Installation – Complete by 06/06/2024 Inground Services (Hydraulics) (29/05/2024 - 07/06/2024) - Milestone 1: Pipework Installation for Hose Taps – Complete by 07/06/2024 - Milestone 2: Hydraulic Isolation Valve and Cut-ins – Complete by 07/06/2024 Foundations – Bored Piers (10/06/2024 - 14/06/2024) - Milestone 1: Excavation and Pier Preparation – Complete by 14/06/2024 - Milestone 2: Bored Piers Installation & Reinforcement – Complete by 14/06/2024 Slab on Ground & Footings (17/06/2024 - 20/08/2024) - Milestone 1: Slab Base Course & Damp Proof Membrane Installation – Complete by 14/06/2024 - Milestone 2: Slab Reinforcement and Footing Preparation – Complete by 20/08/2024 - Milestone 3: Concrete Pouring of Slab & Footings – Complete by 20/08/2024 Blockwork & Engaged Piers (02/07/2024 - 09/07/2024) - Milestone 1: C Block Installation to Piers – Complete by 09/07/2024 - Milestone 2: Corefill of Blockwork – Complete by 09/07/2024 Structural Steel & Roof Framing (10/07/2024 - 14/08/2024) - Milestone 1: Installation of Roof Beams and Rafters – Complete by 14/08/2024 - Milestone 2: Roof Bracing Installation – Complete by 14/08/2024 - Milestone 3: Roofing and Insulation Installation – Complete by 14/08/2024 External Façade & Doors (25/07/2024 - 19/08/2024) - Milestone 1: Louvres and Door Frame Installation – Complete by 19/08/2024 - Milestone 2: Door Hanging & Hardware Installation – Complete by 19/08/2024 Hydraulic Rough-in / Fit Off (25/07/2024 - 30/07/2024) - Milestone 1: Hose Tap Connections – Complete by 30/07/2024 - Milestone 2: Leak Testing & QA – Complete by 30/07/2024 Electrical Rough-in / Fit Off (25/07/2024 - 07/08/2024) - Milestone 1: Conduit and Cable Installation – Complete by 07/08/2024 - Milestone 2: Electrical Testing & Commissioning – Complete by 07/08/2024 Lockers Installation (20/08/2024) - Milestone 1: Locker Installation Completion – 20/08/2024 Civil Works & Landscaping (01/08/2024 - 02/08/2024) - Milestone 1: Footpath Concrete Pouring – Complete by 02/08/2024 - Milestone 2: Landscaping & Rock Protection Channel Completion – Complete by 02/08/2024 Final Project Milestones: - Overall Completion (All Sections): 20/08/2024 - Final QA Inspection & Handover: 20/08/2024 |
| --- | --- |
| Estimated project progress | Bulk Earthworks – Site Cut (23/05/2024 - 20/08/2024) - Duration: 90 days - Milestone Completion: - Site cleared and excavation begins: 06/06/2024 (15% complete) - Excavation and soil testing completed: 01/07/2024 (45% complete) - Material export commences: 01/07/2024 (60% complete) - Estimated Completion: 100% by 20/08/2024 Civil Works – Stormwater Drainage (29/05/2024 - 06/06/2024) - Duration: 8 days - Milestone Completion: - Stormwater pipework and pits installed: 06/06/2024 (100% complete) Inground Services (Hydraulics) (29/05/2024 - 07/06/2024) - Duration: 9 days - Milestone Completion: - Pipework, valves, and hose tap installation completed: 07/06/2024 (100% complete) Foundations – Bored Piers (10/06/2024 - 14/06/2024) Duration: 5 days Milestone Completion: Pier excavation, reinforcement, and concrete pour completed: 14/06/2024 (100% complete) Slab on Ground & Footings (17/06/2024 - 20/08/2024) - Duration: 65 days - Milestone Completion: - Slab base and damp-proof membrane completed: 14/06/2024 (10% complete) - Reinforcement installed & concrete pour for slab: 20/08/2024 (100% complete) Blockwork & Engaged Piers (02/07/2024 - 09/07/2024) - Duration: 8 days - Milestone Completion: - Blockwork completed (C Blocks and corefill): 09/07/2024 (100% complete) Structural Steel & Roof Framing (10/07/2024 - 14/08/2024) - Duration: 36 days - Milestone Completion: - Roof framing and steel installed: 14/08/2024 (100% complete) External Façade & Doors (25/07/2024 - 19/08/2024) - Duration: 26 days - Milestone Completion: - Louvres and door frames installed: 19/08/2024 (100% complete) Hydraulic Rough-in / Fit Off (25/07/2024 - 30/07/2024) - Duration: 6 days - Milestone Completion: - Hose taps connected and QA testing completed: 30/07/2024 (100% complete) Electrical Rough-in / Fit Off (25/07/2024 - 07/08/2024) - Duration: 14 days - Milestone Completion: - Electrical conduit & cable installation, commissioning: 07/08/2024 (100% complete) Lockers Installation (20/08/2024) - Duration: 1 day - Milestone Completion: - Lockers installed: 20/08/2024 (100% complete) Civil Works & Landscaping (01/08/2024 - 02/08/2024) - Duration: 2 days - Milestone Completion: - Footpath concrete and landscaping completed: 02/08/2024 (100% complete) |
| Start date | 20/05/2024 |
| End date | 21/08/2024 |
| Labour start date | 23/05/2024 |
| Delivery date for materials | Bulk Earthworks – Site Cut Delivery Dates: - Machinery fuel & consumables: Before 20/05/2024 - Soil testing services booked: Before 01/06/2024 - Trucks for material export: Scheduled by 01/07/2024 Civil Works – Stormwater Drainage Delivery Dates: - Pipes, pits, and manhole materials: Delivered by 27/05/2024 - Bedding material (gravel, sand): Delivered by 27/05/2024 - Backfill material (crusher dust, compacted fill): Ongoing as needed Inground Services (Hydraulics) Delivery Dates: - Hydraulic pipework, fittings, valves: Delivered by 27/05/2024 - Bedding material (sand, aggregate): Delivered by 27/05/2024 - Concrete cutting tools & supplies: before 29/05/2024 Foundations – Bored Piers Delivery Dates: - Reinforcement steel & formwork: Delivered by 07/06/2024 - Concrete for piers: Scheduled as per pour sequence Slab on Ground & Footings Delivery Dates: - Damp proof membrane & reinforcement mesh: Delivered by 14/06/2024 - Concrete supply: Scheduled as per pour plan Blockwork & Engaged Piers Delivery Dates: - Blocks & mortar: Delivered by 28/06/2024 - Corefill concrete: Scheduled for pour dates Structural Steel & Roof Framing Delivery Dates: - Steel beams, rafters, bracing: Delivered by 08/07/2024 - Purlins & out riggers: Delivered by 08/07/2024 - Roofing sheets & insulation: Delivered by 22/07/2024 External Façade & Doors Delivery Dates: - Louvres & door frames: Delivered by 23/07/2024 - Door hardware: Delivered by 23/07/2024 Hydraulic Rough-in / Fit Off Delivery Dates: - Hose taps & fittings: Delivered by 23/07/2024 Electrical Rough-in / Fit Off Delivery Dates: - Electrical conduits & cables: Delivered by 22/07/2024 - DB-XX, emergency lighting & accessories: Delivered by 22/07/2024 Lockers Installation Delivery Dates: - Lockers (Client-supplied): Ensure delivered before 19/08/2024 Civil Works & Landscaping Delivery Dates: - Base course & concrete for footpaths: Delivered by 29/07/2024 - 750mm rock for protection channel: Delivered by 29/07/2024 - Topsoil, turf & landscaping materials: Delivered by 30/07/2024 |

| Task | Start date | End date | Materials required | Labour required |
| --- | --- | --- | --- | --- |
| Bulk Earth works – site cut - Clear site of vegetation - Excavate foundation material and footings to nominated design - Conduct soil testing to determine classification of fill. - Export Material (export location to be confirmed) | 23/05/2024 | 20/08/2024 | - Temporary fencing - Dust control materials - Excavation tools - Geotextile fabric - Reinforcing steel - Sampling tools - Laboratory materials and equipment - Dumo trucks or haul trucks to transport material off site | Civil Contractor |
| Civil Works- Stormwater Drainage - Excavate trench for new 225 dia SW pipe - Brean in to existing pipework and install new 900 x 900 manhole. - Install new 900 x 900 field inlet pit at Easter side of proposed rock protection channel. - Haunch and backfill excavation - Install bedding and 225 dia SW pipework | 29/05/2024 | 06/06/2024 | - Geotextile fabric for trench lining - Temporary fencing/ barriers - Water trucks for dust control - Concrete manhole sections (900 x 900 size) - Reinforcing steel - Grout for sealing joints - Manhole covers and frames - Waterproofing materials - Precast concrete field inlet pit (900 x 900) - Inlet pit frame and grating - Granular fill - Bedding sand or crushed stone - Backfill material - Compaction aids - 225mm diameter SW stormwater pipes - Bedding material - Pipe connections | Civil Contractor Hydraulics Contractor |
| Inground Services (Hydraulics) - Excavate trench for inground hydraulic pipework. - Lay bedding material and 20 dia pipe with upturn at new building point and connection point. - After hours- locate isolation valve to existing 20 dia pipework. - After Hours- isolate water feed and complete cut in / tee off for new water feed. - After hours- Deisolate water feed and monitor pipework for and leaks. - After Hours- Haunch and backfill pipework to required density ratio for inground services (electrical). - Complete concrete cutting works to existing hardstand areas. - Complete trenching for inground electrical conduits and pits. - Install x2 600 x 600 pits - Lay bedding material and install conduit with upturn at new DB-XX and MSB 3083 connection point. - Haunch and back fill trench to nominated compaction ratio. - Reinstate concrete hardstand. | 29/05/2024 | 07/06/2024 | - Temporary Fencing - Dust suppression materials - Bedding material - 20mm diameter pipe - Fittings and connectors - Sealant for pipe connections - Isolation valve - Tool and valves for isolation - Tee-off fittings - Valve for isolating existing feed - New pipe and fittings for tee-off connection - Gaskets for watertight seals - Backfill material - Cutting blades for concrete - Dust suppression tools - Conduit - Electrical pit frames and lids - Precast concrete - Electrical conduit - Reinforcement - Concrete - Formwork for shaping the reinstated concrete - Joint seal | Civil Contractor |
| Foundations – Bored Piers - Excavate BP1 piers to 1200-1800 depth. - Clear-out excavation and prepare reinforcement to piers. | 10/06/2024 | 14/06/2024 | - Temporary Fencing - Temporary Shoring - Reinforcement Steel - Ties – for securing the reinforcement bars - Concrete for piers - Concrete formwork | Civil Contractor |
| Slab on ground & footings - Prepare slab base course / lay damp proof membrane. - Prepare and install reinforcement to EB1 and IB1’s. - Install top and bottom N12-200 slab reinforcement. - Complete all quality assurance/ prepour inspections - Pour concrete to footings / slab on ground | 17/06/2024 | 20/08/2024 | - Base course material - Damp proof membrane - Geotextile fabric - Reinforcing steel bar - Steel ties - N12-200 reinforcement bar - Inspection forms/ checklists - Concrete mix - Admixtures - Curing compounds | Concrete contractor |
| Blockwork and engaged piers - Install C blocks to EP1 piers and 190 series H block walls corefill blockwork. - Corefill blockwork | 02/07/2024 | 09/07/2024 | - C Blocks - 190 series H Blocks - Mortar - Reinforcement Bars - Block Adhesive - Fillers | Blockwork Contractor |
| Structural Steel, roof framing and installation - Install roof beams and rafters RB1/2 - Install wall headers and fox off to roof beams (WH1’s) - Install bracing to roof framework (BR1 & S1) - Install P1,2 & 3 purlins and OR1 out riggers. - Install roofing/ roof insulation | 10/07/2024 | 14/08/2024 | - Roof Beams (RB1-2) - Rafters - Bolts - Protective coatings - Wall headers - Brackets - Anchor bolts - Steel bracing members (BR1 & S1) - Purlins (P1, P2, P3) - Purlin Brackets - Roof sheets - Roof insulation - Roof flashings - Adhesives - Fasteners | Structural Steel contractor Roofing Contractor |
| External Façade and doors - Install louvres to building (Austral Monsoon AME100HV) - Install Door frames (ST1) - Hang Doors / install door hardware | 25/07/2024 | 19/08/2024 | - Austral Monsoon AME100HV Louvres - Fixing Brackets - Fasteners - Protective Coatings - Sealants - Door Frames (ST1) - Anchor Bolts | Carpentry Contractor |
| Hydraulic rough- in / Fit off - Install pipework at high level and drop down to feed hose taps - Fit off hose taps and complete connection to inground 20 dia - Complete QA testing and monitor for any leaks. | 25/07/2024 | 30/07/2024 | - 20mm (20 dia) Pipe - Pipe Supports and Brackets - Pipe Insulation - Isolation Valves - Hose Taps - Tap Brackets / Mounting Hardware - Threaded Fittings / Compression Fittings - Temporary Blanking Plugs - Sealants | Plumbing Contractor |
| Electrical rough-in / fit off - Install electrical conduits and cable to feed emergency lighting, fans, controllers and lights etc. - Install new DB-XX and prepare for connection to existing MSB- 3083 - After hours- Conduct electrical cutover / connection to existing MSB-3083 - Connect all electrical appliances / accessories to new DB-XX - Complete testing and commissioning of all electrical elements | 25/07/2024 | 07/08/2024 | - Electrical Conduits - Electrical Cabling - Cable Trays and Supports - Fasteners, Clips, and Cable Ties - Junction Boxes & GPO Outlets - Distribution Board (DB-XX) - Circuit Breakers & RCDs - Busbars & Earth Links - Identification Labels & Circuit Schedules - Cable Lugs & Termination Kit - Heat Shrink Tubing & Insulation Tape - Earthing & Bonding Materials - Emergency Lighting Units - Ceiling Fans & Controller - Lighting Fixtures - Switches, Power Points & Control Panels - Test Reports & Compliance Documentation - Warning Labels & Signage - Spare Fuses & Breakers | Electrical contractor |
| Lockers Installation - Install existing lockers to new building (supplied by client) | 20/08/2024 | 20/08/2024 | - Lockers (Supplied by Client) - Fixing Brackets - Wall Plugs & Screw - Shims |  |
| Civil works and Landscaping - Prepare subgrade for new footpaths - Install base course and compact to nominated ratio - Prepare reinforcement and install framework - Pour concrete - Cut sawn joints in to new footpath - Install 750 dia rock protection channel - Makegood surrounding landscape damaged by construction works. | 01/08/2024 | 02/08/2024 | - Road base material - Water for dust control and compaction. - Reinforcement mesh - Formwork - Bar chairs - Ready-mix concrete - Curing compound - 750mm diameter rock - Geotextile underlay - Topsoil - Grass seed or turf - Mulch & plants | Civil and Landscaping contractors |

Contingency

| Summary of contingency | A material contingency of 12% has been allocated to cover unexpected supply delays, wastage, or changes in the project scope, ensuring that critical materials like concrete, steel, and pipes are available when needed. Additionally, a labour contingency of 12% is set aside to manage potential delays, absence, or unforeseen complications, ensuring sufficient workforce availability throughout the project phases. These contingencies provide a safety net, helping to keep the project on track and within budget. |
| --- | --- |
| Materials needed | Please see list of materials above. |
| Labour needed | Please see lists of labour above. |